## Template
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | Monthly Management Review - January 2026
Date: |  | 2026-02-20 |  |  | Start Time: |  | 10:00 |  | End Time: |  | 13:30 | Location: |  | SMSA UAE Head Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Yasser Zahreddine |  |  |  |  | COR |  |  | 1 | Sales Performance |  |  |  | Wadih Mattar
Maridel |  |  |  |  | COR |  |  | 2 | Finance Overview |  |  |  | Lalit Singhi
Wadih Mattar |  |  |  |  | SLS |  |  | 3 | Operations Performance |  |  |  | Dilhan Daskateer
Vidya Kunder |  |  |  |  | SLS |  |  | 4 | Freight Operations |  |  |  | Bilal Noor
Lalit Singhi |  |  |  |  | FIN |  |  | 5 | Logistics & Fulfilment |  |  |  | Mohamed Samir
Mohammed Samir |  |  |  |  | LOG |  |  | 6 | HR & People Metrics |  |  |  | Yathiraj Kotian
Dilhan Daskateer |  |  |  |  | OPS |  |  | 7 | Customer Service |  |  |  | Mir Taqi Ali
Bilal Noor |  |  |  |  | SFD |  |  | 8 | Country Manager’s Update |  |  |  | Yasser Zahreddine
Yathiraj |  |  |  |  | HRD |  |  | 9 | Projects & Initiatives |  |  |  | Yasser Zahreddine
Mir Taqi |  |  |  |  | CSD |  |  | 10 | Risk and Challenges |  |  |  | Yasser Zahreddine
Raghda Osama |  |  |  |  | SLS |  |  | 11
Richelle Zaldivar |  |  |  |  | SLS |  |  | 12
Khaled Taha |  |  |  |  | SLS |  |  | 13
11
12
13
14
15
16
17
18
19
20
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Sales Performance |  |  |  |  | Wadih Mattar |  | CM | Mgt | • LTL performance was on the lower side due to Sporter revenue not being captured. • Customer trend analysis to be conducted from November 2025 to January 2026. • Review and share updates on customers lost over the past three months. • Increased focus on cross-selling within the existing customer base. • Product-wise revenue distribution to be reviewed to improve diversification. • Update required on top downtrading customers. |  |  |  | On-going |  | 2026-03-04
2 | Freight Performance |  |  |  |  | Bilal |  | CM | Mgt | • FTL billing will be migrated to Logistas effective 1st February 2026. • EES movement commenced from 1st February 2026, with dispatch operations from DWC. • Continue the follow up closely with our Tec team and Dubai customs and update us until integration is done |  |  |  | On-going |  | 2026-03-04
3 | Customer Service – Risks & Challenges Slide |  |  |  |  | Mir |  | CM | Mgt | • Taqi to share the list and detailed points with Mr. Yasser for review on below, - Core tickets are being closed without proper action taken. - In cases where alternate contact numbers are provided to Operations, customers are still being contacted on old numbers. This has resulted in shipments being returned without attempting the alternate contact details. |  |  |  | On-going |  | 2026-03-04
4 | Country Managers – Key Focus Areas |  |  |  |  | Yasser |  |  | Mgt | • Stronger focus on B2B inbound business. • Review the decline in Air Freight product performance and identify root causes. • Identify major product challenges and implement a structured, sustainable solution. |  |  |  | On-going |  | 2026-03-04
5 | New Project – Infrastructure Expansion |  |  |  |  | Wadih Samir |  | CM | Mgt | Optimize fulfillment space by leveraging existing customer stock and creating capacity to onboard new customers |  |  |  | On-going |  | 2026-03-04
6 | New Project – DWC Gateway Activation |  |  |  |  | CM Wadih Samir |  | CM | Mgt | • Continue the work with Procurement and Mohd Samir to finalize all reequipments by Customs, including security staff within the moth of Feb • Get Customs inspection and approval to activate DWC as a gateway for transit as well as export |  |  |  | On-going |  | 2026-03-04
7 | New Project – Abu Dhabi Office |  |  |  |  | Khaled Yathiraj |  | CM | Mgt | Identify and secure a new office space in Abu Dhabi, preferably in a central location to support business expansion and ensure accessibility |  |  |  | On-going |  | 2026-03-04
8 | Logistas System Alignment |  |  |  |  | Wadih Vidya |  | CM | Mgt | • Logistas access to mirror ZOHO structure. • Any account created in ZOHO must reflect in Logistas and data between ZOHO & Logistas must match and be reviewed. |  |  |  | On-going |  | 2026-03-04
9
10
11
12
13
14
15
16
17
18
19
20
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 0% | 0
[15 empty] | On-going |  | 100% | 8
[6 empty] | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
[15 empty] | Completed |  | 0% | 0
[6 empty] | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 8
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.