## Form Tender
New Project Risk Identification Owner/ Department: ZAF- Commercial
Project Name |  |  |  | Overall Rating
Project Owner
Deadline |  |  |  | Project Accepted | Y N
Revenue Impact |  |  |  | * If accepted and once implemented the post activity needs to be completed.
New Project - Risk Identification
Pre - Activity |  |  |  |  | Post Activity
Elements of risk to be considered | Risk associated to this project | Impact on SMSA & RISK | How would you rate the impact of each element | How to avoid the risk impact without affecting service | What went well | What went wrong | What can be done differently/ Lessons Learnt | Review by
Deadline requirements | RFQ Submission Date
RFQ Questions Closing Date
Identify Scope Risk | Exclusive provision
Partial Provison of services
Any other scope risks
Legal / Commercial | Terms and Conditions of Contractual Agreement
Contractual Period
Penalty Clause / Liability
Duration of contractual agreement with option to renew
Subcontractors allowed
Administration Requirements
Financial | Profitability and ROI ( Return on Investment)
Customer Payment Terms
Capital costs
Billing Methodology
Rate Calculations and Costing
Manpower | Drivers
Drivers assistants
General Workers
In-house Personnel
Head Office Administration Personnel
Nature of Product | Nature of the product to be transported
Packaging of product
Vehicles | Vehicle Specifications based on Customer Requirements
Vehicle Availability
Facility | Customers facility
Namlog Branches
Operational | Customer Scope of Services
Commencement of contract date
Project Implementation Plan
Reporting requirements (Weekly, Monthly, Quarterly)
SLA | Customer Service Level Agreement requirements
EHS | Customer Environmental Health and Safety requirements
Security | Vehicle tracking and monitoring
Facility Security Management
Supplies | Material Handling Equipment
Risk on any other specific requirements
Special equipment | Driver Monitoring Devices
PDA (Portable Digital Assistant) devices
Process change | Customer Scope of Services Requirements
Truck delivery schedules (Namlog delivery network)
Information Technoligy Integration | Integration with Customers Information Technology Services / Programs
Marketing | Customer or SMSA branding requirements
H
M
L

## Form V2
New Project Risk Identification Owner/ Department: ZAF- Commercial
Project Name |  |  |  | Overall Rating
Project Owner
Deadline |  |  |  | Project Accepted | Y N
Revenue Impact |  |  |  | * If accepted and once implemented the post activity needs to be completed.
New Project - Risk Identification
Pre - Activity |  |  |  |  | Post Activity
Elements of risk to be considered | Risk associated to this project | Impact on SMSA & RISK | How would you rate the impact of each element | How to avoid the risk impact without affecting service | What went well | What went wrong | What can be done differently/ Lessons Learnt | Review by
Financial | Payment Terms Capital costs Duration of contract
Legal / Commercial | Contractual Agreement Penalty Clause
Manpower | Drivers In-house Personnel
Vehicles | Type of vehicles
Facility | Depending on the type of service Customers facility Other Namlog Branches
Operational | Customer Scope of Services: Start date for provision of services
SLA | Customer Service Level Agreement requirements
EHS | Customer Environmental Health and Safety requirements
Security | Vehicle tracking and monitoring
Supplies | Material Handling Equipment
Special equipment | Camera's PDA (Portable Digital Assistant) device
Process change | Customer Scope of Services
Marketing | Branding of Namlog vehicles
H
M
L

## Sample
New Project Risk Identification Owner/ Department: QRM
Project Name | KSA -Sample |  |  | Overall Rating
Project Owner
Deadline |  |  |  | Project Accepted | Y N
Revenue Impact |  |  |  | * If accepted and once implemented the post activity needs to be completed.
New Project - Risk Identification
Pre - Activity |  |  |  |  | Post Activity
Elements of risk to be considered | Risk associated to this project | Impact on SMSA & RISK | How would you rate the impact of each element | How to avoid the risk impact without affecting service | What went well | What went wrong | What can be done differently/Lessons Learnt | Review by
Financial | SMSA rate not meet customer expectation | Loss of revenue Business loss |  | Study market index Ensure price/service levels are reasonable | SMSA provide reasonable price comparing with service provided | N/A | Study RFP carefully before processing the financial proposal
Legal | Contract draft review | Additional commitments, loss of revenue |  | Review the terms and conditions of the contract legally | Comprehensive review to contract with Legal department before summit to customer | N/A | The importance of the recommendations of the Legal Department
Manpower | Manpower shortage | Delay start-up of the project |  | Need to hire project staff in timely manner / provide sufficient training | Share with HR to conduct interviews / prepare action plan to finalize appointment papers | N/A | Establish communication channels with HR / Participation of project manager in appointment interviews
Vehicles | Delay delivery of project vehicles | Delay start-up of the project |  | Determining the specifications and numbers of cars required according to the scope of the work | Fleet dept., to coordinate with rental company to supply of cars in a timely manner | N/A | Action plan to be established
Facility | Difficulties in performing work | Impact quality of service |  | Identify project requirements then configure the place to accommodate the needs to work smoothly | Visit the site and request the necessary modifications as per business requirements | N/A | Prior coordination with customer and requests for modifications before starting the project
Operational | Operation failed | Failed in performance/Not meeting customer expectation |  | Knowledge of business requirements/Establish professional operation plan | Implementation of the operational plan efficiently | N/A | Apply the demo run
SLA | Shortages of service | Non-compliance with agreed scope of the work |  | Establish and implement a professional SLA | Processing SLA in conjunction with the operation plan | N/A | SLA part of SOW
EHS | Difficulties in performing work | Quality of service |  | Working with the recommendations and guidance of the quality department | An appropriate working environment helps to perform better | N/A | Convince the client of the importance of applying rules of EHS
Security | Safe working environment | Quality of service |  | Establish effective security system / information security | The workplace is equipped with safety systems & surveillance cameras | N/A | Identify security concerns
Supplies | Shortages of service | Impact quality of service |  | Provide adequate quantities of supplies according to business need | Bank provided store room to keep sufficient balance of supplies | N/A | Equip a store room in the project to accommodate materials & supplies
Special equipment | Not meeting customer expectation | Impact quality of service |  | Study customer needs as per business requirements | Provide the project with the required equipment based on prior knowledge of the customer needs | N/A | Find alternative solution
Process change | Customer complain | Impact quality of service |  | Monitor activities | N/A | N/A | -
Marketing | Affecting Revenue | Loss of revenue |  | Promote marketing / Marketing study | N/A | N/A | -
H
M
L
H
H
M
M
M
H
L
M
L
M
M
H
H
H