## Template
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | MANAGEMENT MEETING
Date: |  | 2021-12-09 |  |  | Start Time: |  | 10:00 |  | End Time: |  | 12:30PM | Location: |  | SMSA Dubai Head Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Yasser Zahreddine |  |  |  |  | COR |  |  | 1 | Wheel - November 2021 |  |  |  | Yasser Zahreddine
Amir Ebadda |  |  |  |  | SLS |  |  | 2
Lalit Singhi |  |  |  |  | FIN |  |  | 3
Mir Taqui |  |  |  |  | CSD |  |  | 4
Yathiraj Kotian |  |  |  |  | HRD |  |  | 5
Justin Kuriakose |  |  |  |  | SFD |  |  | 6
Nigil Davis ( Absent) |  |  |  |  | SFD |  |  | 7
Dilhan Daskateer |  |  |  |  | OPS |  |  | 8
Sameer Salauddin |  |  |  |  | ITD |  |  | 9
Maridel Loretizo |  |  |  |  | COR |  |  | 10
11
12
13
14
15
16
17
18
19
20
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | DIGITALIZATION 1.0 Dimensional Weight System ( DWS ) 2.0 Scanning Machine ( ADAFZA ) / Rapiscan 3.0 POS System |  |  |  |  | Yasser/Dilhan/Mir | Yasser/Dilhan/Mir | MGMT Team | MGMT Team | DWS is operating properly and all SMSA inbound and outbound shipments are re-weigh , we are streamlining some of the dimensional issues that arte related to SMSA pouches shipment to avoid the over charges . |  |  |  | On-going
2 | NEW INFRASTRACTURE 1.0 HUB and Station - Ajman 2.0 Al-Ain Station and SSC |  |  |  |  | Yasser/Dilhan/Mir | Yasser/Dilhan/Mir | Yasser | Yasser | Lease Improvement is on-going and 75% of the project is finalized , expected to finish by end of DEC |  |  |  | On-going
3 | TAPA CERTIFICATION |  |  |  |  | M Samir/Yasser | M Samir/Yasser | Yasser | Yasser | Payment been processed and work in under for the required documents with air port authority for permits. |  |  |  | On-going
4 | BUSINESS EXPANSION 1.0 Al Ain - SSC |  |  |  |  | Mir/ Yasser | Mir/ Yasser | Yasser | Yasser | Staff recruitment is already proceeded and SSC in Al-Ain expected to operate by Jan 22 . |  |  |  | On-going
5 | REVENUE |  |  |  |  | MGMT Team | MGMT Team | MGMT Team | MGMT Team | YTD Achieved 92% |  |  |  | Not started
6 | COLLECTIONS |  |  |  |  | MGMT Team | MGMT Team | MGMT Team | MGMT Team | YTD Achieved 95% |  |  |  | Not started
7 | ECOM System |  |  |  |  | Mir Taqui/Amir Ebadda | Mir Taqui/Amir Ebadda | Fathi-KSA | Yasser | A conference call with Fathi was initiated by Mr. Mir and Mr. Amir reagrding related to system progress. They found some gaps in system which will be discussed further with CGM. System is under 2nd phase of development |  |  |  | On-going
8 | RETAIL System |  |  |  |  | Mir Taqui | Mir Taqui | Fathi-KSA | Yasser | Following up with Fathi & Team to get a daily system generated reports for SSC & finance department. This was pending since Mohammed Zakariya was on leave. He joined back last week. Follow up is done with IT Dept to have Reports. |  |  |  | On-going
10 | [13 empty] | Not started
11 | [13 empty] | Not started
12 | [13 empty] | Not started
13 | [13 empty] | Not started
14 | [13 empty] | Not started
15 | [13 empty] | Not started
16 | [13 empty] | Not started
17 | [13 empty] | Not started
18 | [13 empty] | Not started
19 | [13 empty] | Not started
20 | [13 empty] | Not started
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 68.42% | 13
[15 empty] | On-going |  | 31.58% | 6
[6 empty] | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
[15 empty] | Completed |  | 0% | 0
[6 empty] | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 19
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.