## Template
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | IBU Management Meeting with Ibu Director Mr. Mohannad Khayyat
Date: |  | 2024-01-19 |  |  | Start Time: |  | 14:00 |  | End Time: |  | 17:00 | Location: |  | SMSA UAE Head Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  | Time
Mohannad Khayyat |  |  |  |  | COR |  |  | 1 | UAE Wheel - Dec2023 |  |  |  | Yasser Zahreddine |  | 14:00
Yasser Zahreddine |  |  |  |  | COR |  |  | 2 | Strategy 2024-2026 |  |  |  | Mohannad Khayyat |  | 15:00
Amir Ebadda |  |  |  |  | SLS |  |  | 3
Lalit Singhi |  |  |  |  | FIN |  |  | 4
Justin Kuriakose |  |  |  |  | SFD |  |  | 5
Nigil Davis |  |  |  |  | SFD |  |  | 6
Dilhan Daskatter |  |  |  |  | OPS |  |  | 7
Mir Taqi |  |  |  |  | CSD |  |  | 8
Yathiraj Kotian |  |  |  |  | HRD |  |  | 9
Mohamed Samir |  |  |  |  | COR |  |  | 10
Andeel
11
12
13
14
15
16
17
18
19
20
SN. | Action Item |  |  |  |  | Responsible Person |  |  |  | Action Taken/ Remarks |  |  |  | Status | Deadline
1 | UAE Training |  |  |  |  | Yathiraj/ Mr. Yasser ( Review) |  |  |  | * Prepare training calendar *Customize training per department |  |  |  | On-going
2 | Introduce New Service Code - ITP System |  |  |  |  | Amir/Nigil |  |  |  | Send requirements for ECOM System |  |  |  | On-going
3 | Update Payment Portal Landing from KSA to UAE |  |  |  |  | IT-KSA/ Mir/ Dilhan/Lalit |  |  |  | Coordination with Finance KSA and IT to work on that. |  |  |  | Not started
4 | Review ICBR -Fulfillment |  |  |  |  | Mr. Mohannad/Mr. Yasser |  |  |  | Review the fulfillment set-up |  |  |  | On-going
5 | Technology 1. Gateway integration 2. Smartship 3. Door to Door |  |  |  |  | Justin/ Dilhan |  |  |  | 1. Intergration - Implementation of ERP System 2. Smartship - Coordinate with Kashan( IT¦ to change the location and currency, confirm the content and marketing campaign to proceed. 3. Door to Door - Check website details anything to be amended with Terms & condition and Portal. |  |  |  | On-going
6 | Strategy 2024-2026 |  |  |  |  | UAE Management |  |  |  | To send Strategy Meeting Attendance to Mr. Mohannad and Mr. Bhaiyat |  |  |  | Completed
11
12
13
14
15
16
17
18
19
20