## HRD (hidden)
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date | Action Taken
Manual reporting and record keeping | Inconsistency in data entry,lack of security ,time consuming and costly to produce reports. |  |  |  | DXB-HRD | Implementation of HRIS system |  |  |  | Risk has increased more , due to enlarged no.of new hired employees. | H | 2019 | After raised the request for implamentation for HRIS systen still no action taken.
Uncompetetive salary scheme with other competetitors (Basic Salary) | Loss of a best employees of the company. |  |  |  | DXB-HRD | Increase the basic salary scale. |  |  |  | The risk might be increased in a couple of monts. | H | 2019 | No action taken.
Inadequate salaries for rise of living cost and market inflation | Tediousness of the employees to do there job . |  |  |  | DXB-HRD | Increased the salary based on their work load. |  |  |  | The risk has elimited | H | 2019 | Increament as per the KPI's has implemented.
No local POA (restricted services only) | Delayed of work which necessary for the things to be done in the period of time. |  |  |  | DXB-HRD | Approval should be administered in a short period of time. |  |  |  | Work delays procedures/process were expected. The risk might increase if not monitor. | H | 2019 | Limited approving in a relevant matter should applied.
Lenghty process and manual documentation for recruitment and financial approvals | Fines , and delayed of work in processing recruitment and renewals. |  |  |  | DXB-HRD | Process for financial approval should be done within 2 days only to avoid any delays and fines. |  |  |  | The risk will be decreased if the approvals provided within 2 days. | H | 2019 | No action taken.
Petty cash unavailability for government related activities, fleet and procurement. | Work-delays , and fines , lenghty process of all related matter. |  |  |  | DXB-HRD | Providing enough petty cash in the deparment. |  |  |  | The risk will be decreased if there is petty cash to be handled by the department head. | H | 2019 | NO action taken. Risk still the same and it might increased.
Loss of data | Distrupts the day to day function of any information-based business. |  |  |  | DXB-HRD | Providing proper management of data base (SOFTWARE) . |  |  |  | Need to provide proper management of data base so that the risk will be eliminated. | H | 2019 | No action taken.
Loss of qualified candidates for vacancies | Never attain good quality of working and unqualified candidate can cause failure & damage of the company |  |  |  | DXB-HRD | Proper background checking and excelent recruitment process should be done. Giving right offer package in the right position. |  |  |  | The risk has eliminated. | H | 2019 | Candidates well screened as well following the right hiring process.
Unproductive and demotivated staff | Employee will do minimal best , ultimately could have a negative effect on the entire team's productivity adn will affect corporate culture and company status. |  |  |  | DXB-HRD | Implementation of CAFO , increament and incentives scale |  |  |  | The risk has eliminated. | M | 2019 | CAFO , and PAF has inisiated.
Penalties and fines due to Government regulation changes | Work-delays , and fines |  |  |  | DXB-HRD | Awareness and monitoring UAE rules and regulation in weekly basis. |  |  |  | Risk has eliminated. | M | 2019 | Any changes and new rugulation in the government are contious monitored.
Late payments, bad debts, and loss of vendor relation and confidence | Late payments to vendor or suppliers are disrespectful and it will leads to break a trust between the company and vendor. |  |  |  | DXB-HRD | Monitoring the due date for all the payments. |  |  |  | N/A | M | 2019 | All payments and debts has been monitored .
H
M
L

## ADMIN (hidden)
Risk Assessment Department: Information Technology - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date |  | Action Taken
No centralized Admin in-charge | Unable to monitor and control cash flow on time. |  |  |  | DXB-HRD | Case study and assessment of factors that get affected based on the lack of Admin in-charge. Deployment of Admin-in-charge based on the manpower planned. |  |  |  | Lack of organizational harmony. The risk remained the same. | H | 2019 |  | No action taken.
No AMS's for facilities | Unable to comply with EHS policy due to lack of air cooling units inside the warehouse during summer. |  |  |  | DXB-HRD | Approved vendors with AMCs and timeline commitment on service delivery to be set. |  |  |  | Appointed Executive Administrator to facilitate the AMC's. | M | 2019 |  | Assigned to Executibe Administrator to find the AMC's for all facilities.Amenity has been provided.
Inadequate storage for Admin inventory | Customer claims and an negative impact to service levels |  |  |  | DXB-HRD | Assess requirement and allocation of space for Admin inventories. |  |  |  | Satisfactory for the space provided . The Risk has been eliminated. | L | 2019 |  | Space for inventory storage keeping in a safe place and easy to access .
Unstreamelined processes and policies | Business continuity, brand image, lost of trust from suppliers. |  |  |  | DXB-HRD | Analyzation of processes and authority levels |  |  |  | The Risk has been reduced | M | 2019 |  | Simple way and effcient policies has been created and implement.
No disaster recovery plan and contingeny | Lost data system outage, service level and business continuity |  |  |  | DXB-HRD | Case study and assessment of factors that get affected based on the lack of contingency planning. Development of contingency plans. |  |  |  | The Risk remain the same. | H | 2019 |  | No action taken.
Loss of assets | Business continuity and revenue loss |  |  |  | DXB-HRD | Deployment of Admin-in-charge and assessment of requirement. |  |  |  | The Risk might be increase Admin-In-charge is a backbone of an organization and it is a very impportant role which we need to fill in. | H | 2019 |  | No action taken.
Fines and penalties related to facilities | Brand image, and business continuity |  |  |  | DXB-HRD | Analyzation of processes and authority levels and proper AMCs and maintenance of approved vendors. |  |  |  | The risk has been decreased | M | 2019 |  | Continous monitoring of proper AMC's and maintenance for better result by the concern personnel.
Inventory loss and damages | Business continuity and revenue loss |  |  |  | DXB-HRD | Deployment of Admin-in-charge and assessment of requirement. |  |  |  | The Risk is remain the same. | H | 2019 |  | No action taken.
H
M
L
H
M
L

## SLS (hidden)
Risk Assessment Department: Information Technology - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date |  | Action Taken
Non competetive express rates | can not compete in the market to win express volumes |  |  |  | DXB-SLS | find another vendors with better rates as well as to promote SMSA countries (BH-EG) |  |  |  | N/A | 1 | 31st DEC |  | In Process to finalize new vendor
Delay in Invoicing and COD remittance | invoice delay affecting SMSA collecting the outstanding from the market and losing revenue and clients by not remitting customers on agreed cycle. |  |  |  | DXB-SLS | Finance working on both sides to invoice and remitt COD on time |  |  |  | N/A | 1 | N/A |  | Risk is been reduced in term of COD remittance however still delay in invoicing is happening and Finance working to eliminate both risks
Staff salaries not in line with competetion/market | Affect the productivity and hiring experienced people from the industry, so fresh graduate is always the solution |  |  |  | DXB-SLS | Atractive commesion scheme as well as training's to be given to new staff |  |  |  | N/A | 3 | N/A |  | Staff Grading and salary Adjustmenets have been done and this risk does not exsist anymore
Brand visibility and marketing | less knowledge about the brand in the market from customers, and affecting the selling point as well |  |  |  | DXB-SLS | some social media and increasing opening new retails or promotions in social places (Malls-Metro, sponsor one of the events in the UAE, etc) |  |  |  | N/A | 3 | N/A |  | A New Retail store is been opened in RAK as well new operation in umramol, and sponsored one event for Phillipine independence day
Air and sea freight rates and connection | can not secure any regular volumes due to high rates and can not develop the product |  |  |  | DXB-SLS | need to develop the product with new connections and new vendors with competitve rates |  |  |  | N/A | 2 | N/A |  | a new freight manager has been recruited and the risk has reduced however still competitive rates and vendors has to be established
Recession and business pressure | Volumes drop, reveue drop as well will increase the risk of outstanding collection in the market |  |  |  | DXB-SLS | Validation of contracts, cash in advance for prepaid, and remittance invoice deduction from COD |  |  |  | N/A | 1 | N/A |  | Risk has reduced because of the intiatives mentioned however the risk still remains due to the market condition
Recruitment and staff retention | Recruitment of low quality candidates due to non competitve salaries, and no insentive, which is affection retention as well |  |  |  | DXB-SLS | Atractive commession scheme, and to set career path for current achievers and productive employees |  |  |  | N/A | 3 | N/A |  | Salaries adjustmenets and grading reviews has reduced the risk however comission scheme has still to be approved by HO
Customs regulation changes (Saudi & UAE) | loss of accounts due to the sudden decisions happens in KSA customs which leads to destroy or return the shipments |  |  |  | DXB-SLS | SMSA KSA to keep DXB posted with all new regulations once implemented |  |  |  | N/A | 1 | N/A |  | any changes been monitored and delt accordingly
Competetion price war for Saudi sector | decline in revenue and volumes |  |  |  | DXB-SLS | Promote new product by road with competitive rates,promote countries EG & BH, as well focus on road and air freight |  |  |  | N/A | 1 | N/A |  | a new product has been announced and risk is been reduced however Road and air freight still under development and competition of rates in market is still high
Major revenue generated by 10% customers | creates a very high risk of revenue drop incase of losing any of the major clients |  |  |  | DXB-SLS | Launch new products as Domestic, EES, and warehousing as well as finalizing contract with new vendor for worldwwide Express to increase the data base and generate sustainable volumes from SME's |  |  |  | N/A | 1 | N/A |  | Risk is been reduced as new big clients came on board how ever the new launched services still new and under prospecting to generate new business from SME's
Vat impact on majority of E-commerce cusotmers in UAE | customers started to open fulfillemnts and rent warehouses in ksa to avoid paying vat twice, volumes and revenue affected |  |  |  | DXB-SLS | focus on UAE domestic products and projects |  |  |  | N/A | 1 | N/A |  | Risk is still Active and Domestic product is launched however due to high competion in rates we haven't been able to eliminate that risk complitley
E-commerce customers moving to KSA for cost cutting and customs procedures reduction | less monthly volumes going out from dxb to ksa and less revenue as well |  |  |  | DXB-SLS | Focus on the domestic COD and projects aside road freight |  |  |  | N/A | 1 | N/A |  | Risk is still Active and Domestic product is launched however due to high competion in rates we haven't been able to eliminate that risk complitley
H
M
L
H
M
L
H
M
L
H
M
L

## Risk FIN
Department Name | Finance |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
No local POA holder for banking transactions | Delays the Banking work |  |  |  |  | UAE-FIN | Need to have an authorised person with POA locally in UAE |  |  |  |  | Director Finance to take the decision |  |  |  | 2021-12-31
Lack of co-ordination among departments over area of responsibilities with regards to customers | Duplication of work and unwanted follow ups |  |  |  |  | UAE-FIN | Understanding of departmental process and clear communication through emails. | [8 empty] | 2021-06-30
Open credit policy | Aged Account Receivable and increase in bad debt |  |  |  |  | UAE-FIN | Deactivation of account on non-payment for 60 days. Regular follow-up and sending dunning letters and finally sending it to legal if non response from customer. |  |  |  |  | Set the credit limits in system and auto deactivation of account on reaching credit limit or non-payment for 60 days. Link this to Ops system to give alert on shipment pick up. |  |  |  | 2021-06-30
No system to track the customer query aging and response timing | Aged Account Receivable and delay in taking action |  |  |  |  | UAE-FIN | Setup of ticketing system with a timeline to resolve the issue and get the necessary approval through system. Target timeline shall be 4 working days. |  |  |  |  | IT & CS to initiate the project for issuance on automated tickets to track & close the customer queries. |  |  |  | 2021-06-30
Weak IT infrastructure to support the system continuity and old machine for employees to work-on | Delays in report generation, increases the timeline to finish assigned task. This results in late sitting by employees. |  |  |  |  | UAE-FIN | Deployment of up to-date IT system and retirement of old machine every 3 years. |  |  |  |  | IT to identify the infrastructure redundancies and deploy the latest technical know-how. |  |  |  | 2021-06-30
Slow network connectivity impacting department efficiency due to disruption in system connectivity | Delay in completion of day to day task, inefficient |  |  |  |  | UAE-FIN | Over UT network shall be revamped in-line with increasing business need. |  |  |  |  | IT to identify the infrastructure redundancies and deploy the latest technical know-how. |  |  |  | 2021-06-30
Unscheduled OS update rendering the machine non-responsive | Kills around 2 hours when happens and make the employee unproductive |  |  |  |  | UAE-FIN | Such updates need to be pre-scheduled between mid-night and morning 8AM and should be informed through email to all the users to keep their system open while leaving the workplace. | [8 empty] | 2021-06-30
Manual Invoicing leading to loss of revenue due to incorrect update of billing parameters | Delay invoicing, pron to errors, does not meet customer requirement. |  |  |  |  | UAE-FIN | Setup of automated billing system linked with Ops system to capture correct parameters | [8 empty] | 2021-06-30
Write off due to vulnerable customer base & non-compliant signatories/ POAs | Increased bad debts & legal issues |  |  |  |  | UAE-FIN | Process shall be in place while on-boarding the customer and shall be followed strictly by all the stakeholders. |  |  |  |  | KSA Management to put standard policy for all the IBUs. |  |  |  | 2021-12-31
Delayed in COD report due to inefficient IT system & remittance issues | Incompetent compared to local Industry players, loss of customers |  |  |  |  | UAE-FIN | COD report shall be send automatically thru system by end of each cycle period to customers. IT to put this in place. |  |  |  |  | KSA Management to take decision |  |  |  | 2021-12-31
Weak/ incompetent IT system compared to Industry standards | Inefficiency on day to day work, increase manual task of employees |  |  |  |  | UAE-FIN | Over UT network shall be revamped in-line with increasing business need. |  |  |  |  | KSA Management to take decision |  |  |  | 2021-12-31

## FIN (hidden)
Risk Assessment Department: Information Technology - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date |  | Action Taken
Lack of control to ensure the billing completeness | Loss of Revenue and impacts the profitability of the company |  |  |  | DXB-FIN | Monthly billing reconciliation to avoid the non-billing of AWBs | [5 empty] | 2019-05-31
No local POA holder for banking transactions | Delays the Banking work |  |  |  | DXB-FIN | Need to have an authorised person with POA locally in UAE |  |  |  | Director Finance to take the decision |  | 2019-12-31
Last minute submission and payment for Empost quarterly return | Penalty on late payment and loss of confidence |  |  |  | DXB-FIN | Timely close of billing to prepare the computation on time and send the request for payment approval to KSA management. | [5 empty] | 2019-07-31
lack of coordination among team and departments | Duplication of work and unwanted follow ups |  |  |  | DXB-FIN | Understanding of departmental process and clear communication through emails. | [5 empty] | 2019-12-31
Open credit policy | Aged Account Receivable and increase in bad debt |  |  |  | DXB-FIN | Deactivate the account on non-payment for 90 days. Regular follow-up and sending dunning letters and finally sending it to legal if non response from customer. | [5 empty] | 2019-07-31
Manual Invoicing | Delay invoicing, pron to errors, does not meet customer requirement. |  |  |  | DXB-FIN | Setup of automated billing system | [5 empty] | 2019-12-31
Delay in resolution of customer discrepancy | Delays the payment and multiple follow-ups resulting into inefficiency. |  |  |  | DXB-FIN | Setup of ticketing system with a tineline to resolve the issue and get the necessary approval through system. |  |  |  | IT & CS to initiate the project for issuance on automated tickets to track & close the customer queries. |  | 2019-12-31
Weak IT infrastracture to support the system continuity and old machine for employees to work-on | Delays in report generation, increases the timeline to finish assigned task. This results in late sitting by employees. |  |  |  | DXB-FIN | Deployment of upto-date IT system and retirement of old machine every 3 years. |  |  |  | IT to identify the infrastructure redundencies and deploy the latest technical know-how. |  | 2019-12-31
Unscheduled OS update rendering the machine non-responsive | Kills around 2 hours in the morning and make the employe unproductive |  |  |  | DXB-FIN | Such updates need to be pre-scheduled between mid-night and morning 8AM and should be informed through email to all the users to keep their system open while leaving the workplace. | [5 empty] | 2019-12-31
License continuity due to non compliance to Empost | Non-complaince can result into fines and penalties. Also, loss of confidence in brand SMSA amoung local authorities. |  |  |  | DXB-FIN | Billing need to be closed fully on-time by 10th of every month to ensure the quarterly filing by 15th of month subquent to qurter end along with payment transfer. | [5 empty] | 2019-07-31
FTA penalty on FY18 vat filings | Non-complaince can result into fines and penalties. Also, loss of confidence in brand SMSA amoung local authorities. |  |  |  | DXB-FIN | Correct booking of vendor invoices and customer invoicing need to be streamlined. | [5 empty] | 2019-02-28 |  | Accountants are booking the vendor invoices correctly and VAT recon is being done on each filing. Also, the VAT filing is reviewed thoroughly before submission.
Lost customers and brand image due to non payment | This may result into decrease in customer base and difficult to get new customers onboard. |  |  |  | DXB-FIN | System to track and approve the dispute raised by customers. Regarding vendor payments, local apporval upto certain limit or regular vendors after necessary voucher approval by KSA. | [5 empty] | 2019-09-30
Delayed customer COD remittance and cash flow | This may impact the development of domestic UAE market. |  |  |  | DXB-FIN | Local banking approval for domestic COD remittance upto certain limit or timebound approval in Banking system. |  |  |  | KSA Management to take decision |  | 2019-12-31
Loss of trained resources | New resource takes time to settle down and also this will result into duplicate efforts on training by existing staff. |  |  |  | DXB-FIN | Career progression plan, staff training, systematic working within the job role, automation of system, and improved IT infrastructure. | [5 empty] | 2019-09-30
Resources back-ups are not ready | Work back log will build up in absence of normal staff, delay in work and risk of error while accomplishing the task. |  |  |  | DXB-FIN | All the new resource will be trained with backup task once they settle in their respective profile. Also, before going on leave, the employee need to ensure the proper backup and handover is being done. | [5 empty] | 2019-12-31
Significant dependency on ENBD bank considering previous experiences | All the vendor and staff related payment will be delayed. Also, customer receipts cannot be utilised. This will bring imbalance to working capital management. |  |  |  | DXB-FIN | We're strengthening our banking relationship with Mashreq Bank. We may also explore our reltionship with another bank if required. | [5 empty] | 2019-12-31
H
M
L
H
M
L

## RTL (hidden)
Risk Assessment Department: Retail - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date | Action Taken
Non Availability of Replacement staff | Labour compliance and overtime |  |  |  | DXB-RTL | Restructuring of retail manpower |  |  |  | The risk has been eliminated. | M | 2019 | There are currently (6) available Retail staff hired but we must needs one floater to cover in case of any emergency or during retail staff leave period
Reconciliation of cash between RTL & FIN | Security issue |  |  |  | DXB-RTL | Daily banking of cash or cash collection by courier from retail to finance |  |  |  | Process needs to be streamlined with FIN | M | 2019 | its already done and every day RSC's sending complete report to finance
Non Availability of Secured Storage Area | Security of shipments |  |  |  | DXB-RTL | Additional locking provision for store |  |  |  | Limited space in Dragon Mart RSC | H | 2019 | Racks have been installed inside the storage area for booked shipments.
Retail to STN Connectivity | Delayed connectivity and transit time |  |  |  | DXB-RTL | Operational route planning |  |  |  | N/A | L | 2019 | Courier assigned to visit on a daily basis but is SHJ RSC station agent and courier staff are available from month of june.
Mall Timings beyond SMSA standard operating hours | Labour compliance, overtime, and fines |  |  |  | DXB-RTL | Additional resource planning |  |  |  | N/A | M | 2019 | Conducted a meeting with the mall management regarding timing change based on our business requirement but they refused as per their mall policy. Retail staff have been given ROTA to cover the mall timings.
H
M
L

## OPS (hidden)
Risk Assessment Department: Information Technology - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date |  | Action Taken
Less manpower with large geographical coverage | Less productivity, commitment failures and staff retention |  |  |  | UAE-OPS | Route and Resource planning |  |  |  | Route planning implemented and resources been assigned accordingly |  | 15 July'2019 |  | New positions were approved in budget and route planing been implemented. CGM had approved to keep initial monthly incentives at AED 500.00 per month until volumes builds for new coutiers from this year.
Lack of complete UAE service coverage own by SMSA | Losing edge with competitors |  |  |  | UAE-OPS | Operate new stations and destribution set ups |  |  |  | New operations begun in AUH, SHJ and 3rd party deliveries in ODA/NSS for key accounts customers. | M | 2019 |  | New SHJ and AUH will have suffecient routes/resouces to cover daily deliveries without negative impacts. DXB station2 will be plaanned after September.
Late flight arrivals from KSA | Unable to improve delivery commitments other parts of UAE apart of DXB and SHJ. |  |  |  | UAE-OPS | Exploring new flight connections from RUH and JED. |  |  |  | Airlines has no plans to add new flights to these sectors. Inadequite to match transit times to continue. | M | 2019 |  | KSA-DXB operations are awaits for any possibility of having a flight short cutoff time(less than 4 hours) to the FLT ATD.
Manual reporting | Inaccuracy in reports in service levels and management analysis |  |  |  | UAE-OPS | CORE reports enhancement |  |  |  | CORE management system share daily & monthly performance reports to every station. | L | 2019 |  | CORE personalized reports to UAE operations. (Station, Courier and Daily Pick up booking channels)
Screening of export shipments | Undeclared DG causing non-compliance with GCAA and airline could result for fines and suspention of license. |  |  |  | UAE-OPS | Procuring of a x-ray machine and setting up GCAA authorized cargo screening system. |  |  |  | Manual process to reduce risk | M | 2019 |  | All couriers been trained and coached in package acceptance. Discription will be cheked during pick up and processing for connection. Export Manifest will be checked by supervisor randomly. DG area set up within Umm Ramool warehouse to be intiated. Items containing Lithium batteries will be seperated from the rest of the packages and sent to destination under ELI declaration as per GCAA requirement.
Manual handling of sorting outbound packages | Delay and process and packages at risk for damages |  |  |  | UAE-OPS | Implementing conveyor belts at specified location(HUB & LH ) |  |  |  | A conveyor with in motion system been introduced and waiting FIN, CORE and IT to give their inputs to finalize the procurement of the unit. |  | 15 Oct'2019 |  | Sent technical details to each Dept/Section head for the review and idea.
Insufficient volumes to justify courier productivity | Unable to meeting given targets for couriers |  |  |  | UAE-OPS | Expand the delivery commitment time to 21:00 for B2C deliveries. |  |  |  | Delivery commitment for B2C been extended and reflecting in CORE report. |  | 15th June'2019 |  | Now couriers could deliver B2C shipments after duty of to increase stops.
Unavailability of temperature control vehicles | Risk of having higher number in damage claims and customer complaints for delivering items that should be under temperature control during summer. |  |  |  | UAE-OPS | Insulate all existing vehicles to reduce the heat inside the vehicle and rent new vehicles with temperature control units. |  |  |  | Vehicles been equipted with pallets and expose the shipments to aircon to reduce the temperatue. |  | 15th Apr'2019 |  | All new vehicles to be with temperature controlled units. Vehicle requests will follow as same.
Lack of equipment's to handle heavy or high volumes | Causing delay and need to deploy more manpower to handle loading and offloading. A negative impact to EHS. |  |  |  | UAE-OPS | Avail a Forklift and hydraulic jack lifters to handle heavy and palletize shipments. |  |  |  | 2 Hydralic jack lifters provided and processing on quotations for stacker under way. |  | 15 Oct'2019 |  | New quotations
Staff retention | Losing trainind and experience employees and reduce productivity. |  |  |  | UAE-OPS | Incentive programs and staff motivaions |  |  |  | New incentives for frontline been introduced as per their monthly achivements in stops and targets. Similaraly for other staff based on yaarly KPI. | L | 2019 |  | Incentive scheme for frontline been processed and staff start receiving in their salary.
Domestic Third-Party network(security, brand image and competetive advantage) | Expand service areas within UAE |  |  |  | UAE-OPS | Risk to reduce with new Operation setups in AUH, SHJ and Al-Ain. |  |  |  | AUH and SHJ new set up with new frontline under a route e plan and extended facility will reduce the 3rd party deliveries and pick ups. Al Ain will be served from DXB until new facility in place. | H | 2019 |  | New hiring and vehile request are under way. New location had begun operating in SHJ, AUH and Al-Ain.
Change in customs regulation for import/export | Clearance delay, Transit time, increased resources and additional operatinal cost. |  |  |  | UAE-OPS | Forward contigency plan for line haul |  |  |  | Risk iliminated with approperiate action taken. | L | 2019 |  | LH from Sharjah airport gegun and running smoothly. On road connections via Bahtha to KFIA succsessful and implemented in HUB&Spoke plan.
Lack of system support to meet custom to meet customs requirements | Additional manpower, errors due to manual uploads and penalties due to non - complian ce |  |  |  | UAE-OPS | IT Integration with Customs system |  |  |  | Customs hasn’t made it as a compulsory for courier mode shipments. Indeed we need to involve IT on the integration if the implementation of system integration become mandatory. | M | 2019 |  | Present submissions are exceptable for courier mode and process moving on smoothly. No risk been identified on the factor. IT for online manifest should be rechecked and integrated.
DCAA Non-compliance may result to suspension of license or heavy fines (Undeclared DG) | Shipments contents Lithum batteries or implanted considered as DG category. |  |  |  | UAE-OPS | Separate Lithium battery implanted shipments and Implement ELI certification/Statement from a DG certified agent to process the connection separate MAWB. |  |  |  | A DG certify entity by GCAA controls the loads with a statement to airline | M | 2019 |  | DXB HUB will process all Lithium battery devices shipments vis G9 undertaken statement and processing by the entity.
Lack of automated reports on cash outstanding on time | Unable to monitor and control cash flow on time. |  |  |  | UAE-OPS | Finance to implement an outstanding report to OPS on weekly basis and resolve the OS within a time frame. |  |  |  | A cahier been assigned to control cash flow on remittance and maintain a report to iddentify outstanding and to resolve within short time. |  | 31 Mar'2019 |  | Cashier at URO warehouse closely monitoting and taking immediate action on outstanding.
Lack of temperature control units available in DXB warehouse | Unable to comply with EHS policy due to lack of air cooling units inside the warehouse during summer. |  |  |  | UAE-OPS | Requesting to purchase additional air coolers suitable for warehouse before summer begins. Also to add air curtain to external main entrance. |  |  |  | CGM approved for 2 more new air coolers for warehouse |  | 30 Jul'2019 |  | LPO issued by finance to vendor
Lack of control over lost shipment between airports | Customer claims and an negative impact to service levels |  |  |  | UAE-OPS | To use boxes or untearable mother bags. |  |  |  | Boxes were used for devices and and double bags for RUH. Most of the valuable shipment sent to DMM-KFIA instead RUH. Much improvement noticed. |  | 30 Apr'2019 |  | Shipments mobiles and HV items consolidated in boxes instead plastic bags. Reduced such shipments to RUH gateway.
H
M
L

## ITD (hidden)
Risk Assessment Department: Information Technology - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date |  | Action Taken
Remote locations not connected to SMSA network | Critical business communication link |  |  |  | UAE-ITD | VPN Firewall Connectivity between remote location |  |  |  | The risk has been eliminated | L | 2018 |  | Umm Ramool and new HO is connected to HQ.
Poor response time for ISPs | Downtime |  |  |  | UAE-ITD | Manage contact and escalation levels with service providers and analyze wireless connectivity options(account manager-Dream Com) |  |  |  | N/A | M | 2018 |  | Close relationship with the channel partners is being maintained to resolve any issues on priority.
Lengthy process of management approvals for procurement of critical IT requirements | Delayed implementation affects business communication |  |  |  | UAE-ITD | Keep back up of all critical IT equipments & contingency plan to be created |  |  |  | N/A | M | 2018 |  | NAS storage and power back up has been procured and installed in the new HO location.
Limited ISP providers | Service levels affects business continuity and limitations on contingency |  |  |  | UAE-ITD | Alternate services to be analyzed within existing service providers with SLAs and maintain personal relationship |  |  |  | Only Du & Etisalat are available in the UAE. | M | 2018 |  | N/A
Business continuity | Outage of all communications and data |  |  |  | UAE-ITD | Alternate services to be analyzed within existing service providers with SLAs and maintain personal relationship |  |  |  | N/A | M | 2018 |  | Close relationship with the channel partners is being maintained to resolve any issues on priority.
H
M
L

## CSD (hidden)
Risk Assessment Department: Customer Service - UAE
RISK ASSESSMENT
Factor | Impact to SMSA | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date | Action Taken
Delay in complain resolution process and visibility | Lost customer and lost revenue |  |  |  | UAE-CSD | Map SLAs and process with centralized HO-CS |  |  |  | There is no ticketing system for RTS shipments. | M | 2019 | Currently, initiating CORE tickets to CS-Key Accounts for Key Account customers. For SME customers tickets are being initiated to resepective locations in KSA.
Lack of robust communication channel for customers | Dissatisfied customers and lose volumes |  |  |  | UAE-CSD | Map SLAs and process with centralized HO-CS |  |  |  | Customers are complaining about tickets not being actioned from respective locations. | M | 2019 | CORE accessibility has been given to key account customers and SME customers are sending email for complaints.
Inefficient & Manual reporting | Analysis and productivity |  |  |  | UAE-CSD | Automated reports from CORE |  |  |  | The risk has been reduced | L | 2019 | System-generated reports are currently being received through CORE on a monthly basis.
Geographical understanding of Country | Increased customer complaints |  |  |  | UAE-CSD | Dedicated CS heads in centralized call center with training on country information and area |  |  |  | No particular person in CS-KSA is allocated to handle SME UAE concerns and complaints. | M | 2019 | A designated KSA-CS Key account has been allocated to support UAE Key Account Customers.
No Local CSA in country to handle escalation from Sales or customers | Increased customer dissatisfaction |  |  |  | UAE-CSD | Reorganize current CS structure |  |  |  | The risk has been eliminated. | L | 2019 | Allocated local CS back support to do specific tasks.
Customer not able to access (Line Busy) | Lost business opportunity and complaints |  |  |  | UAE-CSD | Dedicated hunting line for UAE calls at HO centralized call center |  |  |  | The risk has been eliminated. | L | 2019 | All DXB Customer calls are redirected to the centralized call center in KSA.
H
M
L

## Risk Ranking
Severity
[5 empty] | Low | Medium | High
[5 empty] | Affecting location Affecting employee Affecting Satisfaction | Affecting Individual Customer Affecting SMSA Service Affecting Department | Affecting Corporate SMSA Affecting Revenue Affecting Image Affecting Govt. Regulation Affecting Key Acct customers Affecting Health & Safety
|  |  |  | (multiply) | Severity
|  |  |  | X | Low | Medium | High
Probability | Low | Probability of incidents occuring beyond 24 months | Probability | Low | Low Risk | Med Risk | Med Risk
| Medium | Probability of incidents occuring within 12 to 24 months |  | Medium | Low Risk | Med Risk | High Risk
| High | Probability of incidents occuring within 12 months or less |  | High | Med Risk | Med Risk | High Risk

## Risk ADMIN
Department Name | Administration |  |  |  | For 2023 | Location / Region |  | IBU - UAE
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
No centralized Admin in-charge | Unable to monitor and control cash flow on time |  |  |  | Previous 2021 | UAE-HRD | Follow up and re-proposal for the manpower request for centralized admin in charge. | No action taken |  |  |  | The risk remain the same |  |  | H | 2023
Long Process of approvals/budget constraints | Work efficiency, brand image ,delayed payments and loss of business opportunity. |  |  |  | Previous 2021 | UAE-HRA | Proactive planning on stocks and requirements. Analyse authority level and process in UAE. Appointed Purchase officer. | Appointed Purchase officer manage all the procurement monthly request PRF. |  |  |  | The risk has been elicited ,handed over to Purchase officer |  |  | L | 2023
Manual process, records keeping & data entry | Data loss, service level, brand image, contract renewal fines, inconsistent in data entry and lack of security |  |  |  | Previous 2021 | UAE-HRA | Proposal for implementation of Data Entry System or HRIS system. Sending data files to KSA IT personnel. | After several raised requests for SOFTWARE implementation on process. |  |  |  | The risk might increase |  |  | H | 2023
Loss of good provider vendors/suppliers | Late payments, bad debts to vendor or supplier snare disrespectful and break a trust in the company it will effect brand image. |  |  |  | Previous 2021 | UAE-HRA | Monitoring and follow-ups frequently on the due date for all the due payments. | All payments have been monitored and created one file for the records. |  |  |  | The risk has been eliminated. |  |  | M | 2023
Fines and penalties related to facilities | Work delays and high cost expending for the fines and bad records in the company. |  |  |  | Previous 2021 | UAE-HRA | Awareness and monitoring UAE rules and regulations in weekly basis. Analyzation of processes and authority level and proper AMC'S and maintenance of approved vendor | Continuous monitoring of proper AMC's and maintenance for better result by concern personnel. |  |  |  | The risk has been eliminated. |  |  | H | 2023
Loss of Data | Disrupts the day to day function of any information-based business |  |  |  | Previous 2021 | UAE-HRA | Proposal for providing management data base (SOFTWARE) | Daily back up File save on share folder. |  |  |  | The risk might increase . |  |  | H | 2023
[5 empty] | Previous 2021 |  |  | CAFO , and PAF has initiated. |  |  |  | Implementation of CAFO , increment and incentives scale
[5 empty] | Previous 2021 |  |  | Any changes and new regulation in the government are continues monitored. |  |  |  | Awareness and monitoring UAE rules and regulation in weekly basis.
[5 empty] | Previous 2021 |  |  | All payments and debts has been monitored . |  |  |  | Monitoring the due date for all the payments.
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Previous 2021
Inventory loss and damages | Revenue loss, brand image and business continuity |  |  |  |  | UAE-HRA | Deployment of Purchase officer/Procurement assessment for requirement, and propose for the manpower budget. | Recruited one Purchase office/procurement and appointed for handling related inventory. |  |  |  | Removed (Purchasing Officer has been joined)
No Annual maintenance Services for facilities | High cost on reimbursement and business continuity |  |  |  | Previous 2021 | UAE-HRD | Proposal for the quotation and approved vendors with AMC's and timeline commitment on service to be set . | Related Qoutation,vendors and contracts transferred handover to Purchase Officer and it negotiation is on process. |  |  |  | The risk has been reduced ,it was handled by Purchase Office. |  |  | M

## Risk HRD
Department Name | Human Resources |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Manual reporting and record-keeping(no SSHR System) | Inconsistency in data entry, lack of security ,time consuming and costly to produce reports. |  |  |  | Previous year 2021 | UAE-HRD | Daily back up file save on share folder. | The request /proposal has been escalated to KSA-HR and Management. Discussion on the implementation of the Software system for local HR is ongoing and started to send Data to IT department in KSA.Daily back up file save on share folder. |  |  |  | The risk has increased due to increased number of staff, the proper HRIS System to save and trace employee database. | Follow-ups in IT KSA | Quarterly | H | 2023
Inadequate salaries for rise of living cost and market inflation | Loss of a best employees of the company and recruitment cost and tediousness of employees to do there job. |  |  |  | Previous year 2021 | UAE-HRD | Proposal for Increment and Incentive Schemes, and follow-ups quarterly. | Staff restructuring has been done. CAFO has been implemented and continuous follow-ups. |  |  |  | Monthly sending reminders for the CAFO nomination. | Sending reminder email to the manager. | Monthly every end of the month. | H | 2023
Lengthy process and manual documentation for recruitment and financial approvals | Fines , and delayed of work in processing recruitment and renewals. |  |  |  | Previous year 2021 | UAE-HRD | Proactive planning and process for financial approvals should be done within 2days only to avoid delays and fines. | Follow-ups by email |  |  |  | The risk will eliminated if the approvals provided within 2 days. | Follow-ups by email | Every week | H | 2023
Petty cash unavailability for government related activities and fleet | Work-delays , and fines , lengthy process of all related matter. |  |  |  | Previous year 2021 | UAE-HRD | Providing enough petty cash in the department. | No action taken |  |  |  | The risk remain the same. | Proposal | Quarterly | H | 2023
Long process for requisition and approval | Work efficiency /penalties |  |  |  | Previous year 2021 | UAE-HRD | Proactive planning, approvals should be done within 2 days. | Follow-ups by email |  |  |  | The risk remain the same. | Proposal | Weekly | H | 2023
Loss of employees data file | Delay in processing HR requirement , ei. Visa processing and Medical Insurance Application. |  |  |  | Previous year 2021 | UAE-HRD | Providing and implementing proper management SOFTWARE. Sent data to KSA | The request /proposal has been escalated to KSA-HR and Management. Discussion on the implementation of a Software system for local HR is ongoing and started to send Data to IT department in KSA. |  |  |  | The risk remain the same. | Follow-ups in IT KSA | Quarterly | H | 2023
Loss of qualified candidates for vacancies | Never attain good quality of working and unqualified candidate can cause failure & damage of the company |  |  |  | Previous year 2021 | UAE-HRD | Proper background checking and an excellent recruitment process should be done. Offering the right package in the right position. | Candidates screened as well following the proper recruitment process. |  |  |  | The risk has been eliminated | Reviewing /Screening | Weekly | H | 2023
Unproductive and demotivated staff | Employee will do minimal best , ultimately could have a negative effect on the entire team's productivity and will affect corporate culture and company status. |  |  |  | Previous year 2021 | UAE-HRD | Implementation of CAFO and promotion and incentives scale. | Personal Action Plan ,career pathway initiated and CAFO. |  |  |  | The risk has been eliminated | Reviewing /Screening/Nomination | Monthly/ Quarterly | M | 2023
Penalties and fines due to Government regulation changes | Company image, Work-delays , and fines |  |  |  | Previous year 2021 | UAE-HRD | Awareness and monitoring in the UAE rules and regulations in a daily basis. | Any changes and new regulations in the government are continuously monitored daily. |  |  |  | The risk has been eliminated | Monitoring | Daily | M | 2023
Late payments, bad debts, and loss of vendor relation and confidence | Late payments to vendor or suppliers are disrespectful and it will leads to break a trust between the company and vendor. |  |  |  | Previous year 2021 | UAE-HRD | Monitoring the due date for all the payments | All payments and debts have been monitored and proper follow up in the Finance department. |  |  |  | The risk has been eliminated | Follow-ups in Finance | Weekly | M | 2023
Lack of Manpower for dedicated Manpower Recruitment process. | Delay for recruitment process and loss of qualified candidates. |  |  |  | Previous year 2021 | UAE-HRD | Proposal to Hire /onboard one person dedicated to Recruitment | Escalated to hire/onboard a new dedicated recruitment personnel. |  |  |  | The risk will eliminated if there is one person dedicated for recruitment. | Follow-ups | Quarterly | M | 2023
No Website/Carriers page to receive CV's and Long waiting to receive job posting templates from marketing. | Delay for recruitment process and loss of qualified candidates. |  |  |  |  | UAE-HRD | Time to time follow-ups for the templates | Posting in Meister Task |  |  |  | Removed (Dedicated Recruitment Agency providing CV's) |  |  | M

## Risk CSD
Department Name | Customer Services |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
No Real time updates on customer portal SECOM | Lost customer and lost revenue |  |  |  |  | UAE-CSD | IT Dept to work and enhance the system so that customer can see real time updates of shipments. | Weekly Con Call is done with IT Dept |  |  |  | This is still under process and we have noticed real time updates are not reflecting on all SMSA Portals | SMSA portals/channels |  | M | Under Process
Manual reports to customers | Dissatisfied customers and lose volumes |  |  |  |  | UAE-CSD | It Dept to develop system generated reports to customer or give access to customer so that they can generate require reports. | Weekly Con Call is done with IT Dept |  |  |  | Phase 1 New E-Com Dash board has been developed and access has been given to customers & CS Team but still it does not fulfil the requirements. 2nd Phase is still under process with IT Dept. | Quarterly meeting with IT Dept to understand on development. |  | M | Closed/New Ecom dashboard has been developed and shared to customers
Geographical understanding of Country | Increase customer complaints |  |  |  |  | UAE-CSD | Call Center team should be informed on regular basis with the changes in UAE Services so that they can updated the calling customers | Call Center team has been updated with all needed information with UAE Services. | [6 empty] | L | Completed | Low
Dedicated team to handle low revenue Ecom customers. | Increased customer complaints |  |  |  |  | UAE-CSD | Planned to have a dedicated team to handle low revenue customers shipment inquiries. | Key Accounts team has bee assigned to follow up all customers shipments and provide them with required information. | [6 empty] | M | Completed
Not adopted to the technology used by our competitors | Increased customer dissatisfaction |  |  |  |  | UAE-CSD | IT Dept to develop system based on current market development. | Weekly Con Call is done with IT Dept | [6 empty] | L | Completed
Corporate/Ecom customers are not educated with usage of SMSA Systems. | Lost business opportunity and increase complaints |  |  |  |  | UAE-CSD | Sales Department to educate customers with SMSA system and its usages. | Sales department has been advised to educate customers on how SMSA system will beneficial for them in tracking their shipments. | [6 empty] | L | Completed
Customer Feedback on Complain Handling | SMSA has no source to get customer feedback upon any claim resolution.
Committing customer beyond SMSA SOP delivery process | Customer should be committed beyond SOP process of each department. It has to be discussed and approved by concern dept manager as an exception
Lack of No proper root cause identified by other departments while handling the complaints | Proper root cause of complain in not been mention by departments in Core which will effect in analysing the most effected areas of complains
Lack of new service/systems launched by SMSA | SMSA management to share an new service or any new system launched to all SMSA offices.
Awareness to B2C & B2B customer with SMSA Systems. | Customer should be educated on SMSA system and process
Loosing customer due to insufficient system. | Should have one platform of system for customers where they can see all information related to their shipments.
No accurate system generated reports to evaluate staff performance for CS Management | Monthly, Weekly or daily system generated reports are not accurate
No prior information from Ops(KSA) which might effect Operations Service Levels (Ex:- Peak Season or Unplanned Projects) | This will effect on regular shipments deliveries and end up in complaints.

## Risk SSC
Department Name | SMSA Service Center (SSC) - RISK IDENTIFICATION 2022 |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification - 2022
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Non Availability of Replacement staff (untrained staff allocated) | SSC will be closed and will effect the Brand image and revenue |  |  |  | 2021-01-01 | UAE-SSC | To have a Floated within Retail Department To coach current replacement staff | Floater position is under process Staff to be coached on SSC operations | [6 empty] | M
Reconciliation of cash between SSC & FIN | Security issue |  |  |  | 2021-01-01 | UAE-SSC | Finance to Cross verify and revert back to Retail manager in case of any discrepancy | Finance is checking on weekly basis. | [6 empty] | M
Non Availability of Secured Storage Area | Security of shipments |  |  |  | 2021-01-01 | UAE-SSC | SSC are having secured area for HAL shipment with access only to SSC Staff | SSC staff is only authorized to enter HAL shipments area. | [6 empty] | H |  | Low
SMSA Service Center (SSC) to STN Connectivity | Delayed connectivity and transit time |  |  |  | 2021-01-01 | UAE-SSC | SSC shipments pickup timing has been agreed with Ops Team. | Shipment are collected as per agreed timings between SSC & Ops Team. | [6 empty] | L
Mall Timings beyond SMSA standard operating hours | Labour compliance, overtime, and fines |  |  |  | 2021-01-01 | UAE-SSC | To comply on Mall Operating Hours and regulations. | YES | [6 empty] | M
No brand Marketing/Promotions for SSC Customers | If no brand marketing is done customers will not be aware of SMSA Brand. Regular promotion has be to done in co-ordination with marketing team.
Lack of customers parking in some SSC's | Few SSC does not have dedicated parking for SMSA customers due to which customer might not visit the branch since they will have to pay RTA parking charges to park their vehicles.
Cash transfer Risk from SSC to Cashier | Currently Cash is transferred from SSC to Cashier through Non-Revenue airway bill which is High Risk.
All SSC's not on SMSA network. | All SSC are not connected on SMSA network which results in drop of Network - VPN resulting in delay of creating airway bills.
Absence of information through our system(Re-Used Airway bills | SSC Agents will not be able to identify if the customer is Re-using the same airway bill as the scans will not trigger as used.
Non availability of replacement staff | No floater available to replace SSC staff Annual Vacations and Medical Leaves which is effect the SSC Revenue

## Risk SLS
Department Name |  | Sales | [5 empty] | Location / Region |  |  |  |  | UAE
RISK ASSESSMENT
Factor | Impact to SMSA |  | Probability | Severity | Risk Ranking Prob x Sev | Responsibility | Action To Avoid Risk | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Priority Order | Plan Target Date | Action Taken
Non Competitive Air freight rates and services | Losing heavy weight shipments with good revenue, keep high risk of competitors attacking our volumes for existing customers |  |  |  |  | SFD | Freight team and management working now to develop very strong air freight service supports revenue and sales team |  |  |  | N/A | 1 | N/A | Project on going and started to secure some airfreight shipments however still some lanes under development by freight team
Weak CRM sales system | No visibility on sales activities and manual pipeline, cause of low productivity |  |  |  |  | IT | Tech team in KSA are working on a new system to be provided which is advance and will give full visibility even on existing data base |  |  |  | N/A | 1 | N/A | Tech team developing a new system
SMSA Technologies and IT solutions for customers | Integration with big brands in the market on their own plat forms takes huge time impacting new business |  |  |  |  | IT | HO to provide a solution |  |  |  | N/A | 1 | N/A | Under discussion
SMSA Technologies and IT solutions for customers | Impact SMSA customers |  |  |  |  | Marketing | For major clients manual reports is been done by CS and Tech team are working to improve the dashboard and a new one is giving to clients but still improvements on going |  |  |  | N/A | 1 | N/A | Under discussion
Inefficient Manual Reports | manual reports have no accuracy where sales team do not have a clear visibility on daily volumes as well for pipeline where no system to save opportunities |  |  |  |  | IT | Reports still been done manually to keep sales team updated till new system takes place |  |  |  | N/A | 1 | N/A | Tech team working on new system to provide all reports
Customers Ecom dashboard | creates a very high risk of revenue drop in case of losing any of the major clients for visibility |  |  |  |  | IT | For major clients manual reports is been done by CS and Tech team are working to improve the dashboard and a new one is giving to clients but still improvements on going |  |  |  | N/A | 1 | N/A | Tech team working to improve the dashboard and major clients is been updated by key account customer service
Automated reporting system for clients are not sufficient in term of updates or requirements | creates a very high risk of revenue drop in case of losing any of the major clients for visibility |  |  |  |  | IT | For major clients manual reports is been done by CS and Tech team are working to improve the dashboard and a new one is giving to clients but still improvements on going |  |  |  | N/A | 1 | N/A | Tech team working to improve the dashboard and major clients is been updated by key account customer service
Competitors providing better technologies | creates a very high risk of revenue drop in case of losing any of the major clients for visibility |  |  |  |  | IT | Support the customers with Key account help desk to respond on all queries on time |  |  |  | N/A | 1 | N/A | Tech team works on solutions
Competition price war for UAE & KSA | Impact SMSA main lane KSA |  |  |  |  | SLS | Provide clients full shipping solutions and fulfilment with GCC coverage |  |  |  | N/A | 1 | N/A | Hired BDM to take care of big projects that covers any gap as well as build new sustainable revenue, also hired team in Abu Dhabi to that considered as a blind market for SMSA where we can generate another sustainable revenue from a new vertical
E-commerce customers moving to KSA for cost cutting | Affects revenue |  |  |  |  | SLS | Building a new verticals of B2B business to support the growth of revenue and business and rectify the loss of shutdown business |  |  |  | N/A | 1 | N/A | A full team of B2B is ready to sell now in the market and support business growth aside BDM and Abu Dhabi Team
COVID impact forces start-ups to shut down business | Causing volumes fluctuation up and down and threat the growth of business |  |  |  |  | SLS | Building a new verticals of B2B business to support the growth of revenue and business and rectify the loss of shutdown business for start-ups due to covid impact |  |  |  | N/A | 1 | N/A | A full team of B2B is ready to sell now in the market and support business growth aside BDM and Abu Dhabi Team
Small pillars of local deliveries burning rates in the market | creates lots of challenge to secure and build domestic volumes and to onboard new clients due to rate competition |  |  |  |  | SLS | Focusing on new sectors and projects such as cold chain and banking which will take time due to its criteria of tendering |  |  |  | N/A | 1 | N/A | A new BDM is hired and prospecting the market for health care banking and government sectors
Non Competitive Express Service & Rates by TP | Express courier companies provide a heavy weight service for Express shipments, which sort market share only between small parcel with low revenue |  |  |  |  | SLS | Working only on heavy weight shipments by road to generate revenue |  |  |  | N/A | 1 | N/A | Working to promote the SMSA air freight service, as well creating new rate tariff's for sales force to be able to compete in the market
Competitors attacking our manpower | Competitors approaching our manpower due to knowledge and large customer data base which affecting stability of the team and put customers at risk |  |  |  |  | SLS | New commission scheme took place and promotions for the team |  |  |  | N/A | 1 | N/A | Risk has been reduced by promoting the successful and the achiever sales person, and commission is been given quarterly basis as well, drawing a career path to all the team, promoted a new titles to motivate the team for promotions
Customs Regulation Changes (Saudi & UAE) | Impact SMSA relation with the existing accounts as well drop in volumes |  |  |  |  | CS/Customs | Announce all new news on the spot once released from customs authorities and update our current customers to follow the requirements and changes |  |  |  | N/A | 1 | N/A | CS will get the news from any destination once announced and will update the clients, also exception for only 48H will be taken from customs not to implement the new changes on the spot
Air and Sea Freight Rates and connection | Limitation of sales team providing solutions for the customer in term of B2B business |  |  |  |  | SFD | Focusing on Express and normal courier mode |  |  |  | N/A | 1 | N/A | SFD working to develop the products
H
M
L

## Risk OPS
Department Name | Operations |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
None screening of export shipments at DXBHUB | Undeclared DG causing non-compliance with GCAA and airline could result for fines and suspension of license. |  |  |  |  | UAE-OPS | Screening done under Dnata by DAFZA airport security. | HUB agents does random checks on suspicious and new account shipments
Manual reporting reduces efficiency | Inaccuracy in reports in service levels and management analysis |  |  |  |  | UAE-OPS | CORE report enhancement | CORE system needs to identify the failed data and share the report with actual figures.
Manual sorting of packages is time consuming | Might effect connections with Gateways and Linehauls. |  |  |  |  | UAE-OPS | Studied the volume capacities and LH timings to set needed trained staff to complete the task within the time. | Redistributed job responsibilities - Tasks internally to maximize sorting efficiencies. | [8 empty] | Low
Improper fleet control and management setup | Effect fleet replacements when required, breakdown - Accidents, Delay in maintenance schedules. |  |  |  |  | UAE-OPS | Evaluate vendors and propose to remove/hold renewal of contract or issuing new PO. Assign once of the Dispatchers to close monitor OPS fleet and coordinate with ADMIN/Procurement with reports. | Dispatcher(differed) coordinates with Vendors, ADMIN and Procurement from OPS until a dedicated Fleet coordinator is assigned.
No clear carrier development path for experienced OPS staff | Losing trained and experience employees to competitors and effects productivity. |  |  |  |  | UAE-OPS | Employee Development Plan(EDP) initiated to qualify for next levels. | Provided EDP for eligible staff to prepare for higher positions.
NEW
NEW

## Risk SFD
Department Name | SFD |  |  |  |  | Location / Region |  | Dubai, UAE
L
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Manual Data Entry / Reporting / Storage | Avoiding Human or Typing Error |  |  |  | 2022 | IT | Appropriate software platforms to be allocated as per Departmental requirements. | Appropriate Vendors approved |  |  |  | IT working on it | NA | NA | NA | 2022
SMSA Website is not giving real time status update | Lack of visibility on shipments for clients |  |  |  | 2022 | IT | This issue has being highlighted to the KSA IT team for resolution | On temporary basis updates are send to client via emails |  |  |  | Risk is not eliminated yet since the job is done manually | NA | NA | NA | 2022
KIFA Phase 2 + Eastern Gateway allowing clearance facility | Effecting market share in the later stages |  |  |  | 2022 | KSA KIFA Clearance Team | Further streaming the clearance process, for effective Transit Time commitments | Sales to focus and sell showcasing the advantage of SMSA KIFA faculty's |  |  |  | To increase efficiency and clearance time at KIFA and showcase that KIFA service is far better than any other gateways | NA | NA | NA | NA
Lack of own operations in other GCC sectors like OMAN, KUWAIT & QATAR | Affecting market penetration |  |  |  | 2022 | SFD-HQ | Currently working with agents | SMSA HQ to take decision to open own operation |  |  |  | HQ to take a decision | NA | NA | NA | NA
Turbulent economic conditions | Affecting day to day volumes |  |  |  | 2022 | SFD-HQ | Working against volume commitments | To target clients with regular steady volumes |  |  |  | Prospect the right clients with regular volumes | NA | NA | NA | NA
Varying market demands | Affecting day to day volumes |  |  |  | 2022 | SFD | Working against volume commitments | To target clients with regular steady volumes |  |  |  | Prospect the right clients with regular volumes | NA | NA | NA | NA
Forwarders going for Express license and using Eastern Gateway to clear the cargo | Affecting day to day volumes |  |  |  | 2022 | SFD | Prospect with direct clients | Sales to focus on direct clients and conduct regular visits to existing and new clients |  |  |  | Prospect the right clients with regular volumes | NA | NA | NA | NA
Global companies merging and creating their own Road product | Affecting day to day volumes |  |  |  | 2022 | SFD | Prospect with direct clients | Sales to focus on direct clients |  |  |  | Prospect the right clients with regular volumes | NA | NA | NA | NA
Non Competitive Air freight rates & services | Losing heavy weight shipments with good revenue, keep high risk of competitors attacking our volumes for existing customers |  |  |  | 2022 | SFD | Working on to identify the right agents | Introduction sent to WCA agents |  |  |  | N/A | NA | NA | NA | NA
Weak Brand Marketing | Impact SMSA market share as we are not doing any ads to allow customers to reach us and know our services |  |  |  | 2022 | Marketing | For major clients manual reports is been done by CS and Tech team are working to improve the dashboard and a new one is giving to clients but still improvements on going | Under discussion |  |  |  | N/A | NA | NA | NA | NA
Inefficient & Manual Reporting | manual reports have no accuracy where sales team do not have a clear visibility on daily volumes as well for pipeline where no system to save opportunities |  |  |  | 2022 | IT | Reports still been done manually to keep sales team updated till new system takes place | Tech team working on new system to provide all reports |  |  |  | N/A | NA | NA | NA | NA
Non Availability of the signed POD / Electronic POD on SMSA website | Impacts big clients with high volumes |  |  |  | 2022 | SMSA-HQ | Manual POD are shared currently to meet customers requirements | Under discussion |  |  |  | N/A | NA | NA | NA | NA
Customs Regulation Changes (Saudi & UAE) | Impact SMSA relation with the existing accounts as well drop in volumes |  |  |  | 2022 | CS/Customs | Announce all new news on the spot once released from customs authorities and update our current customers to follow the requirements and changes | CS will get the news from any destination once announced and will update the clients, also exception for only 48H will be taken from customs not to implant the new changes on the spot |  |  |  | N/A | NA | NA | NA | NA
Competitors providing better technologies | creates a very high risk of revenue drop in case of losing any of the major clients for visibility |  |  |  | 2022 | IT | Support the customers with Key account help desk to respond on all queries on time | Tech team works on solutions |  |  |  | N/A | NA | NA | NA | NA

## Risk ITD
Department Name | Information Technology |  |  |  |  | Location / Region |  | IBU - UAE
Risk Identification
| Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Time consumption with internet service providers | Downtime |  |  |  | 25/12/2020 | UAE-ITD | Manage contacts with service providers and analyse wireless connectivity options. | Close relationship with the channel partners maintained to resolve any issues on priority. |  |  |  | N/A |  |  | M | 2021
Obstacles with IT requirements procurement | Affects business |  |  |  | 30/12/2020 | UAE-ITD | Back up of all IT equipment's. | NAS storage and power back up has been procured and installed in the new HO location. |  |  |  | N/A |  |  | M | 2021 | Low
Limited options of internet service providers | Service is compromised |  |  |  | 30/12/2020 | UAE-ITD | Alternate services as probabilities within the existing service providers. | N/A |  |  |  | Only Du and Etisalat are available in the UAE. |  |  | M | 2021
Security threat to data | Retrieval of data - added task |  |  |  | 30/12/2020 | UAE-ITD | Strong security network for data | Upgraded software for data protection |  |  |  | N/A |  |  | H | 2021

## Risk CORP
Department Name | Corporate |  |  |  |  | Location / Region |  | Dubai, UAE
L
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Interfaces Systems needs to reflect the nature of services we are selling in UAE and display appropriate details required by them | Technology is crucial in our business . Good system will increase SMSA customer's satisfaction & grant them the visibility needed to follow the delivery performance. The lack of such systems will result lost in revenue and customers retention . |  |  |  |  | IBU Management and IT | it’s the most essential tool for our continuous growth , SMSA has to rank high the importance of revamp all the systems that manage the relations with the customers . |  |  |  |  | Risk is still high and existing |  |  |  | 2022
Automated reporting system that enables customer's visibility on real time updates and status | Loss business opportunity and increase customer dissatisfaction and complaints |  |  |  |  | IBU Management and IT | start working on an agile system that replace all manual reporting system to increase efficiencies and customer satisfaction |  |  |  |  | Risk is still high and existing |  |  |  | 2022
Poor system supports for remote working and accessibility | Equipping SMSA with the right technology is essential especially during severe situations where we will be oblige to work remotely . Unavailability of such tools in place will lead to business interruption. |  |  |  |  | IBU Management and IT | Having the right risk assessment and equip SMSA with the needed tools to overcome such unusual work situations . |  |  |  |  | Risk is high and increased |  |  |  | 2022 | Low
New HR system to replace manual processing | An advance HR system that replace the manual processes . Increase the efficiencies for the right evaluation and management of SMSA employees and their career path. |  |  |  |  | IBU Management and IT | implement immediately a new system to manage all the aspects of people management . |  |  |  |  | Risk is high and increasing due to the increased number of people |  |  |  | 2022
Weak CRM system that reduces the efficiencies in Sales activities and reporting | Monitoring SMSA sales activities through an advance system is essential for the proper evaluation of business , revenue assumptions and achieved plans . |  |  |  |  | IBU Management and IT | replacing the available systems |  |  |  |  | Risk is high and no solution so far
Billing system based on manual feeding of data that leads to revenue leakage. | Loss of Revenue and impacts the profitability of the company |  |  |  |  | IBU Management and IT | Work to have a new billing system that replace the manual work ,Improve our collection to maintain a healthy cash flow and decrease the customer complains . |  |  |  |  | Billing is purely a manual process and no system so far |  |  |  | 2022
Billing system doesn't have the capability for multiple product's types under one account leading to incompetency | Delay invoicing, revenue leakage , prone to errors , does not meet customer requirement. |  |  |  |  | IBU Management and IT | Work to have a new billing system that replace the manual work ,Improve our collection to maintain a healthy cash flow and decrease the customer complains . |  |  |  |  | No changes |  |  |  | 2022
Billing system doesn't have the capability for multiple product's types under one account leading to incompetency.
AR systems has no ability to control the credit terms that reduces the risk of bad debts . | Lack of liquidity which in turn leads to loss in immunity and non-fulfilment of company obligations towards its vendors and eco-system in general . |  |  | L |  | IBU Management and IT | A well established accounting system for the good management of SMSA customer's credit terms and limits . |  |  |  |  | No changes |  |  |  | 2022
Customizing the view over SMSA website to reflect our products and service's specifications that are related to UAE. | Lack of knowledge and brand awareness about SMSA in the local market from customers and affecting the selling point as well |  |  | L |  | IT and Marketing Team | A holistic Marketing Team vision that covers the needs of SMSA in other that KSA market . |  |  |  |  | At the beginning of 2022 we introduced UAE domain on SMSA website and waiting to customize more tools that reflect the nature of services that SMSA provides in UAE market . |  |  |  | 2022
Turbulent economic and political conditions | Direct impact on our revenue figures as well as the increase in cost due to war and the sanction that are imposed on some of the countries that resulted a total or partial business shut down. |  |  | L |  | UAE management | High cost control. Maintaining healthy cash flow and monitoring the revenue achieved with the yearly budget to secure the growth needed. |  |  |  |  | Risk is still on going |  |  |  | 2022
High Competition and market penetration | Market penetration became an easy process due to new facilities and investment tools provided by the local authorities which increase the competition in prices and services |  |  | L |  | UAE management | Proper business analyses tools. Empowered and driven sales team. Competitive customer value proposition |  |  |  |  | Risk is still on going |  |  |  | 2022
Data security and privacy issues | Full exposure of our price strategy , employees income and benefits in additional to the some legal constraints due to the non-disclosure agreements that are signed with SMSA clients |  |  | L |  | IBU Management and IT | Protecting our data with level of authorities that reduces the risk of data leakages and secure our business |  |  |  |  | Brand become more exposed in the local market. Securing our DATA through an advance system in place is essential. SMSA is an easy hunt for competitors . |  |  |  | 2022
New distractive technology that reshape the whole industry | the lost of our competitive advantages and be out of business . |  |  | L |  | IBU Management and IT | An agile IT department that works continuously to improvement our service in respond with our customers needs and requirements and customizing the needed solutions to them . |  |  |  |  | The development of SMSA systems, ability of customization and the response by our IT team into various market challenges are very slow. |  |  |  | 2022
Airline situation and cost elevation | Cost increase and lost in gross profit |  |  | L |  | UAE Management | Keep looking for best airline option in terms of cost and connectivity to maintain a good proportion of volume vs cost. |  |  |  |  | this risk is mitigated |  |  |  | 2021
Government regulatory bodies and the continuance changes in charges and implementation | Business interruption , imposed penalty , non-compliance and bad business relations |  |  | L |  | UAE Management | Maintaining a good relation with the entire SMSA Eco-system and improve the partnership with the Gov through projects that mutually benefit both entities ., |  |  |  |  | the risk is reduced sue to the continuous development of our infrastructure and the plans of automation with the authorities which will continue in 2022. |  |  |  | 2022