## Risk Identification
Department Name | Corporate |  |  |  |  | Location / Region |  | Dubai, UAE
L
Risk Identification
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) | Risk Identification Date | Responsibility | Action to Mitigate the Risk | Actions taken /Plans | Residual Probability | Residual Severity | Residual Risk Ranking | Remarks | Review Mechanism | Review Frequency | Priority order | Plan target date if applicable
Interfaces Systems needs to reflect the nature of services we are selling in UAE and display appropriate details required by them | Technology is crucial in our business . Good system will increase SMSA customer's satisfaction & grant them the visibility needed to follow the delivery performance. The lack of such systems will result lost in revenue and customers retention . |  |  |  |  | IBU Management and IT | it’s the most essential tool for our continuous growth , SMSA has to rank high the importance of revamp all the systems that manage the relations with the customers .
Automated reporting system that enables customer's visibility on real time updates and status | Loss business opportunity and increase customer dissatisfaction and complaints |  |  |  |  | IBU Management and IT | start working on an agile system that replace all manual reporting system to increase efficiencies and customer satisfaction
Poor system supports for remote working and accessibility | Equipping SMSA with the right technology is essential especially during severe situations where we will be oblige to work remotely . Unavailability of such tools in place will lead to business interruption. |  |  |  |  | IBU Management and IT | Having the right risk assessment and equip SMSA with the needed tools to overcome such unusual work situations . | [9 empty] | Low
New HR system to replace manual processing | An advance HR system that replace the manual processes . Increase the efficiencies for the right evaluation and management of SMSA employees and their career path. |  |  |  |  | IBU Management and IT | implement immediately a new system to manage all the aspects of people management .
Weak CRM system that reduces the efficiencies in Sales activities and reporting | Monitoring SMSA sales activities through an advance system is essential for the proper evaluation of business , revenue assumptions and achieved plans . |  |  |  |  | IBU Management and IT | replacing the available systems
Billing system based on manual feeding of data that leads to revenue leakage. | Loss of Revenue and impacts the profitability of the company |  |  |  |  | IBU Management and IT | Work to have a new billing system that replace the manual work ,Improve our collection to maintain a healthy cash flow and decrease the customer complains .
Billing system doesn't have the capability for multiple product's types under one account leading to incompetency | Delay invoicing, revenue leakage , prone to errors , does not meet customer requirement. |  |  |  |  | IBU Management and IT | Work to have a new billing system that replace the manual work ,Improve our collection to maintain a healthy cash flow and decrease the customer complains .
Billing system doesn't have the capability for multiple product's types under one account leading to incompetency.
AR systems has no ability to control the credit terms that reduces the risk of bad debts . | Lack of liquidity which in turn leads to loss in immunity and non-fulfilment of company obligations towards its vendors and eco-system in general . |  |  | L |  | IBU Management and IT | A well established accounting system for the good management of SMSA customer's credit terms and limits .
Customizing the view over SMSA website to reflect our products and service's specifications that are related to UAE. | Lack of knowledge and brand awareness about SMSA in the local market from customers and affecting the selling point as well |  |  | L |  | IT and Marketing Team | A holistic Marketing Team vision that covers the needs of SMSA in other that KSA market .
Turbulent economic and political conditions | Direct impact on our revenue figures as well as the increase in cost due to war and the sanction that are imposed on some of the countries that resulted a total or partial business shut down. |  |  | L |  | UAE management | High cost control. Maintaining healthy cash flow and monitoring the revenue achieved with the yearly budget to secure the growth needed.
High Competition and market penetration | Market penetration became an easy process due to new facilities and investment tools provided by the local authorities which increase the competition in prices and services |  |  | L |  | UAE management | Proper business analyses tools. Empowered and driven sales team. Competitive customer value proposition
Data security and privacy issues | Full exposure of our price strategy , employees income and benefits in additional to the some legal constraints due to the non-disclosure agreements that are signed with SMSA clients |  |  | L |  | IBU Management and IT | Protecting our data with level of authorities that reduces the risk of data leakages and secure our business
New distractive technology that reshape the whole industry | the lost of our competitive advantages and be out of business . |  |  | L |  | IBU Management and IT | An agile IT department that works continuously to improvement our service in respond with our customers needs and requirements and customizing the needed solutions to them .
Airline situation and cost elevation | Cost increase and lost in gross profit |  |  | L |  | UAE Management | Keep looking for best airline option in terms of cost and connectivity to maintain a good proporttion of volume vs cost.
Government regulatory bodies and the continuance changes in charges and implementation | Business interruption , imposed penalty , non-compliance and bad business relations |  |  | L |  | UAE Management | Maintaining a good relation with the entire SMSA Eco-system and improve the partnership with the Gov through projects that mutually benefit both entities .,
NEW
NEW
NEW

## Risk Ranking
Severity
[5 empty] | Low | Medium | High
[5 empty] | Affecting location Affecting employee Affecting Satisfaction | Affecting Individual Customer Affecting SMSA Service Affecting Department | Affecting Corporate SMSA Affecting Revenue Affecting Image Affecting Govt. Regulation Affecting Key Acct customers Affecting Health & Safety
|  |  |  | (multiply) | Severity
|  |  |  | X | Low | Medium | High
Probability | Low | Probability of incidents occuring beyond 24 months | Probability | Low | Low Risk | Med Risk | Med Risk
| Medium | Probability of incidents occuring within 12 to 24 months |  | Medium | Low Risk | Med Risk | High Risk
| High | Probability of incidents occuring within 12 months or less |  | High | Med Risk | Med Risk | High Risk