## Critera
Quality Inspections Planning Criteria
SNB Project
The location coordinates provided by SNB were given ideal route numbers for example RA, RB - wherein RA is Riyadh ATM and RB is Riyadh Branch.
Each of the coordinate was entered onto google maps. Locations were distributed based on the different routes identified. This was done in order to have an optimized route plan to ensure efficient use of duty hours and days.
The route plan was made using google maps and online route planner wherein the closest districts were considered based on set travel time and total service time.
The planning of locations as per bank requirements which were re adjusted considering the distance for travel and service time for each day
Spare time is provided to include ( Travel from house to location and back, parking, road closures, reroutes, follow-ups -if any
Total trip within the city excludes travel from home/base to location
Spare time threshold is set at min 30 min and maximum 2 hours excluding remote locations and month of Ramadan. Wherein if spare time is less than 30 minutes is identified some locations are reduced for the day, similarly if spare time of more than two hours was identified a location was added for the day. This adjusted based on customer requirements.
Saturday will be given as day off during Ramadan to compensate for the extra working hours
Business Travel for remote locations was identified based on SMSA Business travel policy i.e. 300 km (from base to boundary)
The plan was created keeping in view 1 staff for complete inspections of 1 region.
During business travel to remote areas - the main remote area was set as base to travel to closest remote locations.
ATM needs to be audited 4 times per year (2 quarters at night & 2 quarters during day).
Branches needs to be audited twice a year ( night time only)
Night duty timing will be from 8 pm to 5 am.
Day duty timing will be from 8 am to 5 pm.