## SWOT
Specialized Services Project
SWOT Analysis
Criteria Examples Advantages ? Capabilities ? Competitive advantages ? USP's (unique selling points) Resources, Assets, People? Experience , knowledge, data ? Financial reserves, likely returns ? Marketing - reach, distribution, awareness? Innovative aspects ? Location and geographical ? Price, value, quality ? Accreditations, qualifications, certifications ? communications ? Cultural behavioural ? | Strenghts |  | Weaknesses | Criteria examples Disadvantages ? Gaps in capabilities ? Lack of competitive strength ? Reputation, presence and reach ? Financials ? Timescales, deadlines and pressures ? Cash flow, start-up cash drain ? Continuity, supply chain ? Effects on core activities, distraction ? Reliability of data, plan predictability ?
| System |  | First project of this type
| Route Planning/ Ntework Coverage |  | Back-up data
| Saudi Employees |  | Unplanned/ adhoc visits
| QRM experience (in terms of audit) |  | Unavailability of backup admin users for E-inspection system
Training
Policies & procedures (GUIDE)
Availability of customized inspections application
Availability of mobile application support
ISO 9001:2015 certification (Professional Services)
Validated coordinates/ route plans
Criteria Examples Market developments ? Competitors' vulnerabilities ? Industry of lifestyle trends ? Technology development and innovation ? Global influences ? New markets, vertical, horizontal ? Niche target markets ? Geographical, export, import ? Tactics : eg,surprise, major contracts ? Business and product development ? Partnerships, agencies, distribution ? | Opportunities |  | Threats | Criteria Examples Political effects ? Legislative effects ? Enviornmental effects ? IT developments ? Competitor intentions- various ? Market demand ? New technologies, services, ideas ? Vital contra cts and partners ? Sustaining internal capabilities ? Obstacles faced ? Insurmountable weaknesses ? Loss of key staff ? Sustainable financial backing ? Economy - home abroad ?
| New project with other business in KSA/ oter countries |  | Competition
| Opportunity for employees to progress to interna audit |  | Losing key staff
| Good customer satisfaction result |  | Weather conditions
| Incentive scheme |  | Bad roads
| System enhancement |  | Weak inspection by Inspectors
| New similar projects with other industries |  | Economic/ political situations

## Risk SSP
| Specialized Services Project |  |  |  |  | Location / Region |  | HQ |  |  |  |  | Risk Identification Owner / Department: QRM
|  | Risk Previous Year |  |  | Risk Identification Date | Responsibility | Action to Mitigate the Risk | New Residual Risk |  |  | Remarks | Review Mechanism | Review Frequency | Priority Order | Plan target date if applicable
Factor | Impact to SMSA | Probability | Severity | Risk Ranking (probability X Severity) |  |  |  | Residual Probability | Residual Severity | Residual Risk Ranking
Not meeting SLA | Penalty Deduction from invoice Losing the contract |  |  |  | Feb 2021 | QRM | Regular monitoring and measurement of service level |  |  |  | Database has been created to monitor SLA compliance. Database monitered and maintained by QRM anallysts | Reports System | Weekly Monthly Quarterly | High
Accidents/ breakdowns | Delays in inspections Affects SLA |  |  |  | Feb 2021 | QRM | Pre-trip vehicle inspection checks Regular vehicle maintenance Defensive driving training Ensure updated list of emergency contacts available |  |  |  | Project staff have been nominated on the defensive driving training module via E-learning. Staff training completed and certificates maintained. Company vehicle maintainance done by the leasing company. Contacts shared to all inspectors and project POC defined for project. POC memo approved and communicated. | Training records Incident records/log | Quarterly | Med
Employee Long-term absence | Shortage in manpower SLA not being met |  |  |  | Feb 2021 | QRM | Enforce DVD. Maintain back-up floaters in each region |  |  |  | Security staff in the regions are used as back-up whenever assigned inspector leaves the project. | Staffing level SLA acheivement | Quarterly | Low |  | Low
Extreme weather conditions | Delays in inspections Accidents |  |  |  | Feb 2021 | QRM | Defensive driving training Enforce incident/accident procedure |  |  |  | Project staff have been nominated on the defensive driving training module via E-learning. Staff training completed and certificates maintained. | Training records Incident records/log | Quarterly | Low
Lack of employees | Shortage in manpower SLA not being met |  |  |  | Feb 2021 | HRD | Maintain staffing level Ensure key positions are filled Consider training and maintaining backup floaters |  |  |  | Security Manager and analyst are identified as POC for the project. Back-up of the project is documented. Training for the new staff needs to be tracked and monitered. | Training records Staffing level SLA acheivement | Monthly | Low
System failure | Delays in inspections SLA not being met |  |  |  | Feb 2021 | QRM | Ensure back up plan/availability of manual WI to address system contingencies maintain and perform system maintenance programs/contract. |  |  |  | Contingency work instructions are documented in the specialized services manual. The same has been incorporated in the training module for the project. System is maintained inhouse by IT team. | Complaints Log Internal audits | Quarterly | High
Not accurate inspection | SLA not being met Losing the contract |  |  |  | Feb 2021 | QRM | Ensure regular staff training Evaluate competence Maintain error accurancy measurements. Enforce DVD. |  |  |  | Inspections are regularly monitered by the project manager. Issues identified (if any) are communicated by the project manager to the site inspectors. | Training records complaints log | Monthly | Med
Parking issue (day time) | Delays in inspections |  |  |  | Feb 2021 | SLS/ FIN | Ensure parking space availibility at customer premesis Review fixed variable cost for penalties arising due to wrong parking in the project. |  |  |  | No penalties were reported till date relating to wrong parking. | penalties log communication email/memo | Quarterly | Med
Speeding | Fines & penalties -Traffic violation Accidents |  |  |  | Feb 2021 | TRNG/QRM | Defensive driving training Maintain and monitor staff violations Enforce DVD |  |  |  | Project staff have been nominated on the defensive driving training module via E-learning. Staff training completed and certificates maintained. List of traffic violations maintained by fleet department and reviwed by project manager. | Training records Incvestigation records | Monthly | Med
Replacement vehicles in remote locations | Delays in inspections Affects SLA |  |  |  | Feb 2021 | FLEET | Review terms and conditions with current lease companies Communicate conditions and timeline for replacement to all staff. |  |  |  | Vehicle replacements are done after approval of fleet department in liasion with the leasing company. | Lease contracts Vehicle documentation checks(Fleet) | Monthly | High
Staff turnover | Shortage in manpower Transfer of knowledge |  |  |  | Feb 2021 | TRNG/ HRD | Review and revise positionwise staff benefits Implement dept succession planning Maintain career path plan |  |  |  | QRM succession planning document maintained in QRM DB. | Career path training needs analysis | Quarterly | Low
Bank delay in informing new locations | Delays in inspections |  |  |  | Feb 2021 | QRM | Maintain open communication lines with customer Monitor and maintain complete and correct information periodically Ensure inspections planning terms being agreed with the customer/SLA |  |  |  | Bank has open communication lines with project POC -Security Manager and System admin. Meetings are held between QRM and the bank. MOM maintained on file. | Montly/weely/quarterly and daily reports SLA change log | Monthly | Low
Losing contract to competition | Lost business/ revenue |  |  |  | Feb 2021 | SLS | Review of service support and pricing to ensure competitiveness Enhance IT solutions Regular market surveys |  |  |  | IT solution enhanced - Deployed new system as per bank requirements. | Surveys | Quarterly | High
Delay in BT payments | Delays in inspections |  |  |  | Feb 2021 | FIN | Management/Finance team's commitment to prioritize BTA requests when received |  |  |  | BTA's processed as per policy. Urgent requests are acceptd by Finance after directors approval. | BT approvals ERP requests | Monthly | Med
Political situation (Southern region - Najran) | Delays in inspections SLA not being met |  |  |  | Feb 2021 | QRM | On going monitoring of the current situation and working around this to meet SLA Maintaining open communication lines with the customer/banks Agree and enforce force majeure clause in SLA. |  |  |  | Situation stable. Ongoing monitoring of internal external factors affecting SMSA. This is regularly reviewed as part of MMR. | Internal audit | Quarterly | High
Fuel Card misuse | Increase in fuel usage/ cost |  |  |  | Feb 2021 | QRM | Implement and Maintain fuel usage log Allocate fuel usage limits per route. |  |  |  | Fuel usage is alloted to all staff using the PETRO APP . Each site inspector is alloted 150 Litres within city. For BT's fuel expense claims apply. Fuel usage log is maintained and monitered by project manager | Fuel log | Monthly | Low
Lost/ stolen mobile | Security issues |  |  |  | Feb 2021 | QRM | Ensure personnel security Enforce incident reporting and management procedures Ensure back up plan/availability of manual WI to address contingencies |  |  |  | Contingency is documented in the specialized services manual. The same is part of SSP training module deployed to the project staff. | Incident report training records | Quarterly | Med
Bad roads / Geographical issues | Accidents / death Affects SLA |  |  |  | 2021-07-01 | Fleet | Provide special vehicles Identify dangerous areas / regions / zones Replace vehicle running on such routes |  |  |  | No dangerous areas identified as of yet. Normal vehicle allocation policy applied by fleet as per staff grade. | Route plan | Quarterly | Low
Unavailability of customized inspections application | Security issues Usage limited to available system options Unorganized technical support |  |  |  | 2021-07-01 | QRM | Develop formalized project plans with IT. Clearly clarify scope with customer and IT prior to project commencing. |  |  |  | E-inspection system blue print ceated by QRM as per bank requirements and shared with ITD. New application developed by ITD and deployed. System enhancements gaps maintained and tracked in liasion with IT team by project manager | MOM QRM-IT Communication email/memo | Quarterly | Med
Duplication of system data/ Data overwrite when 2 inspections are uploaded simultaniously | Loss of inspection data Affects SLA Delays in inspections |  |  |  | 2021-07-01 | QRM | More controls must be in place Contracts must be done and reviewed Implement third party review mechanism |  |  |  | Duplication is no longer an issue in the newly deployed E-inspection application. Route plan is created and validated by Quality auditors and sent to system administrator for upload. Sites are upadated on weekly basis on the system for inspections. | Inspection records Inspection plan | Quarterly | Med
Unavailability of backup admin users for E-inspection system | Loss of inspection data Affects SLA Delays in inspections |  |  |  | 2022-10-22 | QRM | Backup administartaor for the system must be defined and documented Authorized backup staff must be given admin portal training and access to the system |  |  |  | Admin portal training module developed by system administartor. Admin Training given to additional nominated staff in QRM. Key backup list maintained | Training records | Monthly | Med

## Risk Ranking
Severity
[5 empty] | Low | Medium | High
[5 empty] | Affecting location Affecting employee Affecting Satisfaction | Affecting Individual Customer Affecting SMSA Service Affecting Department | Affecting Corporate SMSA Affecting Revenue Affecting Image Affecting Govt. Regulation Affecting Key Acct customers Affecting Health & Safety
|  |  |  | (multiply) | Severity
|  |  |  | X | Low | Medium | High
Probability | Low | Probability of incidents occuring beyond 24 months | Probability | Low | Low Risk | Med Risk | Med Risk
| Medium | Probability of incidents occuring within 12 to 24 months |  | Medium | Low Risk | Med Risk | High Risk
| High | Probability of incidents occuring within 12 months or less |  | High | Med Risk | Med Risk | High Risk