## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | Management Meeting
Date: |  | 2024-04-29 |  |  | Start Time: |  | 11:10 |  | End Time: |  | 12:55 | Location: |  | Conference Room Kuwait
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | System and System Access |  |  |  | Shaji George |  |  | 11:10
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | JD & KPI Review |  |  |  | Shaji George
Talal Albadawe |  |  |  |  | HRD |  |  | 3 | Logistas System |  |  |  | Shaji George
Shaji Joby |  |  |  |  | SLS |  |  | 4 | CASS -IATA Registration |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 5 | Annual Leave |  |  |  | Shaji George
Zubair Bin Ali |  |  |  |  | SFD |  |  | 6 | Department Update - GTW |  |  |  | Shaji George
Mohammed Bucheeri |  |  |  |  | ADM |  |  | 7 | Streamline process for Self Clearance |  |  |  | Shaji George
Khalil Musa |  |  |  |  | GTW |  |  | 8 | Department Update - Operations |  |  |  | Shaji George
[8 empty] | 9 | Department Update - SFD |  |  |  | Shaji George
[8 empty] | 10 | Department Update - HRD |  |  |  | Shaji George
[8 empty] | 11 | Department Update - Sales |  |  |  | Shaji George
[8 empty] | 12 | 3rd Party Clearance - Service Agreement |  |  |  | Shaji George
[8 empty] | 13 | Streamline process of Inbound LTL Shipments |  |  |  | Shaji George
[8 empty] | 14 | Delay in agents payments |  |  |  | Shaji George
[8 empty] | 15 | Delay in deliver of express shipments |  |  |  | Shaji George
[8 empty] | 16 | Department update - Finance |  |  |  | Shaji George
[8 empty] | 17 | IT Issues |  |  |  | Shaji George
[8 empty] | 18 | CS Issue |  |  |  | Shaji George
[8 empty] | 19 | Municipality License for Warehouse |  |  |  | Shaji George
[8 empty] | 20 | MOC User |  |  |  | Shaji George
[8 empty] | 21 | Uniform and ID |  |  |  | Shaji George
[8 empty] | 22 | DVD |  |  |  | Shaji George |  |  | 12:55
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | System and System Access |  |  |  |  | CM |  |  | SG | 26-07-2023 - SLS -POS System - Following up with HQ 27-08-2023 - Following up with HQ 28-11-2023 - Shaji Joby to follow with Kuwait IT for System and System Access 08-01-2024 - Mr. Fahad is following 06-03-2024 - Waiting for the update. 29-04-2024 - Requested PC for the retail, once received POS system will be installed. |  |  |  | On-going
2 | JD & KPI Review |  |  |  |  | SB |  |  | SG | 06-03-2024 - Shaji Joby to submit the JD, Org Chart and KPI for CSD and SLS Dept for CGM review. Sanjay to have meeting with CGM to review and finalize the JD and KPI. Mohammad Bucheeri to review his department JD and KPI with CGM. Mahammad Azharuddin to add his dept Individual KPI in monthly report and share the same. Khalil Musa to update the calculation of Individual KPI in monthly report and submit the same. Each HOD should make sure they have Performance Measure Report to do the evaluation in KPI 29-04-2024 - Sanjay to submit the department JD and KPI on priority basis |  |  |  | On-going |  | 2024-05-09
3 | Logistas System |  |  |  |  | SB/ZB |  |  | SG | 27-08-2023 - Implementation of Logistas System for SFD 28-11-2023 - System will be live by 04/01/2024 and training is scheduled. 08-01-2024 - Training in progress 06-03-2024 - Oracle and Logistas to be in effective from 01/04/2024. 29-04-2024 - Testing completed, some amendments are requested. Logistas to be in effect from 01/05/2024 |  |  |  | On-going
4 | CASS -IATA Registration |  |  |  |  | SB |  |  | SG | 27-08-2023 - Registration of OCS/SMSA in CASS 28-11-2023 - Sanjay to check and submit complete details. 08-01-2024 - On hold by CGM |  |  |  | On-hold
5 | Annual Leave |  |  |  |  | All dept. |  |  | SG | 06-03-2024 - Talal to send the report to each HOD for pending number of leave days of employee. 29-04-2024 - Employee who have leave more than 30 days should be send for vacation. |  |  |  | Completed
6 | Department Update - GTW |  |  |  |  | KM |  |  | SG | 06-03-2024 - Bonded Loads and clearance need to have discussion, Scanning at CONS level - Bonded. JD for Administrator need to be created and reviewed with CGM. 29-04-2024 1- Bonded loads clear under one Bayan regardless the number of manifests, waiting for approval to scan the physical shipment in bonded area. 2- JD for Administrator and position on hold by CGM. |  |  |  | On-going
7 | Streamline process for Self Clearance |  |  |  |  | KM/CM/AH |  |  | SG | 06-03-2024- Shaji Joby and Khalil Musa needs to have a discussion and agree for self clearance shipments, once finalize review with CGM. 29-04-2024 - Separate meeting to be arranged with CGM, Khalil, Christopher and Ayesha to discuss whole process. |  |  |  | On-going
8 | Department Update - Operations |  |  |  |  | MA |  |  | SG | 06-03-2024 - Operations department is facing scan synchronizing issue in system, same should be discussed with Saleh and obtain content details of the right person to contact. |  |  |  | On-going
9 | Department Update - SFD |  |  |  |  | ZB/TA |  |  | SG | 06-03-2024 1 - Manpower issue and delay in recruitment. 2 - NVOCC agents to visit in March SMSA Kuwait. 3 - Monitor LTL rates in market and grab the opportunities. 29-04-2024 1- In target of recruitments, CV's pipeline and waiting for interview schedule. 2- NVOCC agents - On hold. 3- Sales team already targeting the best opportunities for LTL business 4- Removal of old customer for previous sales person name. |  |  |  | On-going
10 | Department Update - HRD |  |  |  |  | All dept. |  |  | SG | 06-03-2024 1- Sick Leaves are not signed, not in compliance with SMSA policy. 2 - Manpower should be submitted to HRD Dept on 13th of every month. 3 - CAFO nominations or any other requirements requested by HRD dept should be submitted on timeline mentioned in emails 29-04-2024 1- Brief explanation by Mr. Shaji on promoting CAFO within the organization and 4 CAFO nominations should be submitted by each HOD. 2-Clearance form to be completed 1 day in advance of employee leave. |  |  |  | On-going
11 | Department Update - Sales |  |  |  |  | SJ/MA/ZB/CM |  |  | SG | 06-03-2024 - 1- Cash Customer Account issue ( To be discussed with CGM and Finance Manager separately ) 2 - UTL Updates: Needs to be followed with IT at HQ 3 - LTL transit time delays - Mohammad Azhar and Zubair Bin Ali to work and improve the LTL transit times. 29-04-2024 1- Cash customer account issue ( To be discussed with CGM and Finance Manager separately ) 2- UTL updates: Need to be check and revert with confirmation. |  |  |  | On-going
12 | 3rd Party Clearance - Service Agreement |  |  |  |  | KM/ZB/SB |  |  | SG | 29-04-2024 - Separate meeting to be scheduled with Khalil, Zubair and Sanjay to finalize the contract / service agreement for 3rd Party Clearance. |  |  |  | On-going
13 | Streamline process of Inbound LTL Shipments |  |  |  |  | KM |  |  |  | 29-04-2024 - Khalil to take up completely for LTL inbound shipments from DMM for delay in transit time, documents and all related issues for clearance and solve it. |  |  |  | On-going
14 | Delay in agents payments |  |  |  |  | ZB |  | SJ | SG | 29-04-2024 - Delay in agents payments and demurrage charges against the shipments ( To be discussed with CGM and Finance Manager separately ) |  |  |  | On-going
15 | Delay in deliver of express shipments |  |  |  |  | ZB/CM |  |  | SG | 29-04-2024 -There is an aggressive delay in delivering the express shipments to customers, delivery of the shipment takes almost 3 days. Delay in payments to DHL ( To be discussed with CGM, Zubair, Christopher separately ) Zubair to share the process. |  |  |  | On-going
16 | Department update - Finance |  |  |  |  | SB |  |  | SG | 29-04-2024 - Finance department working on cash flows and to clear all the pending outstanding until 01/05/2024. Planning to have weekly meeting with HOD to review cash receivables. |  |  |  | On-going
17 | IT Issues |  |  |  |  | KM/SJ/ZB |  |  | SG | 29-04-2024 GTW: Prepare the contingency plan for gateway and review with CGM. CS: Core and Email issue. SFD: Email issue. |  |  |  | Not started
18 | CS Issue |  |  |  |  | CM/SJ |  |  | SG | 29-04-2024 1- Majority of the shipments have service issue, detailed report is emailed to Christopher by Shaji Joby. 2- Recruitments in progress. 3- Announcement of new retail at Kuwait City by CGM. |  |  |  | Not started
19 | Municipality License for Warehouse |  |  |  |  | MA |  |  | SG | 29-04-2024 - Mohammad to provide list of all documents required to apply and obtain Municipality License for warehouse. |  |  |  | Not started
20 | MOC User |  |  |  |  | TA/MB/KM |  |  | SG | 29-04-2024 - Talal, Mohammad and Khalil to work together for MOC user. |  |  |  | On-going
21 | Uniform and ID |  |  |  |  | TA/DH |  |  | SG | 29-04-2024 - Strict following of dress code policy and issuance of uniform and ID to all employees. |  |  |  | On-going
22 | DVD |  |  |  |  | TA |  |  | SG | 29-04-2024 - Importance of DVD document and it is compulsory that its read by all staff and signed. New joiners should also read the DVD and all related policies within 1 week on joining. |  |  |  | Completed
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 13.5% | 0
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 72% | 3
Daliya Hanifa |  |  |  | DH |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 4.5% | 1
Khalil Musa |  |  |  | KM | [10 empty] | Completed |  | 10% | 0
Talal Albadawe |  |  |  | TA |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 4
Shaji Joby |  |  |  | SJ
Sanjay Bendale |  |  |  | SB |  | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.
Christopher Mendes |  |  |  | CM
Mohammed Bucheeri |  |  |  | MB
Zubair Bin Ali |  |  |  | ZB
Ayesha Haneefa |  |  |  | AH