## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | Management Meeting
Date: |  | 2024-08-12 |  |  | Start Time: |  | 11:06 |  | End Time: |  | 12:35 | Location: |  | Conference Room Kuwait
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | System and System Access |  |  |  | Christopher Mendes |  |  | 11:06
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | Logistaas |  |  |  | Sanjay Bendale
Talal Albadawe |  |  |  |  | HRD |  |  | 3 | CASS -IATA Registration |  |  |  | Shaji George
Christopher Mendes |  |  |  |  | SLS |  |  | 4 | Annual Leave |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 5 | Streamline process for Self Clearance |  |  |  | Khalil Musa
Zubair Bin Ali |  |  |  |  | SFD |  |  | 6 | Scan Synchronizing |  |  |  | Mahammad Azharuddin
Mohammed Bucheeri |  |  |  |  | ADM |  |  | 7 | 3rd Party Clearance - Service Agreement |  |  |  | Shaji George
Khalil Musa |  |  |  |  | GTW |  |  | 8 | Streamline process of Inbound LTL Shipments |  |  |  | Khalil Musa
Mahammad Azharuddin |  |  |  |  | OPS |  |  | 9 | Delay in delivery of express shipments |  |  |  | Christopher Mendes
[8 empty] | 10 | IT Issues |  |  |  | Khalil Musa
[8 empty] | 11 | SMSA SSC |  |  |  | Shaji George
[8 empty] | 12 | Recruitments |  |  |  | Talal Albadawe
[8 empty] | 13 | SDM Account |  |  |  | Shaji George
[8 empty] | 14 | Wheel and KPI |  |  |  | Shaji George
[8 empty] | 15 | Internal Audit and Self Audit |  |  |  | Shaji George
[8 empty] | 16 | Fixed Assets |  |  |  | Shaji George
[8 empty] | 17 | OVG / Unclaimed Shipments |  |  |  | Shaji George
[8 empty] | 18 | Incidents Reports |  |  |  | Shaji George |  |  | 12:10
[8 empty] | 19 | Address Issue related to Sales |  |  |  | Shaji George |  |  | 12:35
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | System and System Access |  |  |  |  | CM |  |  | SG | 26-07-2023 - SLS -POS System - Following up with HQ 27-08-2023 - Following up with HQ 28-11-2023 - Shaji Joby to follow with Kuwait IT for System and System Access 08-01-2024 - Mr. Fahad is following 06-03-2024 - Waiting for the update. 29-04-2024 - Requested PC for the retail, once received POS system will be installed. 22-07-2024 - POS active for Qibla SSC but rates not reflecting, Ardiya POS still pending as position is vacant. Further updates to be provided by Christopher. 12-08-2024 - Ardiya POS under development. Further updates to be provided by Christopher. |  |  |  | On-going
2 | Logistaas |  |  |  |  | SB |  |  | SG | 27-08-2023 - Implementation of Logistas System for SFD 28-11-2023 - System will be live by 04/01/2024 and training is scheduled. 08-01-2024 - Training in progress 06-03-2024 - Oracle and Logistas to be in effective from 01/04/2024. 29-04-2024 - Testing completed, some amendments are requested. Logistas to be in effect from 01/05/2024 22-07-2024 - Requested some enhancements in the systems, departments already using Logistaas, further updates to be provided by Sanjay. 12-08-2024 - System enhancements to be completed by next week, end to end demo should be with CGM. |  |  |  | On-going
3 | CASS -IATA Registration |  |  |  |  | SB |  |  | SG | 27-08-2023 - Registration of OCS/SMSA in CASS 28-11-2023 - Sanjay to check and submit complete details. 08-01-2024 - On hold by CGM |  |  |  | On-hold
4 | Annual Leave |  |  |  |  | SB/CM |  |  | SG | 22-07-2024 - Talal to submit list of all employee above 30 days with their confirmed leave schedule. 12-08-2024 - Sanjay and Christopher to submit leave plan by end of the day |  |  |  | On-going |  | 2024-08-12
5 | Streamline process for Self Clearance |  |  |  |  | KM/CM |  |  | SG | 06-03-2024- Shaji Joby and Khalil Musa needs to have a discussion and agree for self clearance shipments, once finalize review with CGM. 29-04-2024 - Separate meeting to be arranged with CGM, Khalil, Christopher and Ayesha to discuss whole process. 22-07-2024 - Process implemented and under trial, further updates on progress to be shared by Khalil and Christopher. 12-08-2024 - Some amendments are made in previous process, further updates on progress to be shared by Khalil and Christopher. |  |  |  | On-going
6 | Scan Synchronizing |  |  |  |  | MA/KM/SB |  |  | SG | 06-03-2024 - Operations department is facing scan synchronizing issue in system, same should be discussed with Saleh and obtain content details of the right person to contact. 22-07-2024 - Operations and Finance dept following with system Eng., further updates to be provided by Azhar and Sanjay. 12-08-2024 - Azhar, Khalil and Sanjay to come up with solution to submit the data at night. |  |  |  | On-going
7 | 3rd Party Clearance - Service Agreement |  |  |  |  | KM/ZB |  |  | SG | 29-04-2024 - Separate meeting to be scheduled with Khalil, Zubair and Sanjay to finalize the contract / service agreement for 3rd Party Clearance. 22-07-2024 - Contracts send to vendors, further update to be provided by Zubair. 12-08-2024 - Zubair to forward the format to Khalil with 3 vendors that are currently dealing with, Khalil to make sure vendors agree and submit the agreement by 01/09/2024, incase vendors fail, Khalil to find alternate vendors and replace them. |  |  |  | On-going
8 | Streamline process of Inbound LTL Shipments |  |  |  |  | KM |  |  |  | 29-04-2024 - Khalil to take up completely for LTL inbound shipments from DMM for delay in transit time, documents and all related issues for clearance and solve it. 22-07-2024 - BAH and KSA shipments still pending for analyzation. 12-08-2024 - Streamline the process to 5 working days from pickup to destination, Nadeem from SFD should maintain all the tracks of shipments and submit to Khalil on daily basis. |  |  |  | On-going
9 | Delay in delivery of express shipments |  |  |  |  | CM/MA/SB |  | SJ | SG | 29-04-2024 -There is an aggressive delay in delivering the express shipments to customers, delivery of the shipment takes almost 3 days. Delay in payments to DHL ( To be discussed with CGM, Zubair, Christopher separately ) Zubair to share the process. 22-07-2024 - New process implemented and to be discussed with CGM, Zubair, Christopher and Sanjay separately. 12-08-2024 - Christopher, Azhar and Sanjay should streamline the process. |  |  |  | On-going
10 | IT Issues |  |  |  |  | KM |  |  | SG | 29-04-2024 GTW: Prepare the contingency plan for gateway and review with CGM. CS: Core and Email issue. SFD: Email issue. 22-07-2024 - Core issues from SLS and GTW contingency plan to be discussed separately with CGM. 12-08-2024 - Khalil to organize the meeting |  |  |  | On-going
11 | SMSA SSC | [7 empty] | SG | 29-04-2024 - Announcement of new retail at Kuwait City by CGM. 22-07-2024 - Waiting for the visa's to be issued to plan the opening. |  |  |  | On-hold
12 | Recruitments |  |  |  |  | TA |  |  | SG | 22-07-2024 - Pending Recruitments: SFD: Territory Manager X1, Senior Account Manager X1, Account Executive X2, Account Executive Replacement X2, Customer Service: Customer Care Agent X2, Retail Executive X1 Sales: Territory Manager X1, Account Executive X2, Lead Qualifier X1 Finance: AR Support X1, Accountant X1 GTW: Assistant Clearance Agent X1, Operations Agent X1 12-08-2024 - On going with below addition. OPS: Operation Agent X1, Station Agent X1, Couriers X5 |  |  |  | On-going
13 | SDM Account |  |  |  |  | CM/SB |  |  | SG | 22-07-2024 - Delay in SDM account customer creation, report should be submitted to CGM 12-08-2024 - Last 3 months report should be shared by Sanjay as per the shared format by CGM. |  |  |  | On-going |  | 2024-08-15
14 | Wheel and KPI |  |  |  |  | All dept. |  |  | SG | 22-07-2024 - Brief explanation on 4 main elements of the wheel and importance of KPI. All department heads to complete the initiatives for JAN - JUN in next month's wheel with updates. 12-08-2024 - All HOD should submit wheel by 15th of each month. |  |  |  | On-going |  | 2024-08-15
15 | Internal Audit and Self Audit |  |  |  |  | All dept. |  |  | SG | 22-07-2024 - Brief explanation of audit, each head of department to obtain audit checklist from Bahrain and do the audit of their department. 12-08-2024 - All HOD's should submit the self audit report before next management meeting. |  |  |  | On-going |  | 2024-09-01
16 | Fixed Assets |  |  |  |  | MB/SB |  |  | SG | 22-07-2024 - Admin to take over the responsibility from Finance department and complete the asset tagging. 12-08-2024 - Mohd to coordinate with Sanjay and match the records in books, discard the items which are not listed as assets in books. |  |  |  | On-going |  | 2024-08-15
17 | OVG / Unclaimed Shipments |  |  |  |  | MA/MB |  |  | SG | 22-07-2024 - Admin to take over the responsibility from Operations and Finance department. Review the policy and amend with necessary changes requirement and clear all the OVG / Unclaimed shipments 12-08-2024 - Azhar to speak to QRM representative and close the task, Mohammad will share the total Gaps assigned VS total closure. |  |  |  | On-going |  | 2024-08-15
18 | Incidents Reports |  |  |  |  | CM |  |  | SG | 22-07-2024 - All department heads should submit the incidents reports. As we progress to the second stage, incidents will be categorized, reviewed with departments and action plan to be created. 12-08-2024 - No incident report received from SLS department. |  |  |  | Completed
19 | Address Issue related to Sales |  |  |  |  | All dept. |  |  | SG | All the issues related to Sales should be address to CGM directly. |  |  |  | Completed
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 0% | 0
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 78.94% | 2
Khalil Musa |  |  |  | KM |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 11% | 1
Talal Albadawe |  |  |  | TA | [10 empty] | Completed |  | 10.52% | 0
Sanjay Bendale |  |  |  | SB |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 3
Christopher Mendes |  |  |  | CM
Mohammed Bucheeri |  |  |  | MB |  | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.
Zubair Bin Ali |  |  |  | ZB
Mahammad Azharuddin |  |  |  | MA