## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | Disposal of Goods
Date: |  | 2024-08-15 |  |  | Start Time: |  | 10:03 |  | End Time: |  | 10:18 | Location: |  | CGM Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | Dispose of goods before acquisition of SMSA to OCS |  |  |  | Shaji George |  |  | 10:03
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | NON IT Assets |  |  |  | Shaji George |  |  | 10:18
Sanjay Bendale |  |  |  |  | FIN
Mahammad Azharuddin |  |  |  |  | OPS
Zakir Hussain |  |  |  |  | ITD
Mohammed Bucheeri |  |  |  |  | ADM
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Dispose of goods before acquisition of SMSA to OCS |  |  |  |  | MA/MB |  | ZH/SB | SG | It was noted that the shipments belonging to Imile, Aramex, Yicen, and cash customers are classified as misroutes or return shipments. These shipments are not linked to any Air Waybill (AWB), and no payments have been received from the customers. The shipments have been appropriately segregated, packed, sealed, and labeled. The committee responsible for overseeing the disposal process consists of Sanjay, Mahammad Azharuddin, Zakir Hussain, and Mohammed Bucheeri. Following a discussion with Mr. Marwan from QRM, it was agreed that all items would be donated to charity. Mahammad Azharuddin will lead the completion of the disposal process under the supervision of Mohammed Bucheeri. The process will include a physical verification of the items as per the provided list and ensuring that all items are correctly labeled. |  |  |  | On-going |  | 2024-08-18
2 | NON IT Assets |  |  |  |  | MA/MB/ZH |  | SB | SG | NON IT equipment's have been found during the acquisition that needs to be disposed. Items have been identified by Mr. Sadath Mirza and Mr. Mohammed Adam and further investigated by Mr. Zakir Hussain. It has been decided by committee to check for municipality taking these items or dispose items which are outdated /Sale non repairable, 3 vendor quotation should be obtained in case of Selling the non repair able items or dispose / handover to municipality. Both should be done in presence of Mohammad Bucheeri. Zakir to check and obtain three quotation and Azhar to check with municipality. |  |  |  | On-going |  | 2024-08-18
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 0% | 0
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 100% | 2
Sanjay Bendale |  |  |  | SB |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
Mahammad Azharuddin |  |  |  | MA | [10 empty] | Completed |  | 0% | 0
Zakir Hussain |  |  |  | ZH |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 2
Mohammed Bucheeri |  |  |  | MB
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.