## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | Management Meeting
Date: |  | 2024-07-22 |  |  | Start Time: |  | 11:05 AM 03:25 PM |  | End Time: |  | 01:15 PM 05:25 PM | Location: |  | Conference Room Kuwait
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | CAFO |  |  |  | All Departments |  |  | 11:05
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | System and System Access |  |  |  | Christopher Mendes
Talal Albadawe |  |  |  |  | HRD |  |  | 3 | Logistaas |  |  |  | Sanjay Bendale
Christopher Mendes |  |  |  |  | SLS |  |  | 4 | CASS -IATA Registration |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 5 | Annual Leave |  |  |  | Shaji George
Zubair Bin Ali |  |  |  |  | SFD |  |  | 6 | Streamline process for Self Clearance |  |  |  | Khalil Musa
Mohammed Bucheeri |  |  |  |  | ADM |  |  | 7 | Scan Synchronizing |  |  |  | Mahammad Azharuddin
Khalil Musa |  |  |  |  | GTW |  |  | 8 | 3rd Party Clearance - Service Agreement |  |  |  | Shaji George
Mahammad Azharuddin |  |  |  |  | OPS |  |  | 9 | Streamline process of Inbound LTL Shipments |  |  |  | Khalil Musa
[8 empty] | 10 | Delay in agents payments |  |  |  | Zubair Bin Ali
[8 empty] | 11 | Delay in deliver of express shipments |  |  |  | Christopher Mendes
[8 empty] | 12 | IT Issues |  |  |  | Khalil Musa and Christopher Mendes
[8 empty] | 13 | SMSA SSC |  |  |  | Shaji George
[8 empty] | 14 | MOC User |  |  |  | Khalil Musa |  |  | 13:15
[8 empty] | 15 | Recruitments |  |  |  | All Departments |  |  | 15:25
[8 empty] | 16 | Dress Code Policy |  |  |  | Talal Albadawe
[8 empty] | 17 | SDM Account |  |  |  | Shaji George
[8 empty] | 18 | Increase Revenue |  |  |  | Shaji George
[8 empty] | 19 | Wheel and KPI |  |  |  | Shaji George
[8 empty] | 20 | Internal Audit and Self Audit |  |  |  | Shaji George
[8 empty] | 21 | Fixed Assets |  |  |  | Shaji George
[8 empty] | 22 | OVG / Unclaimed Shipments |  |  |  | Shaji George
[8 empty] | 23 | Incidents Reports |  |  |  | Shaji George
[8 empty] | 24 | Leave Policy and break hours |  |  |  | Shaji George |  |  | 17:25
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | CAFO |  |  |  |  | All dept. |  |  |  | Nominations were discussed and CAFO winner was selected for April to June in presence of Mohd Ameen on Zoom call. |  |  |  | Completed
2 | System and System Access |  |  |  |  | CM |  |  | SG | 26-07-2023 - SLS -POS System - Following up with HQ 27-08-2023 - Following up with HQ 28-11-2023 - Shaji Joby to follow with Kuwait IT for System and System Access 08-01-2024 - Mr. Fahad is following 06-03-2024 - Waiting for the update. 29-04-2024 - Requested PC for the retail, once received POS system will be installed. 22-07-2024 - POS active for Qibla SSC but rates not reflecting, Ardiya POS still pending as position is vacant. Further updates to be provided by Christopher. |  |  |  | On-going
3 | Logistaas |  |  |  |  | SB |  |  | SG | 27-08-2023 - Implementation of Logistas System for SFD 28-11-2023 - System will be live by 04/01/2024 and training is scheduled. 08-01-2024 - Training in progress 06-03-2024 - Oracle and Logistas to be in effective from 01/04/2024. 29-04-2024 - Testing completed, some amendments are requested. Logistas to be in effect from 01/05/2024 22-07-2024 - Requested some enhancements in the systems, departments already using Logistaas, further updates to be provided by Sanjay. |  |  |  | On-going
4 | CASS -IATA Registration |  |  |  |  | SB |  |  | SG | 27-08-2023 - Registration of OCS/SMSA in CASS 28-11-2023 - Sanjay to check and submit complete details. 08-01-2024 - On hold by CGM |  |  |  | On-hold
5 | Annual Leave |  |  |  |  | TA |  |  | SG | Talal to submit list of all employee above 30 days with their confirmed leave schedule. |  |  |  | On-going |  | 2024-07-28
6 | Streamline process for Self Clearance |  |  |  |  | KM/CM |  |  | SG | 06-03-2024- Shaji Joby and Khalil Musa needs to have a discussion and agree for self clearance shipments, once finalize review with CGM. 29-04-2024 - Separate meeting to be arranged with CGM, Khalil, Christopher and Ayesha to discuss whole process. 22-07-2024 - Process implemented and under trial, further updates on progress to be shared by Khalil and Christopher. |  |  |  | On-going
7 | Scan Synchronizing |  |  |  |  | MA |  |  | SG | 06-03-2024 - Operations department is facing scan synchronizing issue in system, same should be discussed with Saleh and obtain content details of the right person to contact. 22-07-2024 - Operations and Finance dept following with system Eng., further updates to be provided by Azhar and Sanjay. |  |  |  | On-going
8 | 3rd Party Clearance - Service Agreement |  |  |  |  | ZB |  | KM/SB | SG | 29-04-2024 - Separate meeting to be scheduled with Khalil, Zubair and Sanjay to finalize the contract / service agreement for 3rd Party Clearance. 22-07-2024 - Contracts send to vendors, further update to be provided by Zubair. |  |  |  | On-going
9 | Streamline process of Inbound LTL Shipments |  |  |  |  | KM |  |  |  | 29-04-2024 - Khalil to take up completely for LTL inbound shipments from DMM for delay in transit time, documents and all related issues for clearance and solve it. 22-07-2024 - BAH and KSA shipments still pending for analyzation. |  |  |  | On-going
10 | Delay in agents payments |  |  |  |  | ZB |  | SJ | SG | 29-04-2024 - Delay in agents payments and demurrage charges against the shipments ( To be discussed with CGM and Finance Manager separately ) 22-07-2024 - Local agents ( Clearance agents ) payments still have delay in transfer ( To be discussed with CGM and Finance Manager separately ). |  |  |  | On-going
11 | Delay in deliver of express shipments |  |  |  |  | ZB/CM |  | SJ | SG | 29-04-2024 -There is an aggressive delay in delivering the express shipments to customers, delivery of the shipment takes almost 3 days. Delay in payments to DHL ( To be discussed with CGM, Zubair, Christopher separately ) Zubair to share the process. 22-07-2024 - New process implemented and to be discussed with CGM, Zubair, Christopher and Sanjay separately. |  |  |  | On-going
12 | IT Issues |  |  |  |  | KM/CM |  |  | SG | 29-04-2024 GTW: Prepare the contingency plan for gateway and review with CGM. CS: Core and Email issue. SFD: Email issue. 22-07-2024 - Core issues from SLS and GTW contingency plan to be discussed separately with CGM. |  |  |  | Not started
13 | SMSA SSC | [7 empty] | SG | 29-04-2024 - Announcement of new retail at Kuwait City by CGM. 22-07-2024 - Waiting for the visa's to be issued to plan the opening. |  |  |  | On-going
14 | MOC User |  |  |  |  | KM |  | TA/MB | SG | 29-04-2024 - Talal, Mohammad and Khalil to work together for MOC user. 22-07-2024 - Khalil to visit MOC on 24th or 25th July to check the progress on custom users in system, further update to be provided by Khalil. |  |  |  | On-going
15 | Recruitments |  |  |  |  | TA |  |  | SG | Pending Recruitments: SFD: Territory Manager X1, Senior Account Manager X1, Account Executive X2, Account Executive Replacement X2, Customer Service: Customer Care Agent X2, Retail Executive X1 Sales: Territory Manager X1, Account Executive X2, Lead Qualifier X1 Finance: AR Support X1, Accountant X1 GTW: Assistant Clearance Agent X1, Operations Agent X1 |  |  |  | On-going
16 | Dress Code Policy |  |  |  |  | ZB/SB |  | TA | SG | Dress code not in compliance with policy in SFD and Finance department, any further negligence to the policy will result in disciplinary action. |  |  |  | Completed
17 | SDM Account |  |  |  |  | CM/SB |  |  | SG | Delay in SDM account customer creation, report should be submitted to CGM |  |  |  | Not started |  | 2024-07-28
18 | Increase Revenue |  |  |  |  | All dept. |  |  | SG | All department heads to find ways to increase revenue and reduce costs. |  |  |  | Completed
19 | Wheel and KPI |  |  |  |  | All dept. |  |  | SG | Brief explanation on 4 main elements of the wheel and importance of KPI. All department heads to complete the initiatives for JAN - JUN in next month's wheel with updates. |  |  |  | On-going |  | 2024-08-18
20 | Internal Audit and Self Audit |  |  |  |  | All dept. |  |  | SG | Brief explanation of audit, each head of department to obtain audit checklist from Bahrain and do the audit of their department. |  |  |  | Not started |  | 2024-08-18
21 | Fixed Assets |  |  |  |  | MB |  |  | SG | Admin to take over the responsibility from Finance department and complete the asset tagging. |  |  |  | On-going |  | 2024-07-31
22 | OVG / Unclaimed Shipments |  |  |  |  | MB |  |  | SG | Admin to take over the responsibility from Operations and Finance department. Review the policy and amend with necessary changes requirement and clear all the OVG / Unclaimed shipments |  |  |  | On-going |  | 2024-07-31
23 | Incidents Reports |  |  |  |  | All dept. |  |  | SG | All department heads should submit the incidents reports. As we progress to the second stage, incidents will be categorized, reviewed with departments and action plan to be created. |  |  |  | Completed
24 | Leave Policy and break hours |  |  |  |  | All dept. |  |  | SG | Less than 6 working days will be unpaid leave which should be approved by CGM / Department Manager All short leaves to be approved by CGM/ Department Manager and need to be planned in advance. All unpaid leaves to be pre-approved by CGM / Department Manager Lunch break for all employees is 1 hour and should be followed strictly. |  |  |  | Completed
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 13% | 0
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 61% | 2
Khalil Musa |  |  |  | KM |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 5% | 1
Talal Albadawe |  |  |  | TA | [10 empty] | Completed |  | 21% | 0
Sanjay Bendale |  |  |  | SB |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 3
Christopher Mendes |  |  |  | CM
Mohammed Bucheeri |  |  |  | MB |  | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.
Zubair Bin Ali |  |  |  | ZB
Mahammad Azharuddin |  |  |  | MA