## 27.08.23
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting Owner/Deprtment: IBU-KWT, COR
Meeting Title/ Name: |  |  |  | Management Meeting
Date: |  | 2023-08-27 |  |  | Start Time: |  | 11:00 |  | End Time: |  | 16:30 | Location: |  | Conference Room Kuwait
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | Updates on the actionables from Last MGMT Meeting |  |  |  | Shaji George |  |  | 11:10
Talal Albadawe |  |  |  |  | HRD |  |  | 2 | Department Update |  |  |  | Head of Departments
Shaji Joby |  |  |  |  | SLS |  |  | 3 | Industry Keywords |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 4 | Attendance Machine |  |  |  | Shaji George
Mahammad Azharuddin Dharwesh |  |  |  |  | OPS |  |  | 5 | Customer Migration |  |  |  | Shaji George
Mohammed Bucheeri |  |  |  |  | ADM |  |  | 6 | Logistas System |  |  |  | Shaji George
Zubair Bin Ali |  |  |  |  | SFD |  |  | 7 | CASS -IATA Registration |  |  |  | Shaji George |  |  | 16:30
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Department Update |  |  |  |  | SB/TA |  |  | Head of Depts | 26-07-2023 - SFD- Vendor Agent payment need to be streamlined 27-08-2023 - Task completion deadline extended |  |  |  | On-going |  | 2023-09-27
[10 empty] | 26-07-2023 - SLS, SFD & OPS - Recruitments for Account Manager, Account Executive and Couriers 27-08-2023 - Task completion deadline extended |  |  |  | On-going |  | 2023-09-30
2 | System and System Access |  |  |  |  | SJ/MA |  |  | SG | 26-07-2023 - SLS -POS System - Following up with HQ 27-08-2023 - Following up with HQ |  |  |  | On-going
[10 empty] | 26-07-2023 - OPS Third party employee Name from Azhar to activate CORE Access for updating shipment 27-08-2023 - Completed |  |  |  | Completed
3 | Vision and Mission |  |  |  |  | TA/SJ/SB/MA/MB/KM |  | DH | SG | 26-07-2023 - Each HOD Should set an appointment with CGM to review and finalize their Dept Mission. 27-08-2023 - Gateway and Admin dept pending for review, rest all dept. are completed. |  |  |  | On-going
4 | Dress Code Policy |  |  |  |  | TA |  |  | SG | 26-07-2023 - Dress code Policy to be followed strictly and Talal should monitor closely the employees who are not following and can give concerns before proceeding for warning letter. 27-08-2023 - Policy is being followed and HR montioring closely. |  |  |  | Completed
5 | Incident Report |  |  |  |  | TA/SJ/SB/MA/KM/MY/MB/ZB |  | DH | SG | 26-07-2023 - All incidents reports should be submitted on time as agreed and all incidents should be reported. 27-08-2023 - To be Reveiwed and Monitored |  |  |  | On-going
6 | JD & KPI |  |  |  |  | TA/SJ/SB/MA/KM/MY/MB/ZB |  | TA | SG | 26-07-2023 - All HOD should complete and submit their team JD's and KPI's to Talal before 15th August 2023. 27-08-2023 - One on One Meeting with Mr. Shaji George for Final Review of JD and KPI's |  |  |  | Not started
7 | Kuwait Guide Access |  |  |  |  | DH |  |  | SG | 26-07-2023 - Need to follow with IT and enable the guide access with email ID for Khalil and Zubair before 15th August 2023. 27-08-2023 - Need to follow with IT and enable the guide access for Khalil |  |  |  | On-going
8 | Job Responsibility List |  |  |  |  | DH/SB |  |  | SG | 26-07-2023 - Need to review the job responsibility list with CGM and finalize before 15th August 2023. 27-08-2023 - Mr. Sanjay have to submit the Job Responsibility List. Ms. Daliya to send the consolidated Job Responsibility List for Mr. Shaji's Review |  |  |  | Not started
9 | Mgmt. Element of SMSA |  |  |  |  | TA/SJ/SB/MA/KM/MY/MB/ZB |  | DH | SG | 26-07-2023 -Explaination and understanding the mgmt. elements of SMSA, Wheel, department and individual KPI's, JD, SWOT, Interested Parties, Risk Identification and Opportunity, Org Chart. Monthly department report should be submitted to Daliya copying Mr. Shaji every month before 15th. 27-08-2023 - Need to submitted on 15th of every month |  |  |  | On-going
10 | SWOT, Risk and Opportunity |  |  |  |  | DH/TA/SJ/SB/MA/KM/MA/MB |  |  | SG | 26-07-2023 - Each HOD should set an appointment with CGM to review and finalize their department SWOT and start the Risk and Opportunity document which needs to be submitted before 15th August 2023. 27-08-2023 - Gateway and Admin dept pending for review, rest all dept. are completed. |  |  |  | On-going
11 | QRM |  |  |  |  | DH/TA/SJ/SB/MA/KM/MA/ZB |  |  | SG | 26-07-2023 -Mohammad Bucheeri will lead and close all the NC and Gaps listed by QRM with each HOD, each HOD should follow the file shared by Mohammad and update the initiatives taken to close the NC and Gaps and submit before 2nd of every month. 27-08-2023 -Each HOD should follow the file shared by Mohammad and update the initiatives taken to close the NC and Gaps and submit before 2nd of every month and it have to be reviewed by Mr. Shaji |  |  |  | On-going
12 | Sick Leave and Policy |  |  |  |  | DH/SJ/SB/MA/KM/MA/ZB/MB |  | TA | SG | 26-07-2023 - Each HOD should be responsible for their team sick leave, annual leave or etc. The employee should not communicate to HRD for anything directly, all the communications should be reported to HOD and HOD should report to HRD dept. 27-08-2023 - Implemented and being followed |  |  |  | Completed
13 | Attendance Machine |  |  |  |  | TA |  | DH | SG | Talal to initiate process to acquire attendance machine to facilitate proper and timely attendance for the PayRoll. |  |  |  | Not started |  | 2023-09-30
14 | Customer Migration |  |  |  |  | SJ |  |  | SG | Major Ecommerce customer migration to SMSA System |  |  |  | On-going |  | 2023-09-30
15 | Logistas System |  |  |  |  | SB/ZB |  |  | SG | Implementation of Logistas System for SFD |  |  |  | Not started |  | 2023-09-30
16 | CASS -IATA Registration |  |  |  |  | SB |  |  | SG | Regisration of OCS/SMSA in CASS |  |  |  | On-going |  | 2023-09-30
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 22.22% | 4
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 61.11% | 11
Talal Albadawe |  |  |  | TA |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
Shaji Joby |  |  |  | SJ | [10 empty] | Completed |  | 16.67% | 3
Sanjay Bendale |  |  |  | SB |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 18
Mahammad Azharuddin Dharwesh |  |  |  | MA
Mohammed Bucheeri |  |  |  | MB |  | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.
Zubair Bin Ali |  |  |  | ZB