## 27.08.23
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting Owner/Deprtment: IBU-KWT, COR
Meeting Title/ Name: |  |  |  | Management Meeting
Date: |  | 2023-11-28 |  |  | Start Time: |  | 11:10 |  | End Time: |  | 13:00 | Location: |  | Conference Room Kuwait
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | Updates on the actionable from Last MGMT Meeting |  |  |  | Shaji George |  |  | 11:10
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | Attendance |  |  |  | Shaji George
Talal Albadawe |  |  |  |  | HRD |  |  | 3 | ID Cards |  |  |  | Shaji George
Shaji Joby |  |  |  |  | SLS |  |  | 4 | Employee Survey and Customer Survey |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 5 | Policy and Procedures |  |  |  | Shaji George
Mahammad Azharuddin Dharwesh |  |  |  |  | OPS |  |  | 6 | Review of Documents |  |  |  | Shaji George
Mohammed Bucheeri |  |  |  |  | ADM |  |  | 7 | 3rd Party Delivery |  |  |  | Shaji George
Khalil Musa |  |  |  |  | GTW |  |  | 8 | Annual Operating Plan |  |  |  | Shaji George
[8 empty] | 9 | Time Table |  |  |  | Shaji George
[8 empty] | 10 | Annual Leave Planning |  |  |  | Shaji George |  |  | 13:00
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Department Update |  |  |  |  | TA |  |  | Head of Depts | 26-07-2023 - SLS, SFD & OPS - Recruitments for Account Manager, Account Executive and Couriers 27-08-2023 - Task completion deadline extended. 28-11-2023 - All Recruitments should be completed before 31-12-2023 |  |  |  | On-going |  | 2023-12-31
2 | System and System Access |  |  |  |  | SJ |  |  | SG | 26-07-2023 - SLS -POS System - Following up with HQ 27-08-2023 - Following up with HQ 28-11-2023 - Shaji Joby to follow with Kuwait IT for System and System Access |  |  |  | On-going |  | 2023-12-31
3 | Incident Report |  |  |  |  | TA/SJ |  | DH | SG | 26-07-2023 - All incidents reports should be submitted on time as agreed and all incidents should be reported. 27-08-2023 - To be Reviewed and Monitored 28-11-2023 - Weekly incidents reports are not being submitted by Sanjay and Talal, need to be monitored |  |  |  | On-going
4 | JD & KPI |  |  |  |  | TA/SJ/SB/MA/MB/KM |  | TA | SG | 26-07-2023 - All HOD should complete and submit their team JD's and KPI's to Talal before 15th August 2023. 27-08-2023 - One on One Meeting with Mr. Shaji George for Final Review of JD and KPI's 28-11-2023 - All JD's and KPI's needs to be completed and submitted before end of the year |  |  |  | On-going |  | 2023-12-31
5 | Job Responsibility List |  |  |  |  | SB |  |  | SG | 26-07-2023 - Need to review the job responsibility list with CGM and finalize before 15th August 2023. 27-08-2023 - Mr. Sanjay have to submit the Job Responsibility List. Ms. Daliya to send the consolidated Job Responsibility List for Mr. Shaji's Review 28-11-2023 - Sanjay needs to be submit Job Responsibility List for department |  |  |  | Not started |  | 2023-12-31
6 | SWOT, Risk and Opportunity |  |  |  |  | TA/SJ/SB/MA/KM/MA/MB |  | DH | SG | 26-07-2023 - Each HOD should set an appointment with CGM to review and finalize their department SWOT and start the Risk and Opportunity document which needs to be submitted before 15th August 2023. 27-08-2023 - Gateway and Admin dept pending for review, rest all dept. are completed. 28-11-2023 - Submit the completed SWOT, risk and Opportunity for year 2023 and new SWOT, Risk and Opportunity for year 2024 |  |  |  | On-going |  | 2024-12-31
7 | Logistas System |  |  |  |  | SB/ZB |  |  | SG | 27-08-2023 - Implementation of Logistas System for SFD 28-11-2023 - System will be live by 04/01/2024 and training is scheduled. |  |  |  | On-going
8 | CASS -IATA Registration |  |  |  |  | SB |  |  | SG | 27-08-2023 - Registration of OCS/SMSA in CASS 28-11-2023 - Sanjay to check and submit complete details |  |  |  | On-going
9 | Attendance |  |  |  |  | TA/SJ/SB/MA/MB/KM |  |  | SG | If head of departments are late to work the same needs to be CGM, and if there employees are late to work the same need to be reported to Head of departments and not HR. Talal need to be make sure all staff is on attendance machine and in case anyone arrives office after 8:15am will have salary deduction. |  |  |  | Completed
10 | ID Cards |  |  |  |  | TA |  |  | SG | Talal need to start working to get SMSA ID's for all employees with SMSA lanyards |  |  |  | Not started |  | 2023-12-31
11 | Employee Survey and Customer Survey |  |  |  |  | TA/SJ/SB/MA/MB/KM |  |  | SG | Brief introduction on survey and why its done. |  |  |  | Completed
12 | Policy and Procedures |  |  |  |  | DH/TA/SJ/SB/MA/MB/KM |  |  | SG | All HOD's needs to make sure they submit the required policy and procedures that should be on guide and is followed daily. |  |  |  | On-going |  | 2023-12-31
13 | Review of Documents |  |  |  |  | DH/TA/SJ/SB/MA/MB/KM |  |  | SG | SWOT, Risk and Opportunity, Interested Parties and year end evaluation (for each and every employee) should be completed and submitted |  |  |  | On-going |  | 2023-12-31
14 | 3rd Party Delivery |  |  |  |  | MB/TA/SB |  | DH | SG | Mohammad Bucheeri to prepare vendor comparison report, Sanjay to review the financial cost and background of vendor and Talal to check the legal compliance of branding the vehicle and if couriers to wear SMSA uniform |  |  |  | On-going |  | 2023-12-31
15 | Annual Operating Plan |  |  |  |  | ZB/TA/SJ/SB/MA/MB/KM |  |  | SG | All HOD's should submit their annual operating plan for the year 2024 |  |  |  | Not started |  | 2023-12-31
16 | Time Table |  |  |  |  | ZB/TA/SJ/SB/MA/MB/KM |  |  | SG | Each HOD should submit their department timing to HR |  |  |  | Not started |  | 2023-12-31
17 | Annual Leave Planning |  |  |  |  | ZB/TA/SJ/SB/MA/MB/KM |  |  | SG | Each HOD should prepare their department annual leave plan for year 2024 |  |  |  | Not started |  | 2023-12-31
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 29% | 3
Shaji George |  |  |  | SG | [10 empty] | On-going |  | 58% | 10
Daliya Hanifa |  |  |  | DH |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
Khalil Musa |  |  |  | KM | [10 empty] | Completed |  | 13% | 2
Talal Albadawe |  |  |  | TA |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | 15
Shaji Joby |  |  |  | SJ
Sanjay Bendale |  |  |  | SB |  | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.
Mahammad Azharuddin Dharwesh |  |  |  | MA
Mohammed Bucheeri |  |  |  | MB
Zubair Bin Ali |  |  |  | ZB