## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | CSD and FIN Process Review
Date: |  | 2024-07-11 |  |  | Start Time: |  | 11:05 |  | End Time: |  | 12:15 | Location: |  | CGM Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | Logitaas |  |  |  | Shaji George |  |  | 11:05
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | Booking Form |  |  |  | Shaji George
Christopher S. Mendes |  |  |  |  | SLS |  |  | 3 | Cash Submission of Retail |  |  |  | Shaji George
Ayesha Haneefa |  |  |  |  | CSD |  |  | 4 | Cash Sales Account |  |  |  | Shaji George
Sanjay Bendale |  |  |  |  | FIN |  |  | 5 | Guide - Process Review |  |  |  | Shaji George |  |  | 12:15
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Logitaas |  |  |  |  | AH/CS/SB |  |  | SG | Logistaas should be discontinued immediately, no CSD staff should be involved in process related to billing or reconciliation. Financial details requirements should be shared by Finance Manager to CSD staff and should be ineffective from 1st August without any exemption request. CSD to maintain Job files and share the report by the end of month to Finance team. |  |  |  | Not started |  | 2024-07-31
2 | Booking Form |  |  |  |  | AH/CS |  |  | SG | Christopher and Ayesha to create a booking form for customers, all details that are necessary to book the shipment should be present on the form with terms and conditions mentioning. |  |  |  | On-going |  | 2024-07-31
3 | Cash Submission of Retail |  |  |  |  | AH |  |  | SG | Physical submission of report to be made only, RTL executive should not send any email for confirmation or acknowledgement TO Finance team. |  |  |  | Completed
4 | Cash Sales Account |  |  |  |  | AH/CS/LZ |  |  | SG | When sales requesting pickup or drop off for shipments for their customers, Liju to send rate to RTL executive copy email to Finance department mentioning under which account number it should be booked. Upon receiving the shipment RTL executive / Booking agent to check the dimensions and weight and if its remote delivery area and collect the charges if needed. CSD will not interfere to send payment links to clients. |  |  |  | Completed
5 | Guide - Process Review |  |  |  |  | AH |  |  | SG | Ayesha to read the policy and process uploaded on guide for Inbound and Outbound shipments to make sure its updated according to what is discussed and followed. |  |  |  | On-going |  | 2024-07-31
NAME MATRIX | [5 empty] | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 20%
Name of Initiator |  |  |  | Initials | [10 empty] | On-going |  | 40% | #REF!
Christopher S. Mendes |  |  |  | CS |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | #REF!
Ayesha Haneefa |  |  |  | AH | [10 empty] | Completed |  | 40% | #REF!
Sanjay Bendale |  |  |  | SB |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | #REF!
Liju Zachariah |  |  |  | LZ | [13 empty] | #REF!
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.