## MOM
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | CSD and RTL Department Management
Date: |  | 2024-06-02 |  |  | Start Time: |  | 14:10 |  | End Time: |  | 14:45 | Location: |  | CGM Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Shaji George |  |  |  |  | COR |  |  | 1 | Structure of CSD and RTL |  |  |  | Shaji George |  |  | 14:10
Daliya Hanifa |  |  |  |  | COR |  |  | 2 | Guide Access |  |  |  | Shaji George
Christopher S. Mendes |  |  |  |  | SLS |  |  | 3 | Review Documents |  |  |  | Shaji George |  |  | 14:45
Ayesha Haneefa |  |  |  |  | CSD
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Structure of CSD and RTL |  |  |  |  | AH |  | CS | SG | 1. Submit the Organization chart of CSD and RTL department. 2. Review of JD's for all employees in CSD and RTL department. 3. Recruitment of 2 CSD and 2 RTL staff ( limited to first level only, final review and approval to be given by Mr. Christoper) |  |  |  | Not started |  | 2024-06-30
2 | Guide Access |  |  |  |  | DH |  |  | SG | Enable the guide access for Ayesha to review CSD and RTL documents. |  |  |  | Not started |  | 2024-06-30
3 | Review Documents |  |  |  |  | AH |  | CS | SG | 1. Review all previously uploaded documents related to CSD and RTL on Guide to make sure its in compliance with employees and process which includes policies, process maps and work instructions. 2. Operations and CSD work process need to be review and make sure its with compliance and uploaded on guide. 3. Read the complaint handling policy. |  |  |  | Not started |  | 2024-06-30
NAME MATRIX | [5 empty] | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 100%
Name of Initiator |  |  |  | Initials | [10 empty] | On-going |  | 0% | #REF!
Daliya Hanifa |  |  |  | DH |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | #REF!
Christopher S. Mendes |  |  |  | CS | [10 empty] | Completed |  | 0% | #REF!
Ayesha Haneefa |  |  |  | AH |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [8 empty] | #REF!
#REF!
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.