## 10-06-2024
Department |  |  | Status |  |  | Location
ADM |  |  | Not started
COR |  |  | On-going
CSD |  |  | On-hold
FIN |  |  | Completed
HRD
IAD
ITD
LGL
LOG
MKT
MRM
OPS
QRM
RTL
SFD
SLS
SDC
Minutes of Meeting
Meeting Title/ Name: |  |  |  | CSD & OPS New SSC opening operations
Date: |  | 2024-06-10 |  |  | Start Time: |  | 12:00 |  | End Time: |  | 12:30 | Location: |  | OPS Supervisor Office
Attendees | [7 empty] | Agenda
Name |  |  |  |  | Department |  |  | Item | Topic/ Agenda Item |  |  |  | Presenter |  |  | Time
Ayesha Haneefa |  |  |  |  | CSD |  |  | 1 | Cut off timings for HAL & IP shipments |  |  |  | Mahammad Azharuddin |  |  | 12:00
Mahammad Azharuddin |  |  |  |  | OPS |  |  | 2 | Shipments handover packing & manifest |  |  |  | Suresh Kumar |  |  | 12:05
Suresh Kumar |  |  |  |  | OPS |  |  | 3 | Pre-alert to OPS & Finance |  |  |  | Mahammad Azharuddin |  |  | 12:10
[8 empty] | 4 | Cash collection packing & hand overing |  |  |  | Ayesha Haneefa |  |  | 12:20
[8 empty] | 5 | Supplies order |  |  |  | Suresh Kumar / Ayesha Haneefa |  |  | 12:25
SN. | Action Item |  |  |  |  | R | A | C | I | Action Taken/ Remarks |  |  |  | Status |  | Deadline
1 | Cut off timings for HAL & IP shipments |  |  |  |  | AH/SK |  |  | MA | •HAL shipments requests routing through CS tickets will be actioned & delivered by 10:00 next day in SSC Qibla. •Shipments for SSC & any HAL requested delivery with cash collection with be collected by SMSA Courier at 15:30. Any shipment received after cutoff will be collected next day at 15:30 by SMSA Courier. •No same day connection for SMSA (Air / Land) linehaul & IP (Third Party) |  |  |  | Not started |  | 2024-08-01
2 | Shipments handover packing & manifest |  |  |  |  | AH/SK |  |  | MA | •Shipments with (Envelop , PAK , small boxes ) will be scanned in manifest and will be sealed in one bag with SMSA Tag , heavy shipments to be snacked and hand overed separately. •Manifest will have each shipment AWB No , tag no , no of pcs with remarks of SMSA Tag stating number of shipments in bag and loose boxes. |  |  |  | Not started |  | 2024-08-01
3 | Pre-alert to OPS & Finance |  |  |  |  | AH/SK |  |  | MA | •Pre-alert to HUB will be shared by the SSC Executive confirming the services of each shipment in Manifest •Pre-alert to Finance will be shared by SSC Executive with cash collection report as per SMSA Standard style. |  |  |  | Not started |  | 2024-08-01
4 | Cash collection packing & hand overing |  |  |  |  | AH/SK |  |  | MA | •Non revenue AWB will be generated by CS TL and will be shared to SSC Executive. PUP Scan will be applied by SSC Executive. •SSC Executive will put all the cash collection & receipts & bank reconciliation in an envelop with cash collection report this will be sealed through a HV tag and HV Tag number will be mentioned on SSC to OPS manifest. Hand overing to be done in front of CCTV Cameras •POD scan will be closed by courier upon submission to Finance. |  |  |  | Not started |  | 2024-08-01
5 | Supplies order |  |  |  |  | AH/SK |  |  | MA | • Supply order to be managed and ordered through TKT. • Incase of any urgency supplies can be provided by SSC Executive through CS TL email confirmation and the supplies can be provided next day by OPS Supervisor. |  |  |  | Not started |  | 2024-08-01
NAME MATRIX
Name of Initiator |  |  |  | Initials |  | R | Responsible |  | People who do the work. Complete the task. Make decisions. Several people can be responsible. | [5 empty] | Not started |  | 100% | 4
Ayesha Hanifa |  |  |  | AH | [10 empty] | On-going |  | 0% | 0
Mahammad Azharuddin |  |  |  | MA |  | A | Accountable |  | Person who is the owner of the work. Sign off the task decisions that have been completed. Assign responsibility. This will always be one person "THE BUCK STOPS HERE" | [5 empty] | On-hold |  | 0% | 0
Suresh Kumar |  |  |  | SK |  | C | Consulted |  | People who need to give input before the work can be done. People who are in the loop and active participants. | [5 empty] | Completed |  | 0% | 4
[6 empty] | I | Informed |  | Inform the people who needs to be kept in the picture. Does not contribute directly to the task or decision but need to know the progress.