## SWOT-IT
Department: Information Technology
SWOT Analysis
Criteria Examples Advantages ? Capabilities ? Competitive advantages ? USP's (unique selling points) Resources, Assets, People? Experience , knowledge, data ? Financial reserves, likely returns ? Marketing - reach, distribution, awareness? Innovative aspects ? Location and geographical ? Price, value, quality ? Accreditations, qualifications, certifications ? communications ? Cultural behavioural ? | Strenghts |  | Weaknesses | Criteria examples Disadvantages ? Gaps in capabilities ? Lack of competitive strength ? Reputation, presence and reach ? Financials ? Timescales, deadlines and pressures ? Cash flow, start-up cash drain ? Continuity, supply chain ? Effects on core activities, distraction ? Reliability of data, plan predictability ?
| Provide Information Technology solutions to all departments. Integrate with customers and business partners. Provide network infrastructure to all SMSA locations. Provide unified communication across SMSA offices. Provide Management Information System data to business units, decision makers, and partners. Provide customized technology solutions based on business needs. Provide cloud computing services and high availability for critical applications and major locations. Increase return on investment from technology solutions. Deliver innovative technology solutions. Improve cost efficiency through technology. |  | Lack of sufficient Information Technology staff compared to business needs. Unplanned Information Technology requirements without proper request and approval process. Limited budget for implementation of new Information Technology improvements and innovations. Critical systems without adequate backup or redundancy. Information Technology personnel reporting outside the Information Technology department structure. Poor data center condition. Lack of workspace and storage for Information Technology staff and equipment.
Criteria Examples Market developments ? Competitors' vulnerabilities ? Industry of lifestyle trends ? Technology development and innovation ? Global influences ? New markets, vertical, horizontal ? Niche target markets ? Geographical, export, import ? Tactics : eg,surprise, major contracts ? Business and product development ? Partnerships, agencies, distribution ? | Opportunities |  | Threats | Criteria Examples Political effects ? Legislative effects ? Enviornmental effects ? IT developments ? Competitor intentions- various ? Market demand ? New technologies, services, ideas ? Vital contra cts and partners ? Sustaining internal capabilities ? Obstacles faced ? Insurmountable weaknesses ? Loss of key staff ? Sustainable financial backing ? Economy - home abroad ?
| Enhance CORE and other business systems. Develop unified customer portals. Improve electronic services. Expand infrastructure for better system performance. Implement Fusion ERP. |  | Inadequate disaster recovery capability. Data center environmental risks, including cooling, fire protection, and alarm systems. Lack of redundancy in network providers and critical systems. Dependence on third-party vendors. Delays in purchasing and approvals. Loss of critical Information Technology knowledge due to staff departure.

## STR Risks ITD
Risk ID | Risk Category | Risk Description | Main Cause | Likelihood (1-3) | Impact (1-3) | Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Status | Last Review Date | Next Review Date
IT-SR-01 | People | Lack of sufficient IT staff affecting IT operations | Limited staffing compared to business needs | 2 | 3 | 6 | CTO | Current IT team structure | Reduce | Assess staffing requirements and recruit additional IT personnel; provide training for existing staff where required | IT National Manager / HR | 2026-09-30 | 2 | 2 | 4 | Open | 2026-03-01 | 2026-06-01 | Reduce | Open
IT-SR-02 | Service Management | Unplanned IT requirements without proper request process | Requests raised without proper approval or planning | 2 | 2 | 4 | IT National Manager | Informal request handling exists | Reduce | Implement a formal request and approval process for IT work and changes | IT National Manager | 2026-08-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01 | Transfer | Addressed
IT-SR-03 | Finance | Insufficient IT budget for improvements and innovation | Limited funding for upgrades and new initiatives | 2 | 3 | 6 | CTO | Annual budget discussion | Reduce | Prepare annual IT budget plan and prioritize key improvements with Finance | CTO / FIN | 2026-10-31 | 2 | 2 | 4 | Open | 2026-03-01 | 2026-06-01 | Avoid
IT-SR-04 | Infrastructure | Critical systems operating without adequate backup or redundancy | Incomplete backup and redundancy arrangements for critical services | 2 | 3 | 6 | IT National Manager | Partial backup arrangements | Reduce | Implement backup and redundancy for critical systems that do not currently have sufficient protection | IT National Manager | 2026-10-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01 | Accept
IT-SR-05 | Governance | IT personnel reporting outside the IT department structure | IT staff governed by different departments instead of centralized IT management | 2 | 2 | 4 | CTO | Partial coordination between teams | Reduce | Centralize governance of all IT personnel under the IT department structure | CTO | 2026-09-30 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01 | NA
IT-SR-06 | Infrastructure | Poor data center condition affecting system reliability | Environmental, layout, or housekeeping issues in the data center | 2 | 3 | 6 | IT National Manager | Basic facility checks | Reduce | Conduct regular data center condition reviews and correct environmental issues | IT National Manager | 2026-08-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-07 | Facilities | Lack of workspace and storage for IT staff and equipment | Insufficient allocated office and storage space | 2 | 2 | 4 | IT National Manager | Existing office allocation | Reduce | Allocate proper workspace and storage for IT staff, spare parts, and equipment | IT National Manager | 2026-09-30 | 1 | 1 | 1 | Open | 2026-03-01 | 2026-06-01
IT-SR-08 | Business Continuity | Inadequate disaster recovery capability | Recovery process not fully defined or tested | 2 | 3 | 6 | IT National Manager | Backup procedures exist | Reduce | Maintain disaster recovery plan and perform regular recovery testing | IT National Manager | 2026-09-15 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-09 | Infrastructure | Data center environmental failure | Weak cooling, fire protection, alarm, or monitoring arrangements | 2 | 3 | 6 | IT National Manager | Basic cooling and fire systems | Reduce | Maintain cooling systems, fire protection, alarms, and environmental monitoring | IT National Manager | 2026-09-30 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-10 | Network | Lack of redundancy in network providers and critical connectivity | Single points of failure in links or provider arrangements | 2 | 3 | 6 | IT National Manager | Current network setup | Reduce | Implement network redundancy and alternative connectivity for critical operations | IT National Manager | 2026-10-15 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-11 | Vendor Management | Dependence on third-party vendors affecting service availability | High reliance on external providers for support or hosted services | 2 | 3 | 6 | IT National Manager | Existing vendor contracts | Reduce | Review vendor performance regularly and maintain valid support and service agreements | IT National Manager / PUR | 2026-10-01 | 2 | 2 | 4 | Open | 2026-03-01 | 2026-06-01
IT-SR-12 | Procurement | Delays in purchasing and approvals affecting IT operations | Slow approvals or procurement delays | 2 | 2 | 4 | CTO | Procurement process exists | Reduce | Improve follow-up and coordination with Procurement and Finance for IT purchasing | CTO / PUR / FIN | 2026-08-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-13 | Infrastructure | Lack of redundancy for core infrastructure systems | Core infrastructure components do not have full failover arrangements | 2 | 3 | 6 | IT National Manager | Partial redundancy exists | Reduce | Implement redundancy for core infrastructure supporting critical business services | IT National Manager | 2026-10-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01
IT-SR-14 | Knowledge Management | Loss of critical IT knowledge due to staff departure | Key staff leaving without proper documentation or handover | 2 | 3 | 6 | IT National Manager | Some documentation exists | Reduce | Maintain up-to-date documentation and ensure knowledge transfer before staff changes | IT National Manager | 2026-08-31 | 2 | 1 | 2 | Open | 2026-03-01 | 2026-06-01