## IT-Tech Risk Document
Asset/System | Process | Threat | Vulnerability | Confidentiality (1-5) | Integrity (1-5) | Availability (1-5) | Impact (Max of CIA) | Likelihood (1-5) | Inherent Risk Score/ Level (R/Y/G) | Risk Owner | Existing Controls | Treatment Decision | Treatment Actions | Target Date | Residual Impact | Residual Likelihood | Residual Risk Score | Acceptance Authority | Status | Risk ID | Asset Domain | Location | In Scope (Y/N) | Risk Scenario Description | Annex A Control Mapping | Responsible Person | Last Review Date | Next Review Date
Active Directory / Identity Platform | User provisioning & authentication | Credential theft / account takeover | Weak password policy; limited MFA coverage | 5 | 4 | 4 | 5 | 2 | 10 | National IT Manager | MFA for admin; password policy; account lockout; periodic access reviews | Reduce | Enforce MFA for all users; implement conditional access; disable legacy protocols; strengthen PAM |  |  |  | 0 | CTO | Open | IT-001 | Identity & Access | Head Office ITD | Y | Credential theft / account takeover exploits Weak password hygiene; legacy auth; limited MFA coverage affecting Active Directory / Identity Platform, impacting confidentiality/integrity/availability. | A.5.15, A.5.16, A.8.2, A.8.5 | National IT Manager | 2026-03-01 | 2026-05-30 | Reduce | Open | Y
Microsoft 365 / Email | Messaging & collaboration | Phishing / Business Email Compromise | User susceptibility; weak email filtering; limited DMARC/SPF/DKIM | 4 | 4 | 3 | 4 | 3 | 12 | National IT Manager | Secure email gateway; awareness training; SPF/DKIM partially enabled | Reduce | Enable DMARC enforcement; tune anti-phishing; mailbox auditing; targeted simulations |  |  |  | 0 | CTO | Open | IT-002 | Collaboration | Cloud Platform | Y | Phishing / BEC exploits User susceptibility; weak email filtering; insufficient DMARC/SPF/DKIM enforcement affecting Microsoft 365 / Email, impacting confidentiality/integrity/availability. | A.6.3, A.8.7, A.8.23 | National IT Manager | 2026-03-01 | 2026-05-30 | Transfer | Addressed | N
Endpoint Fleet (Laptops / Desktops) | Workstations & user computing | Malware / ransomware | Unpatched endpoints; missing EDR; local admin rights | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | Antivirus; partial EDR; imaging baseline | Reduce | Deploy EDR to 100%; remove local admin; patch SLAs; application control |  |  |  | 0 | CTO | Open | IT-003 | Endpoints | Head Office ITD | Y | Malware / ransomware exploits Unpatched endpoints; missing EDR coverage; local admin rights affecting Endpoint Fleet (Laptops/Desktops), impacting confidentiality/integrity/availability. | A.8.1, A.8.7, A.8.9 | National IT Manager | 2026-03-01 | 2026-05-30 | Avoid
Core Logistics System (CORE) | Parcel processing & tracking | Unauthorized access / misuse | Excessive privileges; weak RBAC; limited monitoring | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | Named accounts; periodic review; ticket approvals (partial) | Reduce | RBAC review; least privilege; privileged logging; quarterly access certification |  |  |  | 0 | CTO | Open | IT-004 | Business Applications | Head Office ITD | Y | Unauthorized access / misuse exploits Excessive privileges; weak RBAC; limited monitoring affecting Core Logistics System / Shipping Platform (CORE), impacting confidentiality/integrity/availability. | A.8.15, A.8.16 | National IT Manager | 2026-03-01 | 2026-05-30 | Accept
Warehouse Management / Sorting Systems | Operations systems | Service outage / disruption | Single points of failure; weak failover; limited capacity monitoring | 3 | 3 | 5 | 5 | 2 | 10 | National IT Manager | Basic monitoring; vendor support; backups | Reduce | Implement HA; capacity monitoring; failover tests; define and test RTO/RPO |  |  |  | 0 | CTO | Open | IT-005 | Business Applications | Head Office ITD | Y | Service outage / disruption exploits Single points of failure; limited failover; insufficient capacity monitoring affecting Warehouse Management / Sorting Systems, impacting confidentiality/integrity/availability. | A.8.14, A.8.15 | National IT Manager | 2026-03-01 | 2026-05-30 | NA
VPN Remote Access | Remote connectivity | Brute force / credential stuffing | Weak MFA; exposed login services; insufficient geo/IP restrictions | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | MFA for some users; firewall rules; logs retained | Reduce | Mandatory MFA; lockout policies; anomaly alerts; restrict admin access paths |  |  |  | 0 | CTO | Open | IT-006 | Identity & Access | Head Office ITD | Y | Brute force / credential stuffing exploits Weak MFA; exposed login; insufficient geo/IP restrictions affecting VPN Remote Access, impacting confidentiality/integrity/availability. | A.5.15, A.5.16, A.8.2, A.8.5 | National IT Manager | 2026-03-01 | 2026-05-30
Perimeter Firewalls / Internet Edge | Network security | Exploitation of exposed services | Misconfiguration; outdated firmware; weak rule review | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | Change management; periodic reviews (ad hoc) | Reduce | Firmware lifecycle plan; monthly rule recertification; external exposure review; config backups |  |  |  | 0 | CTO | Open | IT-007 | Network | Head Office ITD | Y | Exploitation of exposed services exploits Misconfigurations; outdated firmware; weak rule review discipline affecting Perimeter Firewalls / Internet Edge, impacting confidentiality/integrity/availability. | A.8.20, A.8.21, A.8.22 | National IT Manager | 2026-03-01 | 2026-05-30
Cloud Backup Platform | Backup & recovery | Backup compromise / deletion | Shared admin accounts; no immutability; poor segregation | 5 | 4 | 5 | 5 | 3 | 15 | National IT Manager | Regular backups; offsite copies (partial) | Reduce | Enable immutable backups; segregate admin; MFA; offline copy; quarterly restore tests |  |  |  | 0 | CTO | Open | IT-008 | Resilience | Cloud Platform | Y | Backup compromise / deletion exploits Shared admin accounts; no immutability; insufficient segregation affecting Cloud Backup Platform, impacting confidentiality/integrity/availability. | A.8.13, A.8.14 | National IT Manager | 2026-03-01 | 2026-05-30
Cloud Storage (Azure / AWS) | File storage & sharing | Data exposure due to misconfiguration | Public access; weak permissions; missing DLP | 5 | 3 | 3 | 5 | 2 | 10 | National IT Manager | Access controls; limited monitoring | Reduce | CSPM checks; private by default; DLP policies; periodic permission review |  |  |  | 0 | CTO | Open | IT-009 | Cloud | Cloud Platform | Y | Data exposure from misconfiguration exploits Public access; weak permissions; no DLP affecting Cloud Storage (Azure/AWS buckets), impacting confidentiality/integrity/availability. | A.5.23, A.8.12, A.8.24 | National IT Manager | 2026-03-01 | 2026-05-30
Server Patch Management (Windows/Linux) | Vulnerability management | Exploitation of known vulnerabilities | Delayed patching; incomplete asset inventory | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | Monthly patch cycle (not enforced) | Reduce | Complete asset inventory; critical patch SLA; vulnerability scanning & tracking |  |  |  | 0 | CTO | Open | IT-010 | Infrastructure | Head Office ITD | Y | Exploitation of known vulnerabilities exploits Delayed patching; incomplete asset inventory affecting Server Patch Management (Windows/Linux), impacting confidentiality/integrity/availability. | A.8.8 | National IT Manager | 2026-03-01 | 2026-05-30
Database Servers (Customer / Shipment Data) | Data hosting | Unauthorized change / corruption | Weak change control; limited DB auditing | 5 | 5 | 4 | 5 | 2 | 10 | National IT Manager | Backups; limited audit logging | Reduce | Enable DB auditing; separation of duties; integrity monitoring; controlled change approvals |  |  |  | 0 | CTO | Open | IT-011 | Data Protection | Head Office Data Center | Y | Unauthorized change / corruption exploits Weak change controls; limited DB auditing; insufficient integrity checks affecting Database Servers (Customer/Shipment Data), impacting confidentiality/integrity/availability. | A.8.12, A.8.16, A.8.24 | National IT Manager | 2026-03-01 | 2026-05-30
Data Center Power & Cooling | IT infrastructure support | Power / cooling failure | Insufficient redundancy; inadequate monitoring | 1 | 2 | 5 | 5 | 2 | 10 | National IT Manager | UPS; generator; maintenance contracts | Reduce | Redundancy review; preventive maintenance; environmental monitoring; incident runbooks |  |  |  | 0 | CTO | Open | IT-012 | Infrastructure | Head Office Data Center | Y | Power/cooling failure exploits Insufficient redundancy; inadequate monitoring; maintenance gaps affecting Data Center Power & Cooling, impacting confidentiality/integrity/availability. | A.7.4, A.7.5, A.7.8 | National IT Manager | 2026-03-01 | 2026-05-30
Virtualization Platform (VMware / Hyper-V) | Hosting environment | Hypervisor compromise / misconfiguration | Weak admin controls; delayed patching | 4 | 4 | 5 | 5 | 3 | 15 | National IT Manager | Admin access limited (partial); backups | Reduce | PAM for admins; patching; hardening baseline; logging to SIEM |  |  |  | 0 | CTO | Open | IT-013 | Infrastructure | Head Office Data Center | Y | Hypervisor compromise / misconfiguration exploits Weak admin controls; delayed patches; shared accounts affecting Virtualization Platform (VMware/Hyper-V), impacting confidentiality/integrity/availability. | A.8.20, A.8.21 | National IT Manager | 2026-03-01 | 2026-05-30
Network Switches / Routers | Network availability | Network outage | Hardware failure; lack of redundancy | 2 | 3 | 5 | 5 | 3 | 15 | National IT Manager | Some redundancy; manual backups | Reduce | Standard configs; change control; automated config backup; monitoring |  |  |  | 0 | CTO | Open | IT-014 | Network | Head Office ITD | Y | Misconfiguration / failure outage exploits No standardized configs; limited redundancy; weak change control affecting Network Switches/Routers, impacting confidentiality/integrity/availability. | A.8.20, A.8.21, A.8.22 | National IT Manager | 2026-03-01 | 2026-05-30
Wi-Fi Networks (Corporate / Guest) | Wireless access | Unauthorized network access | Weak segmentation; outdated encryption | 3 | 3 | 4 | 4 | 3 | 12 | National IT Manager | Guest Wi‑Fi separated (partial) | Reduce | WPA3/Enterprise; segmentation; key rotation; rogue AP detection |  |  |  | 0 | CTO | Open | IT-015 | IT Services | Head Office ITD | Y | Unauthorized access / lateral movement exploits Weak segmentation; shared passwords; outdated encryption affecting Wi‑Fi Networks (Corporate/Guest), impacting confidentiality/integrity/availability. | A.8.20, A.8.21, A.8.24 | National IT Manager | 2026-03-01 | 2026-05-30
SIEM / Central Log Management | Monitoring & detection | Security events not detected | Logs not onboarded; weak alerting; short retention | 4 | 4 | 3 | 4 | 3 | 12 | National IT Manager | Basic logs; manual reviews | Reduce | Onboard critical assets; define retention; tune alerts; incident playbooks |  |  |  | 0 | CTO | Open | IT-016 | Monitoring | Head Office ITD | Y | Undetected compromise exploits Critical logs not onboarded; short retention; weak alerting affecting SIEM / Central Log Management, impacting confidentiality/integrity/availability. | A.8.15, A.8.16 | National IT Manager | 2026-03-01 | 2026-05-30
Privileged Access (Admin Accounts) | Administration | Privilege abuse / insider misuse | Shared accounts; weak approvals | 4 | 4 | 4 | 4 | 3 | 12 | National IT Manager | Some approvals; password vault (partial) | Reduce | Implement PAM; eliminate shared accounts; session logging; break-glass controls |  |  |  | 0 | CTO | Open | IT-017 | Identity & Access | Head Office ITD | Y | Privilege abuse / insider misuse exploits Shared accounts; weak approvals; no session monitoring affecting Privileged Access (Admin Accounts), impacting confidentiality/integrity/availability. | A.5.15, A.5.16, A.8.2, A.8.5 | National IT Manager | 2026-03-01 | 2026-05-30
Third-Party Integrations / APIs | Data exchange | API abuse / supply chain compromise | Weak authentication; insufficient vendor assurance | 4 | 4 | 3 | 4 | 3 | 12 | National IT Manager | API keys; contracts | Reduce | OAuth/mTLS; rate limiting; vendor security review; monitor API anomalies |  |  |  | 0 | CTO | Open | IT-018 | Business Applications | Head Office ITD | Y | API abuse / supply chain exploits Weak API auth; no rate limiting; limited vendor assurance affecting Third‑Party Integrations / APIs, impacting confidentiality/integrity/availability. | A.5.19, A.5.20, A.8.26 | National IT Manager | 2026-03-01 | 2026-05-30
DR / Failover Capability | Business continuity | Recovery failure after incident | DR not tested; unclear RTO/RPO | 3 | 3 | 5 | 5 | 2 | 10 | National IT Manager | Backups; partial DR plan | Reduce | Define RTO/RPO; annual DR test; runbooks; evidence and improvement actions |  |  |  | 0 | CTO | Open | IT-019 | Resilience | Head Office ITD | Y | Recovery failure after incident exploits DR not tested; unclear RTO/RPO; incomplete runbooks affecting DR / Failover Capability, impacting confidentiality/integrity/availability. | A.5.30, A.8.13 | National IT Manager | 2026-03-01 | 2026-05-30
Mobile Devices (phones / tablets) | Mobility | Data exposure from lost or stolen devices | No MDM; weak encryption; no remote wipe | 4 | 3 | 3 | 4 | 3 | 12 | National IT Manager | Password/PIN policy (partial) | Reduce | Deploy MDM; enforce encryption; remote wipe; conditional access; app controls |  |  |  | 0 | CTO | Open | IT-020 | Endpoints | Head Office ITD | Y | Lost/stolen device data exposure exploits No enforced MDM; weak encryption; no remote wipe affecting Mobile Devices (phones/tablets), impacting confidentiality/integrity/availability. | A.8.1, A.8.7, A.8.9 | National IT Manager | 2026-03-01 | 2026-05-30
Microsoft 365 / Outlook Classification | Email data protection | Sensitive data sent externally | Missing mandatory labeling; limited DLP | 5 | 4 | 3 | 5 | 2 | 10 | National IT Manager | User guidance; basic DLP; awareness training | Reduce | Enable mandatory labels; enforce DLP on sensitive labels; block external send for 'Confidential'; audit and alert |  |  |  | 0 | CTO | Open | IT-021 | Collaboration | Cloud Platform | Y | Sensitive data sent externally without protection exploits No mandatory labeling; users can bypass classification; limited DLP enforcement affecting Microsoft 365 / Outlook (Email Classification), impacting confidentiality/integrity/availability. | A.6.3, A.8.7, A.8.23 | National IT Manager | 2026-03-01 | 2026-05-30
Information Assets (Customer / HR / Finance) | Data governance | Improper handling of sensitive data | No formal classification; unclear ownership | 4 | 3 | 3 | 4 | 3 | 12 | National IT Manager | Ad-hoc practices; policy drafts | Reduce | Define data classes and owners; publish handling rules; integrate into systems and training |  |  |  | 0 | CTO | Open | IT-022 | Data Protection | Head Office ITD | Y | Inappropriate handling of sensitive information exploits No formal data classification and ownership; unclear handling rules affecting Information Assets (Customer, HR, Finance Data), impacting confidentiality/integrity/availability. | A.5.12, A.5.13 | National IT Manager | 2026-03-01 | 2026-05-30
Production Systems Change Process | IT change management | System outage due to uncontrolled change | Changes without review or rollback | 2 | 3 | 5 | 5 | 3 | 15 | National IT Manager | CAB exists (partial); ticketing | Reduce | Mandate risk assessment per change; emergency change controls; backout plans; post-implementation review |  |  |  | 0 | CTO | Open | IT-023 | Change Management | Head Office ITD | Y | Service outage or security weakness from uncontrolled change exploits Changes deployed without risk review or rollback plans affecting Production Systems Change Process, impacting confidentiality/integrity/availability. | A.8.32 | National IT Manager | 2026-03-01 | 2026-05-30
End-User SaaS / Shadow IT | End-user applications | Data leakage through unapproved tools | Unsanctioned SaaS; lack of monitoring | 4 | 3 | 3 | 4 | 3 | 12 | National IT Manager | Policy only | Reduce | Implement CASB; discover shadow apps; block high-risk services; provide approved alternatives |  |  |  | 0 | CTO | Open | IT-024 | Shadow IT | Head Office ITD | Y | Data leakage via unapproved tools exploits Users adopt unsanctioned apps; no discovery or blocking affecting End-User SaaS / Shadow IT, impacting confidentiality/integrity/availability. |  | National IT Manager | 2026-03-01 | 2026-05-30
Server Rooms & Network Cabinets | Physical security | Unauthorized physical access | Shared keys; weak access control | 3 | 3 | 4 | 4 | 2 | 8 | National IT Manager | Basic locks; CCTV | Reduce | Badge-controlled access; access logs; quarterly review; tamper alerts |  |  |  | 0 | CTO | Open | IT-025 | Infrastructure | Head Office Data Center | Y | Unauthorized physical access to IT infrastructure exploits Shared keys; no access logging; weak segregation affecting Server Rooms & Network Cabinets, impacting confidentiality/integrity/availability. | A.7.4, A.7.5, A.7.8 | National IT Manager | 2026-03-01 | 2026-05-30
Service Accounts | System automation | Privilege misuse | Shared or unmanaged service credentials | 5 | 4 | 4 | 5 | 2 | 10 | National IT Manager | Managed service accounts; limited privileges; password vault; periodic credential rotation | Reduce | Implement automated credential rotation; eliminate shared service credentials; monitor service account activity |  |  |  | 0 | CTO | Open | IT-026 | Identity & Access | Head Office ITD | Y | Privilege misuse exploits unmanaged or shared service credentials affecting Service Accounts, impacting confidentiality, integrity, and availability. | A.5.15, A.5.16, A.8.2 | National IT Manager | 2026-03-01 | 2026-05-30
Source Code Repositories | Software development | Code tampering | Unrestricted developer access | 5 | 4 | 4 | 5 | 2 | 10 | National IT Manager | Repository access control; branch protection rules; code review requirements | Reduce | Implement mandatory pull request review; enable commit signing; restrict direct pushes to protected branches |  |  |  | 0 | CTO | Open | IT-027 | Identity & Access | Head Office ITD | Y | Code tampering exploits unrestricted developer access affecting Source Code Repositories, impacting integrity and confidentiality. | A.8.2, A.8.5, A.8.28 | National IT Manager | 2026-03-01 | 2026-05-30
Third Party Hosted Systems | External services | Data exposure | Supplier security controls weak | 5 | 4 | 4 | 5 | 3 | 15 | National IT Manager | Vendor security assessment; contractual security clauses; periodic supplier review | Reduce | Implement formal supplier risk assessment program; require security attestations and periodic audits |  |  |  | 0 | CTO | Open | IT-028 | Identity & Access | Head Office ITD | Y | Data exposure may occur because Supplier security controls are weak. | A.5.19, A.5.20, A.5.21 | National IT Manager | 2026-03-01 | 2026-05-30
Remote Endpoints | Remote work | Unauthorized access | Home networks not secure | 5 | 4 | 4 | 5 | 4 | 20 | National IT Manager | Endpoint antivirus; VPN access control; device hardening baseline | Reduce | Deploy endpoint detection and response; enforce secure remote access policy; restrict unmanaged devices |  |  |  | 0 | CTO | Open | IT-029 | Identity & Access | Head Office ITD | Y | Unauthorized access exploits insecure home network environments affecting Remote Endpoints, | A.8.1, A.8.9 | National IT Manager | 2026-03-01 | 2026-05-30
Internet Access Gateway | Internet connectivity | Malicious download | Users downloading unsafe files | 5 | 4 | 4 | 5 | 4 | 20 | National IT Manager | Secure web gateway; URL filtering; malware scanning | Reduce | Implement advanced web filtering; sandbox downloads; restrict high-risk file categories |  |  |  | 0 | CTO | Open | IT-030 | Identity & Access | Head Office ITD | Y | Malicious download exploits unsafe user browsing behaviour affecting Internet Access Gateway. | A.8.7, A.8.23 | National IT Manager | 2026-03-01 | 2026-05-30
Logging Systems | System monitoring | Security events missed | Logs not reviewed regularly | 5 | 4 | 4 | 5 | 4 | 20 | National IT Manager | Centralized log collection; basic SIEM monitoring | Reduce | Define log review procedures; enable automated alerts; implement regular log audits |  |  |  | 0 | CTO | Open | IT-031 | Identity & Access | Head Office ITD | Y | Security events may go undetected due to inadequate log monitoring affecting Logging Systems | A.8.15, A.8.16 | National IT Manager | 2026-03-01 | 2026-05-30

## Glossary
1 | MFA
Multi-Factor Authentication (login requires more than one verification method such as password + mobile code)
2 | PAM
Privileged Access Management (system that controls and monitors administrator accounts)
3 | RBAC
Role-Based Access Control (users receive access permissions based on their job role)
4 | PIN
Personal Identification Number (numeric authentication code used for verification)
5 | SIEM
Security Information and Event Management (central platform that collects and analyzes security logs to detect threats)
6 | EDR
Endpoint Detection and Response (advanced monitoring and threat detection on computers and laptops)
7 | AV
Antivirus (software that detects and removes malicious software)
8 | BEC
Business Email Compromise (fraud attack where criminals impersonate executives or suppliers through email)
9 | DLP
Data Loss Prevention (technology preventing sensitive information from being leaked or shared improperly)
10 | DB
Database (structured storage system used to store operational or customer data)
11 | VPN
Virtual Private Network (secure encrypted connection used for remote access to company network)
12 | IP
Internet Protocol Address (unique network address assigned to devices on a network)
13 | NAC
Network Access Control (system that restricts which devices are allowed to connect to the network)
14 | AWS
Amazon Web Services (cloud infrastructure platform used to host systems and data)
15 | API
Application Programming Interface (interface allowing systems or applications to communicate with each other)
16 | CSPM
Cloud Security Posture Management (tool that monitors cloud environments for security misconfigurations)
17 | CASB
Cloud Access Security Broker (security layer that monitors and controls access to cloud services)
18 | SPF
Sender Policy Framework (email authentication mechanism preventing domain spoofing)
19 | DKIM
DomainKeys Identified Mail (cryptographic email signature verifying sender authenticity)
20 | DMARC
Domain-based Message Authentication Reporting and Conformance (policy that protects against email spoofing and phishing)
21 | MDM
Mobile Device Management (system used to control and secure company mobile devices)
22 | DR
Disaster Recovery (process for restoring systems and data after major disruption)
23 | RTO
Recovery Time Objective (maximum acceptable time to restore a system after failure)
24 | RPO
Recovery Point Objective (maximum acceptable amount of data loss measured in time)
25 | HA
High Availability (system design ensuring services remain operational with minimal downtime)
26 | UPS
Uninterruptible Power Supply (battery backup that provides temporary power during electricity failure)
27 | CCTV
Closed-Circuit Television (video surveillance system used for security monitoring)
28 | CAB
Change Advisory Board (group responsible for reviewing and approving system changes)

## Sheet3
Risk ID | IT Tasks
IT-001 | Enable MFA for all users; disable legacy authentication protocols; implement Conditional Access policies; deploy Privileged Access Management (PAM); perform quarterly access reviews
IT-002 | Enforce DMARC (p=reject); fully configure SPF and DKIM; enable anti-phishing policies in Microsoft Defender; enable mailbox auditing; conduct phishing simulation campaigns
IT-003 | Deploy Endpoint Detection & Response (EDR) to all endpoints; remove local admin rights; enforce patching SLA; implement application control; monitor endpoint alerts
IT-004 | Implement Role-Based Access Control (RBAC); remove excessive privileges; enable application audit logging; conduct quarterly access certification; enforce least-privilege model
IT-005 | Implement high availability architecture; deploy capacity monitoring; define RTO/RPO; conduct failover testing; monitor backup status
IT-006 | Enforce MFA for all VPN users; configure lockout policies; restrict admin access through VPN; enable anomaly detection alerts; monitor VPN authentication logs
IT-007 | Establish firewall rule review schedule; update firmware regularly; maintain configuration backups; conduct external exposure scans; document rule change approvals
IT-008 | Enable immutable backups; segregate backup admin accounts; enforce MFA for backup access; maintain offline backup copy; conduct quarterly restore tests
IT-009 | Configure private-by-default storage policies; deploy Cloud Security Posture Management (CSPM); enforce DLP policies; review storage permissions periodically; monitor public access exposure
IT-010 | Build full asset inventory; implement vulnerability scanning; define patch management SLA; enforce monthly patch cycles; monitor patch compliance
IT-011 | Enable database audit logging; implement separation of duties; restrict DB admin privileges; deploy database integrity monitoring; enforce controlled change approvals
IT-012 | Monitor environmental conditions; test UPS and generator failover; conduct preventive maintenance; define power incident runbooks; implement temperature/power alerts
IT-013 | Implement PAM for hypervisor admins; apply hypervisor patching schedule; enforce hardening baseline; restrict admin network access; forward logs to SIEM
IT-014 | Standardize network configurations; deploy automated configuration backups; implement network monitoring; enforce change management for network devices; maintain redundancy
IT-015 | Deploy WPA3-Enterprise authentication; segregate guest and corporate networks; enable network segmentation; rotate wireless keys; detect rogue access points
IT-016 | Onboard critical systems to SIEM; configure alert rules; define log retention; monitor alerts daily; develop incident response playbooks
IT-017 | Deploy Privileged Access Management; eliminate shared admin accounts; enable admin session logging; implement break-glass access procedures; conduct quarterly privilege reviews
IT-018 | Implement OAuth or secure API authentication; enable mutual TLS; configure API rate limiting; monitor API activity; conduct vendor security assessments
IT-019 | Define RTO/RPO formally; perform annual DR testing; document recovery runbooks; capture test evidence; improve recovery procedures
IT-020 | Deploy Mobile Device Management; enforce device encryption; enable remote wipe capability; enforce conditional access; restrict unmanaged devices
IT-021 | Implement mandatory email sensitivity labels; enforce DLP rules; block external sending of confidential data; monitor sensitive email events
IT-022 | Define data classification levels; assign data owners; publish handling guidelines; integrate classification into systems and training
IT-023 | Enforce change management workflow; require risk assessment for changes; implement rollback procedures; perform post-implementation reviews
IT-024 | Deploy CASB solution; discover shadow SaaS applications; block high-risk services; provide approved alternatives
IT-025 | Implement badge access control; enable physical access logging; install tamper alerts; review access quarterly
IT-026 | Implement automated credential rotation for service accounts; remove shared credentials; restrict privileges; monitor service account activity
IT-027 | Enforce pull-request code review; enable commit signing; restrict direct pushes to protected branches; enable repository audit logging
IT-028 | Conduct supplier security assessments; enforce security clauses in contracts; obtain security attestations; perform periodic vendor reviews
IT-029 | Deploy EDR for remote endpoints; enforce secure VPN usage; block unmanaged device access; enforce remote device security baseline
IT-030 | Deploy secure web gateway; enable URL filtering; sandbox file downloads; block high-risk file types
IT-031 | Define log monitoring procedures; enable automated SIEM alerts; perform regular log review audits; escalate incidents