## Slide 1
DEMOBILIZATION POLICY
Management summary

## Slide 2
Demobilization: from decision to controlled closure
1
Management summary — SMSA Demobilization Policy
Think about the exit when a major project starts. Notice periods, people, assets, contracts, data, licenses and likely exit cost should not be left until the end.
1
Decision / Trigger
Closure, relocation, project exit, transfer or major operational reduction.
2
Risk Review + MOC
Name the Owner and Lead, set key dates, assess risk and complete Management of Change.
3
Plan / Checklist
Major demobilization = full plan. Smaller low-risk change may use the simplified checklist.
4
Required Approval
Obtain approval before physical demobilization starts, except urgent emergency action.
5
Execute
Manage people, customer work, assets, contracts, site, IT, finance, legal and safety actions.
6
Verify / Inspect
Reconcile records, collect evidence, confirm handovers and complete final physical inspection.
7
Final Sign-off
All functions identified in the plan/checklist provide their required clearance.
8
Risk & Record Closure
Close, accept or transfer residual risks and keep the complete closure evidence.
Key rule: Stopping operations is not final closure
Emergency: protect people, customer property, information and SMSA assets first; document urgent actions and complete the remaining controls once stable.

## Slide 3
Who owns what
The Business / Project Owner remains accountable; each function owns and clears its part.
2
Management summary — SMSA Demobilization Policy
A
Business / Project Owner
Starts the demobilization, appoints the Lead, confirms the route and remains accountable for final closure.
C
Demobilization Lead
Coordinates the plan/checklist, action tracker, evidence, handovers, clearances, escalations and sign-off pack.
PEOPLE & CUSTOMER
ASSETS, SITE & TECHNOLOGY
COMMERCIAL, FINANCIAL & CONTROL
HR
Employee transfer, reassignment, separation and clearance.
Operations / Business
Operational closure or transfer, shipments, customer property and continuity.
Sales / Commercial
Customer communication and commercial exit obligations.
Receiving Location
Confirms readiness and formally accepts transferred work, people and responsibilities.
Inventory / Fleet
Count, reconcile, move, return or decommission assets and vehicles with evidence.
Facilities / Administration
Lease, landlord, utilities, site services, keys and physical handover.
ITD
IT assets, system access, data, licenses, telecom and technical clearance.
Security / EHS
Keep safety, security, fire/life safety and environmental controls effective until handover.
Contract Owner / Purchasing
Each owner closes or transfers its contracts; Purchasing handles POs and sourcing commitments in its control.
Finance / Insurance
Financial closure, deposits, guarantees, claims and insurance continuity.
Legal / QRM
Legal/regulatory matters and risk oversight; open risks must be properly transferred or controlled.
Internal Audit
May independently review the process and evidence; does not operate the demobilization.
Simple rule: the Demobilization Lead coordinates — but responsibility stays with the function that owns the action, contract, asset, system or risk.

## Slide 4
Final closure: when can management sign off?
Physical handover may happen earlier. Final closure needs evidence, clearance and controlled residual risk.
3
Management summary — SMSA Demobilization Policy
READY TO CLOSE
Management can approve final closure when:
✓
All functions identified in the plan/checklist have provided clearance.
✓
People outcomes and receiving ownership are documented.
✓
Customer property, cash/COD and significant assets are accounted for.
✓
Contracts, site, IT/access/data, finance/insurance and legal/regulatory matters are closed or formally transferred.
✓
If work is moving, the receiving location is ready and a fallback exists where needed.
✓
Any permitted open item has a named owner, action, target date and accepted risk position.
✓
Final sign-off is approved under the current SMSA authority.
DO NOT CLOSE
Final closure must not be approved while any of these remain uncontrolled:
HIGH RISK
An unacceptable High risk remains uncontrolled.
CUSTOMER PROPERTY / CASH
Customer property or cash/COD is unaccounted for.
ASSET SHORTAGE
There is an unexplained significant asset shortage.
INSURANCE
An ongoing risk would be left without adequate insurance coverage
REGULATOR
A regulator matter requiring immediate action remains uncontrolled.
Closure principle: nothing disappears because the site or project stops. Every remaining obligation or risk must be closed, accepted or transferred to a named owner.