## Closure Checklist Detailed
SMSA Demobilization Closure Checklist
Site / Project / Operation |  | Location / Country |  |  | Demobilization Type
Business / Project Owner |  | Demobilization Lead |  |  | Last Operating Date
Receiving Site / Function |  | Target Final Closure Date |  |  | Checklist Date
All applicable items must be completed and supported by evidence before final closure. Select Yes, No or N/A. Any No item must have a responsible owner, action and target date. N/A must include a reason.
Each function must carry out its demobilization activities in accordance with its applicable approved policies, procedures, work instructions and controls. This document lists overall demobilization requirements per responsible function and does not replace departmental processes.
Section | Minimum Closure Check |  | Yes / No / N/A | Responsible Function | Evidence / Comments / Open Action |  | Target Date
People | Have all SMSA employees been relocated, reassigned or formally separated? |  |  | HR / Business Owner
People | Has every transferred employee been assigned a receiving manager/location and effective date? - as per SMSA policies |  |  | HR / Receiving Manager
People | Has outsourced manpower been reduced, transferred or closed with the manpower provider? |  |  | Contract Owner / HR as applicable
People | Have employee and contractor system, physical and operational access rights been removed or transferred? |  |  | HR / ITD / Security
People | Has SMSA property issued to employees or contractors been returned or formally transferred? |  |  | Inventory / Business Owner
Assets & Equipment | Has a complete physical asset check been completed and reconciled to Inventory records? |  |  | Inventory / Asset Custodian
Assets & Equipment | Does every SMSA-owned asset have an approved destination? |  |  | Inventory / Business Owner
Assets & Equipment | Has the asset register been updated for all transfers, storage, auction referrals or approved disposals? |  |  | Inventory
Assets & Equipment | Have rented, leased, customer-owned, supplier-owned and landlord-owned items been returned or transferred with evidence? |  |  | Contract Owner / Inventory
Assets & Equipment | Have vehicles, MHE and specialist equipment been transferred, returned or decommissioned through the responsible process? |  |  | Fleet / Technical Custodian
Customer Items & Operations | Are all shipments fully accounted for, reconciled and transferred to the appropriate destination? |  |  | Operations/ SSC
Customer Items & Operations | Is all customer inventory fully accounted for, reconciled and transferred or returned to the appropriate location/party? |  |  | Operations
Customer Items & Operations | Has customer property been returned or formally transferred? |  |  | Operations / Sales
Customer Items & Operations | Have returns, overgoods and COD/cash been reconciled? |  |  | Operations/ SSC/ Finance
Customer Items & Operations | Where work is transferred, is the receiving location ready and has custody been formally handed over? |  |  | Business Owner / Receiving Site
Customer Items & Operations | Have required customer and stakeholder communications been completed? |  |  | Sales / Business Owner
Contracts & Vendors | Have customer/commercial contract obligations been closed or transferred? |  |  | Sales / Commercial / Legal
Contracts & Vendors | Have logistics, project, warehousing, transport and other operational service contracts been closed, reduced or transferred? |  |  | Logistics / Project / Contract Owner
Contracts & Vendors | Have outsourced manpower contracts been closed, reduced or transferred? |  |  | Contract Owner / HR / Legal
Contracts & Vendors | Have facility-related contracts such as cleaning, pest control, security, maintenance, waste and utilities been addressed? |  |  | Facilities / Administration
Contracts & Vendors | Have rented-equipment and other recurring service arrangements been reviewed and closed or transferred? |  |  | Contract Owner
Contracts & Vendors | Have Purchasing-owned POs or sourcing commitments been closed where applicable? |  |  | Purchasing / Requesting Function
Contracts & Vendors | Has written cancellation, expiry, transfer or reassignment confirmation been obtained where required? |  |  | Contract Owner
Contracts & Vendors | Have continuing charges, penalties, deposits and guarantees been identified and addressed? |  |  | Finance / Contract Owner / Legal
Facility | Has the landlord/site handover been completed? |  |  | Facilities / Administration
Facility | Have keys, badges and access cards been returned, transferred or cancelled? |  |  | Facilities / Security
Facility | Have utilities and facility services been closed or transferred? |  |  | Facilities / Administration
Facility | Has SMSA signage/branding been removed where required? Has removed signage/branding been returned, stored, reused or disposed of through the approved process, as applicable? |  |  | Facilities / Administration/Marketing
Facility | Have safety, security, CCTV and fire/life-safety controls remained effective until handover? |  |  | Security / EHS
Facility | Has waste and any controlled material been removed through the approved process? |  |  | Facilities / EHS
Facility | Has the final facility inspection been completed and photographs retained where applicable? |  |  | Demobilization Lead / Facilities
IT & Information | Has IT equipment been recovered or transferred and IT asset records updated? |  |  | ITD
IT & Information | Has system, email, network, VPN, privileged and other access been removed or changed as required? |  |  | ITD
IT & Information | Has vendor, third-party and customer-portal access been removed where no longer required? |  |  | ITD / System Owner
IT & Information | Has SMSA and customer information been protected, transferred, retained or securely deleted as required? |  |  | ITD / Business Owner
IT & Information | Have software licences, telecom lines, internet and IT support arrangements been closed or transferred? |  |  | ITD
IT & Information | Have required records been transferred or stored correctly? |  |  | Business Owner / Record Owner
Finance & Insurance | Have all relevant accounts/ balances been reconciled and outstanding invoices, accruals and closure costs identified and recorded? |  |  | Finance
Finance & Insurance | Have deposits, guarantees, prepayments and recoverable balances been accounted for? |  |  | Finance
Finance & Insurance | Are all open financial commitments known and assigned? |  |  | Finance / Business Owner
Finance & Insurance | Has COD, petty cash, advances and other company money been cleared? |  |  | Finance / Operations
Finance & Insurance | Have asset auction/disposal entries and any related proceeds been recorded where applicable? |  |  | Finance / Inventory
Finance & Insurance | Have claims and recoveries been identified and assigned? |  |  | Finance / Business Owner
Finance & Insurance | Has Finance/Insurance reviewed whether the closure, relocation or asset movement affects insurance coverage? |  |  | Finance / Insurance
Finance & Insurance | Has the broker/insurer been notified and any premium/coverage adjustment recorded where required? |  |  | Finance / Insurance
Finance & Insurance | Are open insurance claims still assigned and being followed after closure? |  |  | Finance / Insurance
Legal & Regulatory | Have affected licences, permits, registrations and regulatory approvals been cancelled, transferred, amended, renewed or retained as required? |  |  | Legal / Business Owner
Legal & Regulatory | Have required regulator notifications, correspondence or formal approvals been completed? |  |  | Legal
Legal & Regulatory | Have open regulator NCs, notices, inspection findings and corrective actions been reviewed and updated? |  |  | Legal / Relevant Function
Legal & Regulatory | Does every continuing regulatory matter have a named owner and target date? |  |  | Legal / Relevant Function
Legal & Regulatory | Have legal disputes, claims, legal holds and evidence-preservation requirements been addressed? |  |  | Legal / QRM as applicable
Risk / Incident / Final Closure | Has the demobilization risk assessment been completed and updated where required? |  |  | Business Owner / QRM
Risk / Incident / Final Closure | Have significant risks been addressed and continuing risks transferred to a named Risk Owner? |  |  | Business Owner / QRM
Risk / Incident / Final Closure | Have incidents, shortages, losses, suspected theft/fraud or investigations identified during demobilization been reported and assigned? |  |  | Business Owner / QRM
Risk / Incident / Final Closure | Have all required functional clearances been completed? |  |  | Demobilization Lead
Risk / Incident / Final Closure | Have all remaining open items been assigned a named owner, action and target date? |  |  | Demobilization Lead / Business Owner
Risk / Incident / Final Closure | Has final closure been approved under the current SMSA authority as per approved Org structure & DOA? |  |  | Business / Project Owner / Approving Authority
Checklist Summary | Total Items |  | Yes | No | N/A | Ready for Final Closure?
| 57 |  | 0 | 0 | 0 | INCOMPLETE
Final Sign-Off
Role | Name | Confirmation |  | Date | Signature / Approval Reference |  | Comment
Demobilization Lead |  | Checklist complete and evidence attached
Business / Project Owner |  | Confirms all applicable items are complete or formally assigned
Final Approving Authority |  | Final closure approved under current SMSA approved Structure & DOA
Final closure must not be approved while a uncontrolled issue remains, including unaccounted customer property, an unexplained asset shortage, an insurance coverage gap, a regulator matter requiring immediate action, or an unacceptable open risk.

## Tracker
Final Functional Sign Off Tracker
Function | Name | Clearance Status | Date | Approval | Signature Ref / Comment
Business / Project Owner |  | Open
Operations / Logistics
HR
Sales / Commercial
Finance / Insurance |  | Cleared
Inventory / Fleet |  | N/A
ITD / Information Security
Facilities / Administration /Marketing
Security / EHS
Legal
QRM
Receiving Site / Function

## Demobilization Sign Off Tracker (hidden)
SMSA Demobilization Sign Off & Tracking Checklist
Site / Project / Operation |  |  | Demobilization Type |  |  | Business / Project Owner
Location / Country |  |  | Last Operating Date |  |  | Demobilization Lead
Reason for Closure / Move |  |  | Target Final Closure |  |  | Receiving Site / Function
Use one form for each demobilization. Mark Complete, Open or N/A. N/A needs a reason. Every Open item must show an owner, target date and next action.
No. | Area | Control / Sign Off Check |  |  | Status | Responsible Owner | Target Date | Evidence / Open Action / Comment
1 | Planning | Demobilization approved; owner, lead, last operating date, target closure date and receiving arrangement confirmed. |  |  | Open
2 | People | SMSA employees transferred, reassigned or separated with approved HR records and receiving owner where applicable.
3 | People | Outsourced manpower supplier notified; worker status, SMSA assets, badges, keys and access cleared.
4 | Operations | Customer/service continuity completed and required customer/stakeholder communication issued.
5 | Operations | Shipments, customer inventory/property, returns, overgoods and COD/cash fully reconciled or formally transferred.
6 | Assets | SMSA owned assets physically counted and reconciled to Inventory records.
7 | Assets | SMSA assets transferred/stored/auction referred/disposed with records; rented/third party items returned to the legal owner.
8 | Assets | Fleet, MHE and specialist equipment transfer/return/decommissioning completed with technical records. |  |  | Complete
9 | Contracts | Customer/commercial and logistics/project/manpower contracts closed, reduced or transferred with written evidence.
10 | Facilities | Lease/landlord handover completed and facility services/PO commitments closed or transferred where applicable.
11 | IT / Access | IT assets, systems, email/VPN/vendor/customer portal/physical access reviewed and removed or transferred.
12 | IT / Access | Data, software licences, telecom lines, internet and technology support arrangements transferred or closed.
13 | Safety / Security | Safety, security, CCTV, fire/life safety and environmental controls maintained until handover; waste handled correctly.
14 | Finance | Final invoices, accruals, deposits, guarantees, cash/COD, claims, recoveries and other financial obligations reviewed and recorded.
15 | Insurance | Finance/Insurance confirmed broker/insurer notification, coverage changes, premium impact and open claim status where applicable.
16 | Legal / Regulatory | Licences, permits, registrations and regulatory approvals cancelled, transferred, amended, renewed or retained as required.
17 | Legal / Regulatory | Regulator notices, open NCs and corrective actions updated; continuing items have a named owner and target date.
18 | Risk / Incident | Open risks, incidents, investigations, claims, legal holds and evidence requirements closed or formally transferred to named owners. |  |  | N/A
19 | Final Inspection | Final physical inspection completed; no unaccounted assets/customer property, uncontrolled access, records or waste remain.
20 | Final Closure | All required functional clearances completed and final closure approved.
Checklist Summary |  |  |  |  | Complete | Open | N/A | Ready for Final Closure?
Formulated Area on right do not input manually |  |  |  |  | 1 | 1 | 1 | NO
Final Functional Sign Off Tracker
Function |  | Name |  | Clearance Status |  | Date | Approval / Signature Ref / Comment
Business / Project Owner |  |  |  | Open
Operations / Logistics
HR
Sales / Commercial
Finance / Insurance |  |  |  | Cleared
Inventory / Fleet |  |  |  | N/A
ITD / Information Security
Facilities / Administration
Security / EHS
Legal
QRM
Receiving Site / Function
Do not approve final closure while a uncontrolled issue remains, including unaccounted customer property, material asset shortage, insurance coverage gap, regulator matter requiring immediate action, or unacceptable open risk.