## Country-SWOT
IBU Egypt SWOT
Strengths • One-stop shop solution (variety of services) • Strong infrastructure (fast-growing network) • Providing COD service within Gulf Area & Egypt • SMSA has a strong presence and network across the country with numerous branches. • Experience and efficient Customs Clearance team. • Operate inside our own clearance facility at Airport • Obtained all required licenses (i.e. EIFFA, FIATA, Consolidation, Civil aviation...etc.) • ISO Certification Alignment: SMSA Egypt is ISO 9001 certified, backed by KSA HQ’s comprehensive Integrated Management System (ISO 9001, 45001, 14001, 10002, 10015, and 27001) • Good medical insurance benefits for all employees • Online training programs • Employee recognition programs •Quality standards for operational processes and commitment fulfillment • Automated Billing system • ERP system implementation • Fulfilment and logistic service • GPS tracking system |  | Weaknesses • Lack of marketing activities & authority • Unavailability of an alternative Bank account for SMSA Egypt (Bank account with another bank) • Third party challenges for our international and domestic business • Very limited clearance facility space • Outdated Core system • Absence of the integration between ECOM and billing systems (Customer COD amount visibility)
Opportunities • SDC (Diplomat sector) • Upgrade our current technology/system integration • Ongoing re-engineering of courier and linehaul routes for more effectiveness, efficiency, and cost reduction • Freight outbound business & Land Freight services • Implement new UPS for HQ Server room to cover 90 Minutes • Retention and career path program. • Rewarding Programs. • Apply booking & tracking via the IVR system & Customer application • Sales restructure for more specialized focus |  | Threats • Egyptian Pound floating led to inflation that affects employees' retention and new hiring. • Regular unplanned increases in Fuel price • Business continuity (i.e. electricity, internet stability) • USD unavailability negatively impacted international business, especially imports. • Political instability and Red Sea crisis in Middle East region • Price war especially from unlicensed operators in Egypt • Unexpected Governmental regulations and decisions that affect the Company or employee( i.e., Income tax, minimum wages) • Tax authorities inspection that increase our cost and negatively impact our cash flow • Climate Change

## Country-Risk
Risk Register
Department | CORP | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
IT-SR-01 | Cybersecurity | Lack of sufficient IT staff affecting IT operations | Limited staffing compared to business needs | SWOT | 2 | 3 | 6 | CTO | Current IT team structure | Reduce | Assess staffing requirements and recruit additional IT personnel; provide training for existing staff where required | IT National Manager / HR | 2026-09-30 | 2 | 2 | 4 | FA | Open | 2026-03-01 | 2026-06-01 | Open | FC - Fully Compliant
EGY-CORP-SR-01 | Strategic | Lack of marketing activities & authority | Insufficient marketing support and limited authority to execute local marketing initiatives. | SWOT | 3 | 2 | 6 | Marketing KSA HQ | Marketing activities, promotional campaigns, giveaways, and collaboration with external marketing agencies to improve brand visibility and lead generation. | Reduce | Continue collaboration with external marketing agencies to enhance brand awareness, improve lead generation, and support market growth initiatives. | MD | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-02 | Operational | Third party challenges for our international and domestic business | Dependency on third-party service providers with limited control over their pricing, service quality, and operational processes. | SWOT | 3 | 3 | 9 | OPS | Service Level Agreements (SLAs) with third parties and continuous performance monitoring to maintain service quality and pricing stability. | Reduce | Maintain regular performance reviews with third-party providers and continue linehaul improvement initiatives to enhance service quality and cost efficiency. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-03 | Operational | Very limited clearance facility space | Insufficient customs clearance facility capacity to support current and future business volumes. | SWOT | 3 | 2 | 6 | CGM /OPS | Ongoing coordination with authorities and EgyptAir to secure additional customs clearance facility space. | Reduce | Continue follow-up with EgyptAir and relevant authorities to secure additional clearance facility space. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-04 | IT | Outdated Core system | Legacy system limitations and delayed system modernization. | SWOT | 3 | 2 | 6 | KSA HQ | Daily monitoring of system updates and preparation of manual operational reports to compensate for system limitations. | Reduce | Continue monitoring daily reports and implement necessary corrective actions until system modernization is completed. | KSA IT Team | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-05 | Operational | Absence of on-time shipment visibility for domestic shipments | Lack of real-time tracking integration and shipment visibility for domestic operations. | SWOT | 3 | 2 | 6 | OPS | Continuous monitoring and performance improvement initiatives with third-party providers. | Reduce | Improve coordination with third-party providers and enhance shipment visibility reporting processes. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-06 | IT | Business continuity (i.e. electricity, internet stability) | Dependence on external utilities and communication infrastructure subject to service interruptions. | SWOT | 3 | 2 | 6 | IT | Data backup procedures and user awareness to ensure information availability during infrastructure outages. | Reduce | Implement UPS solution and strengthen business continuity arrangements for critical infrastructure. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-07 | Financial | Egyptian Pound floating led to inflation that affects employees' retention and new hiring. | Currency devaluation and inflationary pressures increasing operating and employee-related costs. | SWOT | 3 | 3 | 9 | EGY MGT | Annual salary and BSI review, employee engagement programs, retention initiatives, rate adjustments, and operational cost optimization. | Reduce | Continue cost optimization initiatives, salary structure reviews, retention programs, and revenue enhancement actions. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-08 | Compliance | Unexpected Governmental regulations and decisions that affect the Company or employee i.e., Income tax, Social Insurance, Pandemic Tax | Changes in government regulations, taxation, and labor requirements beyond company control. | SWOT | 3 | 2 | 6 | HR | Annual salary review, employee engagement initiatives, and retention programs to reduce employee impact. | Accept | Continue employee retention initiatives, monitor regulatory changes, and review compensation structures when required. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-09 | Financial | USD unavailability negatively impacted international business specially imports. | Foreign currency shortage affecting international transactions and import activities. | SWOT | 3 | 3 | 9 | Finance | Business focus diversification toward export services, especially airfreight operations. | Reduce | Continue focusing on export business opportunities and monitor foreign currency availability impacts on operations. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-10 |  | Regular unplanned increases in Fuel price | Frequent fuel price increases driven by market and governmental factors. | SWOT | 3 | 3 | 9 | Sales | Periodic fuel surcharge review and adjustment of domestic rates in line with market changes. | Reduce | Review and adjust fuel surcharge and customer pricing whenever significant fuel price increases occur. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-11 | Financial | Unavailability of an alternative Bank account for SMSA Egypt (Bank account with another bank) | Reliance on a single banking relationship without an approved alternative banking arrangement. | SWOT | 3 | 2 | 6 | KSA HQ | Escalation to management and evaluation of alternative banking solutions. | Reduce | Continue coordination with management and complete evaluation and opening of an alternative banking account. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-12 | IT | Absence of the integration between ECOM and billing systems (Customer COD amount visibility) | Lack of system integration between ECOM and billing platforms. | SWOT | 3 | 3 | 9 | Egypt Finance/KSA IT | Oracle Fusion implementation project to improve system integration and financial visibility. | Reduce | Complete Oracle Fusion implementation and system integration activities. | Finance Manager & IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-13 | External | Political instability in the Middle East | Regional geopolitical instability affecting transportation routes and trade activities. | SWOT | 2 | 2 | 4 | Sales | Utilization of alternative shipping routes and Mediterranean ports when required. | Accept | Continue utilizing alternative routing options and monitor geopolitical developments affecting logistics operations. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-14 | Strategic | Price war especially from unlicensed operators in Egypt | Aggressive market competition from operators offering unsustainably low pricing. | SWOT | 3 | 3 | 9 | Sales | Competitive pricing strategy focusing on key cities and high-potential market segments. | Reduce | Continue market-focused pricing strategies and strengthen competitive positioning in key cities and sectors. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-15 | Financial | Cash collection risk | Cash handling and transportation activities exposing the company to loss, theft, or collection errors. | SWOT | 3 | 3 | 9 | Operations | System monitoring, cash remittance tracking, strengthened disciplinary controls, and legal escalation procedures. | Reduce | Strengthen cash monitoring controls, remittance tracking, disciplinary measures, and legal escalation procedures when required. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CORP-SR-16 | External | Climate Change | Increasing frequency of extreme weather conditions affecting operations and service delivery. | SWOT | 2 | 1 | 2 | Operations | Emergency response planning, flexible delivery scheduling, driver safety training, alternative logistics arrangements, and enhanced maintenance programs. | Reduce | Maintain emergency response procedures, safety training, alternative logistics arrangements, and enhanced maintenance programs. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
Note on R3: FC - Fully Compliant FA - Further Action Required

## Sales-SWOT
Sales Department - IBU Egypt
Strengths • One-stop shop solution (variety of services) • Providing COD service within Gulf Area & Egypt • SMSA has a strong presence and network across the country with numerous branches. • Experience and efficient Customs Clearance team. • Operate inside our own clearance facility at Airport • Obtained all required licenses (i.e. EIFFA, FIATA, Consolidation, Civil aviation...etc.) • ISO Certification Alignment: SMSA Egypt is ISO 9001 certified, backed by KSA HQ’s comprehensive Integrated Management System (ISO 9001, 45001, 14001, 10002, 10015, and 27001) • Advanced real-time GPS tracking and fleet monitoring technology. • Digitalized operational workflows and customer relationship management supported by ZOHO platforms. • Quality standard for OPS process & meet our commitment • Highly competitive sales incentive and commission structure driving commercial performance. |  | Weaknesses • Lack of marketing activities & authority • Delay in COD payment cycle • Third party challenges for our international business • Absence of published import rate card • High inter-company' charges (ICBRS) lead to uncompetitive rates • Outdated Core system
Opportunities • Sales restructure for more specialized focus-Added • High potential market • Fulfilment and logistic service • Banking sector penetration • SDC (Diplomat sector) • Upgrade our current technology/system integration • ERP system implementation • Apply booking via the IVR system & Customer application • Shipment tracking via IVR • Automated Billing system • Freight outbound business & Land Freight services |  | Threats • Regular unplanned increases in Fuel price • Egyptian Pound floating led to inflation that affects employees' retention and new hiring. • USD unavailability negatively impacted international business specially import. • Political instability in the Middle East • Price war especially from unlicensed operators in Egypt • Unexpected Governmental regulations and decisions that affect the Company or employee( i.e., Income tax, minimum wages)

## Sales-Risk
Risk Register
Department | Sales | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-SLS-SR-01 | Operational | Third party challenges for our international business | Dependence on third-party service providers with limited control over service quality, transit time, and pricing. | SWOT | 3 | 3 | 9 | Operations | We obtained our own clearance facility that allowed us to send direct linehaul to KSA & Dubai. We are already integrated with the third party and operate our own linehaul services. | Reduce | Maintain regular performance reviews with third-party providers and continue linehaul improvement initiatives to enhance service quality and operational efficiency. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-02 | Strategic | Lack of marketing activities & authority | Insufficient marketing support and limited authority to execute local marketing initiatives. | SWOT | 3 | 2 | 6 | Marketing KSA HQ | Marketing activities, promotional campaigns, giveaways, and collaboration with external marketing agencies to improve brand visibility and lead generation. | Reduce | Continue collaboration with external marketing agencies to enhance brand awareness, improve lead generation, and support market growth initiatives. | MD | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-03 | IT | System Issues (Integration and client ticketing tool) | Lack of full system integration and limitations in customer ticketing and reporting tools. |  | 1 | 2 | 2 | IT |  | Reduce | Complete testing and deployment of the new ticketing system and implement system integration improvements. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-04 | IT | Outdated Core system | Legacy system limitations and delayed system modernization. | SWOT | 3 | 2 | 6 | KSA HQ | Daily monitoring of system updates and preparation of manual operational reports to compensate for system limitations. | Reduce | Continue monitoring daily reports and implement necessary corrective actions until system modernization is completed. | KSA IT Team | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-05 | Strategic | Price war especially from unlicensed operators in Egypt | Aggressive market competition from operators offering unsustainably low pricing. | SWOT | 3 | 3 | 9 | Sales | Competitive pricing strategy focusing on key cities and high-potential market segments. | Reduce | Continue market-focused pricing strategies and strengthen competitive positioning in key cities and sectors. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-06 | Financial | Egyptian Pound floating led to inflation that affects employees' retention and new hiring. | Currency devaluation and inflationary pressures increasing operating and employee-related costs. | SWOT | 3 | 3 | 9 | EGY MGT | Annual salary and BSI review, employee engagement programs, retention initiatives, rate adjustments, and operational cost optimization. | Reduce | Continue cost optimization initiatives, salary structure reviews, retention programs, and revenue enhancement actions. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-07 | Financial | High inter-company charges (ICBRS) lead to uncompetitive rates | High internal cost allocations resulting in reduced market competitiveness and pricing flexibility. | SWOT | 3 | 3 | 9 | Finance | Escalation to CGM and Finance Management supported by market analysis and competitor benchmarking. | Reduce | Continue coordination with Finance and Management to review inter-company pricing and improve market competitiveness. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-08 | Financial | USD unavailability negatively impacted international business specially imports. | Foreign currency shortage affecting international transactions and import activities. | SWOT | 3 | 3 | 9 | Finance | Business focus diversification toward export services, especially airfreight operations. | Reduce | Continue focusing on export business opportunities and monitor foreign currency availability impacts on operations. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-09 | External | Political instability in the Middle East | Regional geopolitical instability affecting transportation routes and trade activities. | SWOT | 2 | 2 | 4 | Sales | Utilization of alternative shipping routes and Mediterranean ports when required. | Accept | Continue utilizing alternative routing options and monitor geopolitical developments affecting logistics operations. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-10 | Operational | Absence of published import rate card | Lack of standardized import pricing structure and delayed rate communication. | SWOT | 3 | 3 | 9 | Sales | Exploration of new vendors with fixed rate cards and standardized pricing structures. | Reduce | Finalize import rate card development and maintain regular review of vendor pricing structures. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-11 | Financial | Regular unplanned increases in Fuel price | Frequent fuel price increases driven by market and governmental factors. | SWOT | 3 | 3 | 9 | Sales | Periodic fuel surcharge review and adjustment of domestic rates in line with market changes. | Reduce | Review and adjust fuel surcharge and customer pricing whenever significant fuel price increases occur. | Sales Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-SLS-SR-12 | Operational | Delivery of COD shipments, on time COD remittance, & HV shipments | Cash handling, shipment security, and operational process gaps affecting COD remittance and high-value shipment management. | SWOT | 3 | 3 | 9 | OPS | ERP monitoring, HV process compliance, staff training, shipment monitoring, barcode scanning controls, and daily COD follow-up procedures. | Reduce | Strengthen ERP monitoring, enforce HV process compliance, enhance staff training, and maintain daily COD follow-up and shipment monitoring controls. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## CS-SWOT
CS Department - IBU Egypt
Strengths • Automated E-com system (SECOM):( Customer Dashboard, Ability to view the status of shipments) • Cisco system solution ( Hotline number ) • TSF system. • Validation team • Key accounts helpdesk. |  | Weaknesses • Absence of on-time shipment visibility for domestic shipments from third party side. • Ongoing issue with ticketing system reports • Restrictions from third party co. (international)
Opportunities • Restructuring the CS team to meet the volume increase and customers' requirements . • Apply booking via the IVR system & Customer application • Shipment tracking via IVR • Apply a new system for complaint shipments received by customers. |  | Threats • Network disconnection

## CS-Risk
Risk Register
Department | Sales & CS | Section | CS | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-CS-SR-01 | Operational | Restrictions from third-party companies regarding international shipments. | Dependence on third-party service providers with limited control over response time, shipment updates, and service performance. | SWOT | 3 | 3 | 9 | Opetations | Daily follow-up with third-party service providers to monitor shipment status and ensure timely customer updates. | Reduce | Maintain regular coordination with third-party providers and conduct periodic performance reviews to improve response time and customer service quality. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CS-SR-02 | IT | Network disconnection | Dependence on external network and communication infrastructure that may experience service interruptions or connectivity failures. | SWOT | 3 | 3 | 9 | IT | Alternative network connectivity arrangements and business continuity procedures to maintain customer service operations during network interruptions. | Reduce | Implement and maintain backup connectivity solutions and strengthen business continuity arrangements to ensure uninterrupted customer service operations. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CS-SR-03 | Operational | Absence of on-time shipment visibility for domestic shipments | Lack of real-time tracking integration and limited shipment visibility from third-party service providers. | SWOT | 3 | 2 | 6 | Opetations | Continuous performance monitoring and reporting follow-up with third-party providers to improve shipment visibility and customer communication. | Reduce | Improve coordination with third-party providers and enhance shipment visibility reporting processes to provide accurate customer updates. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-CS-SR-04 | IT | Ongoing problem with ticketing system reports | System limitations and reporting issues affecting the accuracy and availability of ticketing system data. | SWOT | 3 | 2 | 6 | IT | Ongoing system monitoring, escalation to IT, and regular review of ticketing system performance and reporting accuracy. | Reduce | Continue system performance monitoring, resolve reporting issues, and implement required system enhancements in coordination with IT. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## FIN-SWOT
FIN Department - IBU Egypt
Strengths • SECOM system for COD AP issuance • CPS Banking governmental payment system setup • ERP system implementation in progress |  | Weaknesses • Absence of integration between ECOM and billing systems (Customer COD amount visibility) • Unavailability of an alternative Bank account for SMSA Egypt (Bank account with another bank)
Opportunities •Automated billing system implementation |  | Threats •Inflation impact on operations cost • Tax authority inspections that increase our costs and negatively impact our cash flow

## FIN-Risk
Risk Register
Department | Finance | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-FIN-SR-01 | IT | Absence of the integration between ECOM and billing systems (Customer COD amount visibility) | Lack of system integration between ECOM and billing platforms. | SWOT | 3 | 3 | 9 | Finance | Oracle Fusion implementation project to improve system integration and financial visibility. | Reduce | Complete Oracle Fusion implementation and system integration activities to improve financial visibility and reporting accuracy. | Finance Manager & IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
| Financial | Unavailability of an alternative Bank account for SMSA Egypt (Bank account with another bank) | Reliance on a single banking relationship without an approved alternative banking arrangement. |  | 3 | 2 | 6 | KSA HQ | Escalation to management and evaluation of alternative banking solutions. | Reduce | Continue coordination with management and complete evaluation and opening of an alternative banking account. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
| Compliance | Tax authority inspections that increase our costs and negatively impact our cash flow | Regulatory inspections, tax assessments, and tax authority requirements that may increase operational costs and negatively affect cash flow. |  | 3 | 3 | 9 | Finance | Tax consultant engagement, ongoing tax case management, regulatory compliance monitoring, and coordination with tax authorities. | Reduce | Continue coordination with tax consultants, monitor ongoing tax cases, and ensure compliance with all regulatory and tax authority requirements. | Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
| Financial | Inflation impact on Operations cost | Inflationary pressures and increasing operational costs affecting profitability, cash flow, and business sustainability. |  | 3 | 3 | 9 | EGY MGT | Retention plan, domestic rate adjustments, operational cost optimization, and periodic financial reviews. | Reduce | Continue cost optimization initiatives, pricing reviews, retention programs, and revenue enhancement actions. | HR Manager / CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## OPS-SWOT
OPS Department - IBU Egypt
Strengths • One-stop shop solution (variety of services) • Strong infrastructure (fast-growing network) • SMSA has a strong presence and network across the country with numerous branches. • Experience and efficient Customs Clearance team. • Operate inside our own clearance facility at Airport • Quality standards for operational processes and commitment fulfillment • GPS tracking system |  | Weaknesses • Third party challenges for our international and domestic business • Very limited clearance facility space • Outdated Core system • Absence of on-time shipment visibility for domestic shipments
Opportunities • Fulfilment and logistic service • First-mile solution • Upgrade our current technology/system integration • Ongoing re-engineering of courier and linehaul routes for more effectiveness, efficiency, and cost reduction |  | Threats • Cash collection risk • Climate Change

## OPS-Risk
Risk Register
Department | Operations | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-OPS-SR-01 | Operational | Very limited clearance facility space | Insufficient customs clearance facility capacity to support current and future business volumes. | SWOT | 3 | 2 | 6 | CGM /OPS | Ongoing coordination with authorities and EgyptAir to secure additional customs clearance facility space. | Reduce | Continue follow-up with EgyptAir and relevant authorities to secure additional clearance facility space. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-OPS-SR-02 | IT | Outdated Core system | Legacy system limitations and delayed system modernization. | SWOT | 3 | 2 | 6 | KSA HQ | Daily monitoring of system updates and preparation of manual operational reports to compensate for system limitations. | Reduce | Continue monitoring daily reports and implement necessary corrective actions until system modernization is completed. | KSA IT Team | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-OPS-SR-03 | Operational | Absence of on-time shipment visibility for domestic shipments | Lack of real-time tracking integration and shipment visibility for domestic operations. | SWOT | 3 | 2 | 6 | Operations | Continuous performance monitoring and reporting follow-up with third-party providers to improve shipment visibility and operational communication. | Reduce |  | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-OPS-SR-04 | Operational | Third party challenges for our international and domestic business | Dependency on third-party service providers with limited control over their pricing, service quality, and operational processes. | SWOT | 3 | 3 | 9 | OPS | Service Level Agreements (SLAs) with third parties and continuous performance monitoring to maintain service quality and pricing stability. | Reduce | Maintain regular performance reviews with third-party providers and continue linehaul improvement initiatives to enhance service quality and cost efficiency. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-OPS-SR-05 | Financial | Cash collection risk | Cash handling and transportation activities exposing the company to loss, theft, or collection errors. | SWOT | 3 | 3 | 9 | Operations | System monitoring, cash remittance tracking, strengthened disciplinary controls, and legal escalation procedures. | Reduce | Strengthen cash monitoring controls, remittance tracking, disciplinary measures, and legal escalation procedures when required. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-OPS-SR-06 | External | Climate Change | Increasing frequency of extreme weather conditions affecting operations and service delivery. | SWOT | 2 | 1 | 2 | Operations | Emergency response planning, flexible delivery scheduling, driver safety training, alternative logistics arrangements, and enhanced maintenance programs. | Reduce | Maintain emergency response procedures, safety training, alternative logistics arrangements, and enhanced maintenance programs. | Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## IT-SWOT
IT Department - IBU Egypt
Strengths • Cisco IP Telephone in HO • SDSL Line in HO with a backup plan • Firewall In HO EG • IP Cams Existence in HO EG and Branches • Monitoring the printing process for the printer server and Papercut Application • Billing System for Egypt • VPN Site to Site HO to RUH • Stable Data Transfer between employees through QNAP Share Folder • Data Backup from users to QNAP Server • All SMSA Employees have a Company SIM Card with free internal calls • SDC server local in SMSA Egypt • Local server for E-Invoice • Oracle for Finance |  | Weaknesses • No Firewall in SMSA Egypt Outside HO Branches
Opportunities • Implementing a new Server Backup device for SMSA Egypt servers (high availability) • Implement new UPS for KSA HQ Server room to cover 90 Minutes • Integration between SMSA and third parties |  | Threats • Inflation in equipment's prices

## IT-Risk
Risk Register
Department | IT | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-IT-SR-01 | IT | No Firewall in SMSA Egypt Outside HO Branches | Lack of firewall protection and network security controls across branch locations outside Head Office. | SWOT | 3 | 3 | 9 | IT | User awareness communications, internet usage controls, and planned firewall implementation across branch locations. | Reduce | Complete firewall implementation across branch locations and strengthen network security controls to enhance protection against unauthorized access and cyber threats. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-IT-SR-02 | Financial | Inflation in equipment's prices | Inflationary pressures and market fluctuations increasing the cost of IT equipment, software, and technology solutions. | SWOT | 3 | 3 | 9 | IT | Obtaining quotations in USD and expediting approval and purchasing processes to minimize the impact of price fluctuations. | Reduce | Continue obtaining quotations in USD, accelerate procurement approvals, and optimize purchasing plans to minimize the impact of equipment price increases. | IT Supervisor | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## HR-SWOT
HR Department - IBU Egypt
Strengths • Attractive incentive schemes • Comprehensive medical insurance with strong network coverage for employees and dependents • High-value facilities and company assets • Timely and accurate salary payments • Clear HR policies and procedures • Online learning and training opportunities • Professional uniforms and courier appearance • Structured HR processes and employee lifecycle management • Established HR systems and digital HCM processes • Supportive working environment and cross-functional collaboration |  | Weaknesses • Salaries are currently below market levels, and salary increments could not be implemented in 2026 due to financial constraints. • Limited face-to-face training and practical development opportunities. • Employee turnover in key positions, resulting in knowledge loss and additional recruitment and onboarding costs. • Limited career progression and internal mobility opportunities in some functions. • Difficulty attracting and retaining experienced talent due to market salary competitiveness. • High dependency on individual employees in certain specialized roles, creating business continuity risks.
Opportunities • Enhance salary structures and BSI to align with market benchmarks • Introduce performance-based commission and salary increment schemes linked to business and individual performance. • Develop structured retention and career path programs to improve employee engagement and reduce turnover. • Strengthen employee recognition and reward programs to motivate and retain high-performing employees. • Expand learning and development opportunities, including face-to-face and practical training programs. |  | Threats • Increasing competition for talent, including counteroffers from competitors to retain or attract our employees. • Unexpected changes in government regulations and legislation that may impact the Company and employees, such as income tax, social insurance, and labor regulations. • Egyptian Pound fluctuations and inflation, which may affect employees' purchasing power, salaries, and benefits. • Increasing market salary levels, creating pressure on employee retention and recruitment. • Difficulty attracting and retaining skilled talent due to competition in the logistics and courier industry. • Rising costs of employee benefits, particularly medical insurance and other employee-related expenses.

## HR-Risk
Risk Register
Department | HR & Admin | Section | - | Country | Egypt
Risk ID | Risk Category | Risk Description | Main Cause | Risk Source (ref.MORI) | Inherent Likelihood (1-3) | Inherent Impact (1-3) | Inherent Risk Score | Risk Owner | Existing Controls | Treatment Decision | Action Required / Treatment Actions | Responsible Person/ Dept | Target Date | Residual Impact (1-3) | Residual Likelihood (1-3) | Residual Risk Score | Control / Compliance Status (FC/FA/NC/NA) | Status | Last Review Date | Next Review Date
EGY-HR-SR-01 | Strategic | Employee turnover in key positions, resulting in knowledge loss and additional recruitment and onboarding costs. | Inadequate employee retention, limited career development opportunities, and increasing market competition for qualified talent. | SWOT | 3 | 2 | 6 | HRD | Current IT team structure | Reduce | Employee benefits and compensation programs, structured recruitment process, training programs, employee engagement initiatives, and retention plans. | HR Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-02 | Financial | Salaries are currently below market levels, and salary increments could not be implemented in 2026 due to financial constraints. | Financial constraints and salary levels below market benchmarks affecting employee attraction and retention. | SWOT | 2 | 2 | 4 | HRD / CGM |  |  | Salary benchmarking, employee retention initiatives, career development programs, and employee benefits review. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-03 | Operational | Limited face-to-face training and practical development opportunities. | Insufficient practical training programs and limited professional development opportunities. | SWOT | 1 | 2 | 2 | HRD |  |  | Online learning platform, annual training plans, and identification of external training requirements. | HR Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-04 | Strategic | Competitors provide a counter offer to our employees. | Intense market competition and more attractive compensation packages offered by competitors. | SWOT | 3 | 1 | 3 | HRD |  |  | Annual salary and BSI review, employee engagement initiatives, reward programs, training, and retention plans. | HR Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-05 | Compliance | Unexpected Governmental regulations and decisions that affect the Company or employee i.e., Income tax, Social Insurance, Pandemic Tax | Changes in government regulations, taxation, and labor requirements beyond company control. | SWOT | 3 | 2 | 6 | HRD | Annual salary review, employee engagement initiatives, and retention programs to reduce employee impact. | Accept | Continue employee retention initiatives, monitor regulatory changes, and review compensation structures when required. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-06 | Financial | Egyptian Pound floating led to inflation that affects employees' retention and new hiring. | Currency devaluation and inflationary pressures increasing operating and employee-related costs. | SWOT | 3 | 2 | 6 | EGY MGT | Annual salary and BSI review, employee engagement programs, retention initiatives, rate adjustments, and operational cost optimization. | Reduce | Continue cost optimization initiatives, salary structure reviews, retention programs, and revenue enhancement actions. | HR Manager/CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-07 | Strategic | Limited career progression and internal mobility opportunities in some functions. | Lack of structured career paths and limited internal promotion or mobility opportunities. | SWOT | 2 | 2 | 4 | HRD / Line Managers |  |  | Career path development, internal mobility guidelines, succession planning, and cross-functional development initiatives. | HR Manager /EGY MTM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-08 | Strategic | Difficulty attracting and retaining experienced talent due to market salary competitiveness. | Competitive labor market and salary gaps compared to industry standards. | SWOT | 3 | 2 | 6 | HRD |  |  | Employee value proposition enhancement, medical insurance coverage, salary benchmarking, and optimized recruitment channels. | HR Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-09 | Operational | High dependency on individual employees in certain specialized roles, creating business continuity risks. | Limited succession planning, insufficient cross-training, and concentration of critical knowledge in key individuals. | SWOT | 2 | 3 | 6 | HRD /EGY MTM |  |  | Cross-training programs, job rotation, SOP documentation, succession planning, and key talent identification initiatives. | HR Manager /EGY MTM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-10 | Financial | Increasing market salary levels, creating pressure on employee retention and recruitment. | Rising market salaries and increasing competition for qualified employees. | SWOT | 3 | 2 | 6 | HRD / CGM |  |  | Salary structure reviews, incentive schemes, employee recognition programs, and engagement initiatives. | HR Manager / CGM | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-11 | Strategic | Difficulty attracting and retaining skilled talent due to competition in the logistics and courier industry. | Strong competition for skilled talent within the logistics and courier sector. | SWOT | 3 | 2 | 6 | HRD / Operations |  |  | Performance-based incentive programs, employee engagement initiatives, training programs, and employer branding activities. | HR Manager / Operations Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26
EGY-HR-SR-12 | Financial | Rising costs of employee benefits, particularly medical insurance and other employee-related expenses. | Inflationary pressures and increasing healthcare and employee benefit costs. | SWOT | 3 | 2 | 6 | HRD / Finance |  |  | Annual insurance contract review, vendor negotiations, health awareness programs, and periodic employee benefits evaluation. | HR Manager / Finance Manager | 2026 / Ongoing |  |  |  | FA Residual Risk to be evaluated during the Annual Management Review in Dec-2026. | Open | Sep'26 | Dec'26

## Risk Ranking (3)
Severity
[5 empty] | Low | Medium | High
[5 empty] | Affecting location Affecting employee Affecting Satisfaction | Affecting Individual Customer Affecting SMSA Service Affecting Department | Affecting Corporate SMSA Affecting Revenue Affecting Image Affecting Govt. Regulation Affecting Key Acct customers Affecting Health & Safety
|  |  |  | (multiply) | Severity
|  |  |  | X | Low (1) | Medium (2) | High (3)
Probability | Low | Probability of incidents occuring beyond 24 months | Probability | Low(1) | Low Risk (1) | Low Risk (2) | Med Risk (3)
| Medium | Probability of incidents occuring within 12 to 24 months |  | Medium (2) | Low Risk (2) | Med Risk (4) | High Risk (6)
| High | Probability of incidents occuring within 12 months or less |  | High (3) | Med Risk (3) | High Risk (6) | High Risk (9)